## Original Bid
inhouse quotation + Contractor quotation
PROJECT TITLE: |  | Supply of labor and consumables for the Installation of Mechanical Works for Dryblending Project Phase 2 |  |  | Date: | 2021-07-20 10:11
COST CENTER: |  |  |  |  | Reference:
|  |  | In House |  |  |  |  | O and J |  |  |  |  | Fedcon |  |  |  |  | Acepack |  |  |  |  | megantech
No. | SCOPE OF WORKS |  | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT
A. | GENERAL REQUIREMENTS
1 | Mobilization/Demobilization |  |  | lot | 1 | 40000 | 40000 |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 76200 | 76200 |  | lot | 1 | 25000 | 25000
2 | Safety Provisions |  |  | lot | 1 | 35000 | 35000 |  | lot | 1 | 45000 | 45000 |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 39257 | 39257 |  | lot | 1 | 119841 | 119841
3 | Tools & Equipment Rentals |  |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 35000 | 35000 |  | lot | 1 | 30500 | 30500 |  | lot | 1 | 265525 | 265525
| Sub-Total | [5 empty] | 105000 |  |  |  |  | 100000 |  |  |  |  | 75000 |  |  |  |  | 145957 |  |  |  |  | 410366
B | Enclosure
| Scaffolding Rent |  |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 35080 | 35080 |  | lot | 1 | 30000 | 30000
| Duct Tape & other consumable |  |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 1000 | 1000 |  | lot | 1 | 13884 | 13884 |  | lot | 1 | 12000 | 12000
| Tarpauline |  |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0
| Sandwich Panel |  |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0
| Sub-Total | [5 empty] | 25000 |  |  |  |  | 45000 |  |  |  |  | 6000 |  |  |  |  | 48964 |  |  |  |  | 42000
C | CAGE & Big Bag platform
Fabrication works
| 2"x2"x3mm thck Square tube,SS 304 |  |  | le | 20 | 8700 | 174000 |  | le | 20 | 8100 | 162000 |  | le | 20 | 10400 | 208000 |  | le | 20 | 9000 | 180000 |  | le | 34 | 8162 | 277508
| 5mm x 6m round bar |  |  | le | 37 | 1440 | 53280 |  | le | 40 | 450 | 18000 |  | le | 37 | 960 | 35520 |  | le | 37 | 1440 | 53280 |  | le | 48 | 385 | 18480
| Fabricated SS hinges |  |  | pcs | 16 | 1518 | 24288 |  | pcs | 20 | 2500 | 50000 |  | pcs | 8 | 2400 | 19200 |  | pcs | 16 | 1518 | 24288 |  | pcs | 16 | 2000 | 32000
| Fabricated SSBarrel Bolt |  |  | pcs | 4 | 1214 | 4856 |  | pcs | 2 | 2500 | 5000 |  | pcs | 2 | 6425 | 12850 |  | pcs | 4 | 1214 | 4856 |  | pcs | 4 | 1000 | 4000
| 150mmx150mmx10mm thck SS Plate |  |  | pcs | 16 | 9600 | 153600 |  | pcs | 16 | 1500 | 24000 |  | pcs | 1 | 2500 | 2500 |  | pcs | 16 | 9600 | 153600 |  | pcs | 0.5 | 50820 | 25410
| 4" SS 304 pipe,Sch 40,Welded |  |  | le | 1 | 25200 | 25200 |  | le | 1 | 23900 | 23900 |  | le | 1 | 28000 | 28000 |  | le | 1 | 25200 | 25200 |  | le | 1 | 25190 | 25190
| 2" SS 304 Pipe,Sch 40,Welded |  |  | le | 1 | 7200 | 7200 |  | le | 1 | 8900 | 8900 |  | le | 1 | 10625 | 10625 |  | le | 1 | 7200 | 7200 |  | le | 1 | 8250 | 8250
| 10mm dia. X4inch SS 304 bolt w/ SS 304 Cap Nut | [12 empty] | pcs | 50 | 120 | 6000
| G.I Sheet 1.5mm thck | [12 empty] | sht | 5 | 2260 | 11300
| Tension Rod | [22 empty] | lot | 1 | 5000 | 5000
| SS 304 Angle Bar 1"x1"x3mmthkx6m long | [22 empty] | le | 1 | 1496 | 1496
CIVIL WORKS
| Footing - 16 set |  |  | lot | 16 | 3000 | 48000 |  | lot | 1 | 7500 | 7500 |  | lot | 1 | 6500 | 6500 |  | lot | 16 | 3705.6 | 59289.6 |  | lot | 1 | 100000 | 100000
| Sub-Total | [5 empty] | 490424 |  |  |  |  | 299300 |  |  |  |  | 340495 |  |  |  |  | 507713.6 |  |  |  |  | 497334
D | Platform Extension and Railings
Fabrication works
| 4"x6"x10mm thck MS I Beam |  |  | le | 3 | 10500 | 31500 |  | le | 3 | 14600 | 43800 |  | le | 3 | 11400 | 34200 |  | le | 3 | 10824 | 32472 |  | le | 3 | 9625 | 28875
| 2"x4"x5mm thck MS C-Purlins |  |  | le | 1 | 3500 | 3500 |  | le | 1 | 4900 | 4900 |  | le | 1 | 6100 | 6100 |  | le | 1 | 3690 | 3690 |  | le | 1 | 5170 | 5170
| 4'x8'x3mm SS checkered Plate |  |  | sht | 5 | 30000 | 150000 |  | sht | 5 | 28800 | 144000 |  | sht | 5 | 35000 | 175000 |  | sht | 5 | 38400 | 192000 |  | sht | 6 | 33220 | 199320
| 4'x8'x5mm MS Plain Sheet |  |  | sht | 3 | 9500 | 28500 |  | sht | 3 | 7300 | 21900 |  | sht | 3 | 10000 | 30000 |  | sht | 3 | 9564 | 28692 |  | sht | 3 | 9416 | 28248
| 4'x8'x3mm MS Plain Sheet |  |  | sht | 4 | 5500 | 22000 |  | sht | 3 | 5800 | 17400 |  | sht | 3 | 6000 | 18000 |  | sht | 4 | 5742 | 22968 |  | sht | 3 | 5665 | 16995
| 2"x10mm SS Plat Bar,SS 304 |  |  | le | 1 | 5500 | 5500 |  | le | 5 | 4500 | 22500 |  | le | 5 | 9400 | 47000 |  | le | 1 | 4320 | 4320 |  | le | 6 | 9350 | 56100
| 1.5"(2") SS IDF Tube |  |  | le | 2 | 1850 | 3700 |  | le | 2 | 4200 | 8400 |  | le | 2 | 6200 | 12400 |  | le | 2 | 1656 | 3312 |  | le | 3 | 7865 | 23595
| 2"x3mm thck SS angle Bar | [12 empty] | le | 1 | 4700 | 4700
| SS 304 Angle Bar 1"x1"x3mmthkx6m long | [22 empty] | le | 1 | 1496 | 1496
| Sub-Total | [5 empty] | 244700 |  |  |  |  | 262900 |  |  |  |  | 327400 |  |  |  |  | 287454 |  |  |  |  | 359799
E | SS Stairs
Fabrication works
| 4'x8'x5mm SS checkered Plate |  |  | sht | 1 | 30000 | 30000 |  | sht | 1 | 54000 | 54000 |  | sht | 1 | 50000 | 50000 |  | sht | 1 | 48240 | 48240 |  | sht | 1 | 54450 | 54450
| 2"x5mm(10mm) thck SS 304 Flat Bar |  |  | le | 1 | 3600 | 3600 |  | le | 3 | 4500 | 13500 |  | le | 3 | 4200 | 12600 |  | le | 1 | 3600 | 3600 |  | le | 4 | 9350 | 37400
| 1.5"x5mm thck SS 304 Flat Bar |  |  | le | 1 | 2850 | 2850 |  | le | 1 | 8600 | 8600 |  | le | 2 | 3200 | 6400 |  | le | 1 | 2760 | 2760 |  | le |  |  | 0
| 1.5"(2") SS IDF Tube |  |  | le | 1 | 1850 | 1850 |  | le | 2 | 4200 | 8400 |  | le | 1 | 6200 | 6200 |  | le | 1 | 1656 | 1656 |  | le | 1 | 7865 | 7865
| SS Footing |  |  | Set | 2 | 5520 | 11040 |  | Set | 2 | 1800 | 3600 |  | lot | 1 | 8500 | 8500 |  | Set | 2 | 5520 | 11040 |  | Set | 2 | 1500 | 3000
| Steps Bendeng | [5 empty] | 0 | [11 empty] | lot | 1 | 4000 | 4000
| SS 304 10mm thk Plate 4'x8' | [5 empty] | 0 | [11 empty] | sht | 1 | 50025 | 50025
| Sub-Total | [5 empty] | 49340 |  |  |  |  | 88100 |  |  |  |  | 83700 |  |  |  |  | 121321 |  |  |  |  | 102715
F | CONSUMABLES
1 | CONSUMABLES |  |  | lot | 1 | 60000 | 60000 |  | lot | 1 | 160000 | 160000 |  | lot | 1 | 80000 | 80000 |  | lot | 1 | 67353.49 | 67353.49 |  | lot | 1 | 387935 | 387935
| Sub-Total | [5 empty] | 60000 |  |  |  |  | 160000 |  |  |  |  | 80000 |  |  |  |  | 67353.49 |  |  |  |  | 387935
G | LABOR COSTING |  | Manpower |  | No. of Days | Rate |  | Manpower | No. of Days |  | Rate |  | Manpower |  | No. of Days | Rate |  | Manpower |  | No. of Days | Rate |  | Manpower |  | No. of Days | Rate
Fabrication
| Project Engineer/Supervisor |  | 1 | days | 21 | 1200 | 25200 | 1 | days | 21 | 980 | 20580 | 1 | days | 21 | 1000 | 21000 | 1 | days | 21 | 2055.09 | 43156.89 | 1 | days | 21 | 1527.39 | 32075.09
| Safety Officer |  | 1 | days | 21 | 1100 | 23100 | 1 | days | 21 | 900 | 18900 | 1 | days | 21 | 900 | 18900 | 1 | days | 21 | 1322.66 | 27775.86 | 1 | days | 21 | 1333.26 | 27998.51
| Welders |  | 4 | days | 21 | 1100 | 92400 | 2 | days | 21 | 850 | 35700 | 3 | days | 21 | 650 | 40950 | 2 | days | 21 | 1445.14 | 60695.88 | 4 | days | 21 | 1137.3 | 95533.52
| Fitter |  | 2 | days | 21 | 1100 | 46200 | 2 | days | 21 | 850 | 35700 | 2 | days | 21 | 600 | 25200 | 2 | days | 21 | 1445.14 | 60695.88 | 3 | days | 21 | 1137.3 | 71650.14
| Skilled Helpers/scaffolders |  | 4 | days | 21 | 1000 | 84000 | 4 | days | 21 | 800 | 67200 | 4 | days | 21 | 550 | 46200 | 4 | days | 21 | 1200.12 | 100810.08 | 10 | days | 21 | 859.1 | 180411.79
| Machinist | [16 empty] | 1 | days | 21 | 1710.13 | 35912.73
| Finisher | [16 empty] | 1 | days | 21 | 1445.14 | 30347.94
| Sub-Total | [5 empty] | 270900 |  |  |  |  | 178080 |  |  |  |  | 152250 |  |  |  |  | 359395.26 |  |  |  |  | 407669.04
Installation
| Project Engineer/Supervisor |  | 1 | days | 14 | 1200 | 16800 | 1 | days | 14 | 980 | 13720 | 1 | days | 14 | 1000 | 14000 | 1 | days | 14 | 2055.09 | 28771.26 | 1 | days | 14 | 1527.39 | 21383.46
| Safety Officer |  | 1 | days | 14 | 1100 | 15400 | 1 | days | 14 | 900 | 12600 | 1 | days | 14 | 900 | 12600 | 1 | days | 14 | 1322.66 | 18517.24 | 1 | days | 14 | 1333.26 | 18665.64
| Welders |  | 4 | days | 14 | 1100 | 61600 | 2 | days | 14 | 850 | 23800 | 3 | days | 14 | 650 | 27300 | 3 | days | 14 | 1445.14 | 60695.88 | 6 | days | 14 | 1137.3 | 95533.2
| Fitter |  | 2 | days | 14 | 1100 | 30800 | 2 | days | 14 | 850 | 23800 | 2 | days | 14 | 600 | 16800 | 2 | days | 14 | 1445.14 | 40463.92 | 4 | days | 14 | 1137.3 | 63688.8
| Skilled Helpers/scaffolders |  | 4 | days | 14 | 1000 | 56000 | 4 | days | 14 | 800 | 44800 | 4 | days | 14 | 550 | 30800 | 4 | days | 14 | 1200.12 | 67206.72 | 12 | days | 14 | 859.1 | 144328.8
| Scaffolder | [21 empty] | 2 | days | 7 | 1137.3 | 15922.2
| Mason | [21 empty] | 2 | days | 7 | 1137.3 | 15922.2
| Fire Watcher | [21 empty] | 1 | days | 14 | 859.1 | 12027.4
| Sub-Total | [5 empty] | 180600 |  |  |  |  | 118720 |  |  |  |  | 101500 |  |  |  |  | 215655.02 |  |  |  |  | 387472.98
| Sub-Total | [10 empty] | 296800
H | CARI.03% | [5 empty] | 12500 |  |  |  |  | 4472.78 |  |  |  |  | 4272.25 |  |  |  |  | 12747.14 |  |  |  |  | 10014
I | Administrative cost(10%) | [5 empty] | 46045.758 |  |  |  |  | 95530 |  |  |  |  | 119334.5 |  |  |  |  | 91051 |  |  |  |  | 100184.8
Summary:
| General Requirements | [5 empty] | 105000 |  |  |  |  | 100000 |  |  |  |  | 75000 |  |  |  |  | 145957 |  |  |  |  | 410366
| Materials & Consumables | [5 empty] | 869464 |  |  |  |  | 855300 |  |  |  |  | 837595 |  |  |  |  | 983842.09 |  |  |  |  | 1001848
| Labor cost | [5 empty] | 451500 |  |  |  |  | 296800 |  |  |  |  | 253750 |  |  |  |  | 642257 |  |  |  |  | 795142.02
| Mark-up / profit | [5 empty] | 213894.6 |  |  |  |  | 143295 |  |  |  |  | 238669 |  |  |  |  | 281378.14 |  |  |  |  | 347633.22
| GRAND TOTAL COST (VAT Exclusive) | [5 empty] | 1698404.358 |  |  |  |  | 1495397.78 |  |  |  |  | 1528620.75 |  |  |  |  | 2053434.23 |  |  |  |  | 2665188.04
| GRAND TOTAL COST (VAT Inclusive) | [5 empty] | 1902212.881 |  |  |  |  | 1674845.5136 |  |  |  |  | 1712055.24 |  |  |  |  | 2299846.3376 |  |  |  |  | 2985010.6048
| COMPLETION |  | 35 working days |  |  |  |  | 35 working days |  |  |  |  | 35 working days |  |  |  |  | 35 working days
| GRAND TOTAL |  |  |  |  | Php | 1698404.358 |  |  |  | Php | 1495397.78 |  |  |  | Php | 1528620.75 |  |  |  | Php | 2053434.23 |  |  |  | Php | 2665188.04
Visa | Submitted by: |  |  | Noted by:
Date
The Grand total indicated above constitute the Fixed Lump Sum Price of our bid which includes the cost of materials, labor, equipments, overhead profits and all other construction related costs to satisfactorily complete the work in accordance with the drawings, Scope of Work, Specifications and other related bid documents.
It is understood that the quantities and unit prices indicated above are complete and any item not shown but otherwise required to satisfactorily complete the work are considered built-in and included in our Fixed Lump Sum Price. It is also understood that this Bid Breakdown is part of our proposal and the Owner can use this as one of the basis for evaluation.
Construction Duration :
Submitted by:
(Company Name)

## Adjusted Qty
PROJECT TITLE: |  | Supply of labor and consumables for the Installation of Mechanical Works for Dryblending Project Phase 2 |  |  | Date: | 2021-07-20 10:11
COST CENTER: |  |  |  |  | Reference:
|  |  | In House |  |  |  |  | O and J |  |  |  |  | Fedcon |  |  |  |  | Acepack |  |  |  |  | megantech
No. | SCOPE OF WORKS |  | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT
A. | GENERAL REQUIREMENTS
1 | Mobilization/Demobilization |  |  | lot | 1 | 40000 | 40000 |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 76200 | 76200 |  | lot | 1 | 25000 | 25000
2 | Safety Provisions |  |  | lot | 1 | 35000 | 35000 |  | lot | 1 | 45000 | 45000 |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 39257 | 39257 |  | lot | 1 | 119841 | 119841
3 | Tools & Equipment Rentals |  |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 35000 | 35000 |  | lot | 1 | 30500 | 30500 |  | lot | 1 | 265525 | 265525
| Sub-Total | [5 empty] | 105000 |  |  |  |  | 100000 |  |  |  |  | 75000 |  |  |  |  | 145957 |  |  |  |  | 410366
B | Enclosure
| Scaffolding Rent |  |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 35080 | 35080 |  | lot | 1 | 30000 | 30000
| Duct Tape & other consumable |  |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 1000 | 1000 |  | lot | 1 | 13884 | 13884 |  | lot | 1 | 12000 | 12000
| Tarpauline |  |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0
| Sandwich Panel |  |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0
| Sub-Total | [5 empty] | 25000 |  |  |  |  | 45000 |  |  |  |  | 6000 |  |  |  |  | 48964 |  |  |  |  | 42000
C | CAGE & Big Bag platform
Fabrication works
| 2"x2"x3mm thck Square tube,SS 304 |  |  | le | 20 | 8700 | 174000 |  | le | 20 | 8100 | 162000 |  | le | 21 | 10400 | 218400 |  | le | 20 | 9000 | 180000 |  | le | 34 | 8162 | 277508
| 5mm x 6m round bar |  |  | le | 37 | 1440 | 53280 |  | le | 40 | 450 | 18000 |  | le | 37 | 960 | 35520 |  | le | 37 | 1440 | 53280 |  | le | 48 | 385 | 18480
| Fabricated SS hinges |  |  | pcs | 16 | 1518 | 24288 |  | pcs | 20 | 2500 | 50000 |  | pcs | 16 | 2400 | 38400 |  | pcs | 16 | 1518 | 24288 |  | pcs | 16 | 2000 | 32000
| Fabricated SSBarrel Bolt |  |  | pcs | 4 | 1214 | 4856 |  | pcs | 2 | 2500 | 5000 |  | pcs | 4 | 6425 | 25700 |  | pcs | 4 | 1214 | 4856 |  | pcs | 4 | 1000 | 4000
| 150mmx150mmx10mm thck SS Plate |  |  | pcs | 16 | 9600 | 153600 |  | pcs | 16 | 1500 | 24000 |  | pcs | 1 | 2500 | 2500 |  | pcs | 16 | 9600 | 153600 |  | pcs | 0.5 | 50820 | 25410
| 4" SS 304 pipe,Sch 40,Welded |  |  | le | 1 | 25200 | 25200 |  | le | 1 | 23900 | 23900 |  | le | 1 | 28000 | 28000 |  | le | 1 | 25200 | 25200 |  | le | 1 | 25190 | 25190
| 2" SS 304 Pipe,Sch 40,Welded |  |  | le | 1 | 7200 | 7200 |  | le | 1 | 8900 | 8900 |  | le | 2 | 10625 | 21250 |  | le | 1 | 7200 | 7200 |  | le | 1 | 8250 | 8250
| 10mm dia. X4inch SS 304 bolt w/ SS 304 Cap Nut | [12 empty] | pcs | 50 | 120 | 6000
| G.I Sheet 1.5mm thck | [12 empty] | sht | 5 | 2260 | 11300
| Tension Rod | [22 empty] | lot | 1 | 5000 | 5000
| SS 304 Angle Bar 1"x1"x3mmthkx6m long | [22 empty] | le | 1 | 1496 | 1496
CIVIL WORKS
| Footing - 16 set |  |  | lot | 16 | 3000 | 48000 |  | lot | 1 | 7500 | 7500 |  | pcs | 20 | 6500 | 130000 |  | lot | 16 | 3705.6 | 59289.6 |  | lot | 1 | 100000 | 100000
| Sub-Total | [5 empty] | 490424 |  |  |  |  | 299300 |  |  |  |  | 517070 |  |  |  |  | 507713.6 |  |  |  |  | 497334
C | Platform Extension and Railings
Fabrication works
| 4"x6"x10mm thck MS I Beam |  |  | le | 3 | 10500 | 31500 |  | le | 3 | 14600 | 43800 |  | le | 3 | 11400 | 34200 |  | le | 3 | 10824 | 32472 |  | le | 3 | 9625 | 28875
| 2"x4"x5mm thck MS C-Purlins |  |  | le | 1 | 3500 | 3500 |  | le | 1 | 4900 | 4900 |  | le | 1 | 6100 | 6100 |  | le | 1 | 3690 | 3690 |  | le | 1 | 5170 | 5170
| 4'x8'x3mm SS checkered Plate |  |  | sht | 5 | 30000 | 150000 |  | sht | 5 | 28800 | 144000 |  | sht | 5 | 35000 | 175000 |  | sht | 5 | 38400 | 192000 |  | sht | 6 | 33220 | 199320
| 4'x8'x5mm MS Plain Sheet |  |  | sht | 3 | 9500 | 28500 |  | sht | 3 | 7300 | 21900 |  | sht | 2 | 10000 | 20000 |  | sht | 3 | 9564 | 28692 |  | sht | 3 | 9416 | 28248
| 4'x8'x3mm MS Plain Sheet |  |  | sht | 4 | 5500 | 22000 |  | sht | 3 | 5800 | 17400 |  | sht | 2 | 6000 | 12000 |  | sht | 4 | 5742 | 22968 |  | sht | 3 | 5665 | 16995
| 2"x10mm SS Plat Bar,SS 304 |  |  | le | 1 | 5500 | 5500 |  | le | 5 | 4500 | 22500 |  | le | 5 | 9400 | 47000 |  | le | 1 | 4320 | 4320 |  | le | 6 | 9350 | 56100
| 1.5"(2") SS IDF Tube |  |  | le | 2 | 1850 | 3700 |  | le | 2 | 4200 | 8400 |  | le | 4 | 6200 | 24800 |  | le | 2 | 1656 | 3312 |  | le | 3 | 7865 | 23595
| 2"x3mm thck SS angle Bar | [12 empty] | le | 1 | 4700 | 4700
| Hinges | [12 empty] | pcs | 2
| Barrel bolt | [12 empty] | pcs | 2
| SS 304 Angle Bar 1"x1"x3mmthkx6m long | [22 empty] | le | 1 | 1496 | 1496
| Sub-Total | [5 empty] | 244700 |  |  |  |  | 262900 |  |  |  |  | 323800 |  |  |  |  | 287454 |  |  |  |  | 359799
D | SS Stairs
Fabrication works
| 4'x8'x5mm SS checkered Plate |  |  | sht | 1 | 30000 | 30000 |  | sht | 1 | 54000 | 54000 |  | sht | 1 | 50000 | 50000 |  | sht | 1 | 48240 | 48240 |  | sht | 1 | 54450 | 54450
| 2"x10mmthck SS 304 Flat Bar |  |  | le | 1 | 3600 | 3600 |  | le | 3 | 4500 | 13500 |  | le | 3 | 4200 | 12600 |  | le | 1 | 3600 | 3600 |  | le | 4 | 9350 | 37400
| 1.5"x5mm thck SS 304 Flat Bar |  |  | le | 1 | 2850 | 2850 |  | le | 1 | 8600 | 8600 |  | le | 2 | 3200 | 6400 |  | le | 1 | 2760 | 2760 |  | le |  |  | 0
| 2" SS IDF Tube |  |  | le | 1 | 1850 | 1850 |  | le | 2 | 4200 | 8400 |  | le | 1 | 6200 | 6200 |  | le | 1 | 1656 | 1656 |  | le | 1 | 7865 | 7865
| SS Footing - 2 pcs |  |  | Set | 2 | 5520 | 11040 |  | Set | 2 | 1800 | 3600 |  | lot | 1 | 8500 | 8500 |  | Set | 2 | 5520 | 11040 |  | Set | 2 | 1500 | 3000
| Steps Bendeng | [5 empty] | 0 | [11 empty] | lot | 1 | 4000 | 4000
| SS 304 10mm thk Plate 4'x8' | [5 empty] | 0 | [11 empty] | sht | 1 | 50025 | 50025
| 4'x8'x10mm SS checkered Plate | [5 empty] | 49340 |  |  |  |  | 88100 |  |  |  |  | 83700 |  |  |  |  | 121321 |  |  |  |  | 102715
C | CONSUMABLES
1 | CONSUMABLES |  |  | lot | 1 | 60000 | 60000 |  | lot | 1 | 160000 | 160000 |  | lot | 1 | 80000 | 80000 |  | lot | 1 | 67353.49 | 67353.49 |  | lot | 1 | 387935 | 387935
| Sub-Total | [5 empty] | 60000 |  |  |  |  | 160000 |  |  |  |  | 80000 |  |  |  |  | 67353.49 |  |  |  |  | 387935
D | LABOR COSTING |  | Manpower |  | No. of Days | Rate |  | Manpower | No. of Days |  | Rate |  | Manpower |  | No. of Days | Rate |  | Manpower |  | No. of Days | Rate |  | Manpower |  | No. of Days | Rate
Fabrication
| Project Engineer/Supervisor |  | 1 | days | 21 | 1200 | 25200 | 1 | days | 21 | 980 | 20580 | 1 | days | 21 | 1000 | 21000 | 1 | days | 21 | 2055.09 | 43156.89 | 1 | days | 21 | 1527.39 | 32075.09
| Safety Officer |  | 1 | days | 21 | 1100 | 23100 | 1 | days | 21 | 900 | 18900 | 1 | days | 21 | 900 | 18900 | 1 | days | 21 | 1322.66 | 27775.86 | 1 | days | 21 | 1333.26 | 27998.51
| Welders |  | 4 | days | 21 | 1100 | 92400 | 2 | days | 21 | 850 | 35700 | 3 | days | 21 | 650 | 40950 | 2 | days | 21 | 1445.14 | 60695.88 | 4 | days | 21 | 1137.3 | 95533.52
| Fitter |  | 2 | days | 21 | 1100 | 46200 | 2 | days | 21 | 850 | 35700 | 2 | days | 21 | 600 | 25200 | 2 | days | 21 | 1445.14 | 60695.88 | 3 | days | 21 | 1137.3 | 71650.14
| Skilled Helpers/scaffolders |  | 4 | days | 21 | 1000 | 84000 | 4 | days | 21 | 800 | 67200 | 4 | days | 21 | 550 | 46200 | 4 | days | 21 | 1200.12 | 100810.08 | 10 | days | 21 | 859.1 | 180411.79
| Machinist | [16 empty] | 1 | days | 21 | 1710.13 | 35912.73
| Finisher | [16 empty] | 1 | days | 21 | 1445.14 | 30347.94
| Sub-Total | [5 empty] | 270900 |  |  |  |  | 178080 |  |  |  |  | 152250 |  |  |  |  | 359395.26 |  |  |  |  | 407669.04
Installation
| Project Engineer/Supervisor |  | 1 | days | 14 | 1200 | 16800 | 1 | days | 14 | 980 | 13720 | 1 | days | 14 | 1000 | 14000 | 1 | days | 14 | 2055.09 | 28771.26 | 1 | days | 14 | 1527.39 | 21383.46
| Safety Officer |  | 1 | days | 14 | 1100 | 15400 | 1 | days | 14 | 900 | 12600 | 1 | days | 14 | 900 | 12600 | 1 | days | 14 | 1322.66 | 18517.24 | 1 | days | 14 | 1333.26 | 18665.64
| Welders |  | 4 | days | 14 | 1100 | 61600 | 2 | days | 14 | 850 | 23800 | 3 | days | 14 | 650 | 27300 | 3 | days | 14 | 1445.14 | 60695.88 | 6 | days | 14 | 1137.3 | 95533.2
| Fitter |  | 2 | days | 14 | 1100 | 30800 | 2 | days | 14 | 850 | 23800 | 2 | days | 14 | 600 | 16800 | 2 | days | 14 | 1445.14 | 40463.92 | 4 | days | 14 | 1137.3 | 63688.8
| Skilled Helpers/scaffolders |  | 4 | days | 14 | 1000 | 56000 | 4 | days | 14 | 800 | 44800 | 4 | days | 14 | 550 | 30800 | 4 | days | 14 | 1200.12 | 67206.72 | 12 | days | 14 | 859.1 | 144328.8
| Scaffolder | [21 empty] | 2 | days | 7 | 1137.3 | 15922.2
| Mason | [21 empty] | 2 | days | 7 | 1137.3 | 15922.2
| Fire Watcher | [21 empty] | 1 | days | 14 | 859.1 | 12027.4
| Sub-Total | [5 empty] | 180600 |  |  |  |  | 118720 |  |  |  |  | 101500 |  |  |  |  | 215655.02 |  |  |  |  | 387472.98
| Sub-Total | [10 empty] | 296800
E | CARI.03% | [5 empty] | 12500 |  |  |  |  | 4472.78 |  |  |  |  | 4272.25 |  |  |  |  | 12747.14 |  |  |  |  | 10014
F | Administrative cost(10%) | [5 empty] | 46045.758 |  |  |  |  | 95530 |  |  |  |  | 119334.5 |  |  |  |  | 91051 |  |  |  |  | 100184.8
Summary:
| General Requirements | [5 empty] | 105000 |  |  |  |  | 100000 |  |  |  |  | 75000 |  |  |  |  | 145957 |  |  |  |  | 410366
| Materials & Consumables | [5 empty] | 869464 |  |  |  |  | 855300 |  |  |  |  | 1010570 |  |  |  |  | 983842.09 |  |  |  |  | 1001848
| Labor cost | [5 empty] | 451500 |  |  |  |  | 296800 |  |  |  |  | 253750 |  |  |  |  | 642257 |  |  |  |  | 795142.02
| Mark-up / profit | [5 empty] | 213894.6 |  |  |  |  | 143295 |  |  |  |  | 238669 |  |  |  |  | 281378.14 |  |  |  |  | 347633.22
| GRAND TOTAL COST (VAT Exclusive) | [5 empty] | 1639858.6 |  |  |  |  | 1495397.78 |  |  |  |  | 1701595.75 |  |  |  |  | 2053434.23 |  |  |  |  | 2665188.04
| GRAND TOTAL COST (VAT Inclusive) | [5 empty] | 1836641.632 |  |  |  |  | 1674845.5136 |  |  |  |  | 1905787.24 |  |  |  |  | 2299846.3376 |  |  |  |  | 2985010.6048
COMPLETION
| GRAND TOTAL |  |  |  |  | Php | 1639858.6 |  |  |  | Php | 1495397.78 |  |  |  | Php | 1701595.75 |  |  |  | Php | 2053434.23 |  |  |  | Php | 2665188.04
Visa | Submitted by: |  |  | Noted by:
Date
The Grand total indicated above constitute the Fixed Lump Sum Price of our bid which includes the cost of materials, labor, equipments, overhead profits and all other construction related costs to satisfactorily complete the work in accordance with the drawings, Scope of Work, Specifications and other related bid documents.
It is understood that the quantities and unit prices indicated above are complete and any item not shown but otherwise required to satisfactorily complete the work are considered built-in and included in our Fixed Lump Sum Price. It is also understood that this Bid Breakdown is part of our proposal and the Owner can use this as one of the basis for evaluation.
Construction Duration :
Submitted by:
(Company Name)

## Final Quotation
In house adjusted quantity + Contractor adjusted quantity and reconciled quotation
PROJECT TITLE: |  | Supply of labor and consumables for the Installation of Mechanical Works for Dryblending Project Phase 2 |  |  | Date: | 2021-07-20 10:11
COST CENTER: |  |  |  |  | Reference:
|  |  | In House |  |  |  |  | O and J |  |  |  |  | Fedcon |  |  |  |  | Acepack |  |  |  |  | megantech
No. | SCOPE OF WORKS |  | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT
A. | GENERAL REQUIREMENTS
1 | Mobilization/Demobilization |  |  | lot | 1 | 40000 | 40000 |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 76200 | 76200 |  | lot | 1 | 25000 | 25000
2 | Safety Provisions |  |  | lot | 1 | 35000 | 35000 |  | lot | 1 | 45000 | 45000 |  | lot | 1 | 15000 | 62000 |  | lot | 1 | 39257 | 39257 |  | lot | 1 | 119841 | 119841
3 | Tools & Equipment Rentals |  |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 35000 | 35000 |  | lot | 1 | 35000 | 40000 |  | lot | 1 | 30500 | 30500 |  | lot | 1 | 265525 | 265525
| Sub-Total | [5 empty] | 105000 |  |  |  |  | 110000 |  |  |  |  | 127000 |  |  |  |  | 145957 |  |  |  |  | 410366
B | Enclosure
| Scaffolding Rent |  |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 35080 | 35080 |  | lot | 1 | 30000 | 30000
| Duct Tape & other consumable |  |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 1000 | 1000 |  | lot | 1 | 13884 | 13884 |  | lot | 1 | 12000 | 12000
| Tarpauline |  |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0
| Sandwich Panel |  |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0 |  | NPI will Provide |  |  | 0
| Sub-Total | [5 empty] | 25000 |  |  |  |  | 45000 |  |  |  |  | 6000 |  |  |  |  | 48964 |  |  |  |  | 42000
C | CAGE & Big Bag platform
Fabrication works
| 2"x2"x3mm thck Square tube,SS 304 |  |  | le | 21 | 8700 | 182700 |  | le | 21 | 8100 | 170100 |  | le | 21 | 10400 | 218400 |  | le | 20 | 9000 | 180000 |  | le | 34 | 8162 | 277508
| 5mm x 6m round bar |  |  | le | 37 | 1440 | 53280 |  | le | 40 | 450 | 18000 |  | le | 37 | 960 | 35520 |  | le | 37 | 1440 | 53280 |  | le | 48 | 385 | 18480
| Fabricated SS hinges |  |  | pcs | 16 | 1518 | 24288 |  | pcs | 24 | 2500 | 60000 |  | pcs | 16 | 2400 | 38400 |  | pcs | 16 | 1518 | 24288 |  | pcs | 16 | 2000 | 32000
| Fabricated SSBarrel Bolt |  |  | pcs | 4 | 1214 | 4856 |  | pcs | 6 | 2500 | 15000 |  | pcs | 4 | 6425 | 25700 |  | pcs | 4 | 1214 | 4856 |  | pcs | 4 | 1000 | 4000
| 150mmx150mmx10mm thck SS Plate |  |  | lot | 1 | 10600 | 10600 |  | pcs | 20 | 3500 | 70000 |  | lot | 1 | 22000 | 22000 |  | pcs | 16 | 9600 | 153600 |  | pcs | 0.5 | 50820 | 25410
| 4" SS 304 pipe,Sch 40,Welded |  |  | le | 1 | 25200 | 25200 |  | le | 1 | 23900 | 23900 |  | le | 1 | 28000 | 28000 |  | le | 1 | 25200 | 25200 |  | le | 1 | 25190 | 25190
| 2" SS 304 Pipe,Sch 40,Welded |  |  | le | 1 | 7200 | 7200 |  | le | 1 | 8900 | 8900 |  | le | 2 | 9000 | 18000 |  | le | 1 | 7200 | 7200 |  | le | 1 | 8250 | 8250
| 10mm dia. X4inch SS 304 bolt w/ SS 304 Cap Nut | [12 empty] | pcs | 50 | 120 | 6000
| G.I Sheet 1.5mm thck | [12 empty] | sht | 5 | 2260 | 11300
| Tension Rod | [15 empty] | 0 | [6 empty] | lot | 1 | 5000 | 5000
| SS 304 Angle Bar 1"x1"x3mmthkx6m long | [15 empty] | 0 | [6 empty] | le | 1 | 1496 | 1496
| 10mmdia x4inch SS 304 cup nut | [12 empty] | pcs | 50 | 120 | 6000
| G.I Sheet 1.5mm thck | [12 empty] | sht | 5 | 280 | 1400
CIVIL WORKS
| Footing - 20 set |  |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 28000 | 28000 |  | lot | 16 | 3705.6 | 59289.6 |  | lot | 1 | 100000 | 100000
| Sub-Total | [5 empty] | 333124 |  |  |  |  | 380900 |  |  |  |  | 421420 |  |  |  |  | 507713.6 |  |  |  |  | 497334
D | Platform Extension and Railings
Fabrication works
| 4"x6"x10mm thck MS I Beam |  |  | le | 3 | 10500 | 31500 |  | le | 3 | 14600 | 43800 |  | le | 3 | 11400 | 34200 |  | le | 3 | 10824 | 32472 |  | le | 3 | 9625 | 28875
| 2"x4"x5mm thck MS C-Purlins |  |  | le | 1 | 3500 | 3500 |  | le | 1 | 4900 | 4900 |  | le | 1 | 6100 | 6100 |  | le | 1 | 3690 | 3690 |  | le | 1 | 5170 | 5170
| 4'x8'x6mm SS checkered Plate |  |  | sht | 5 | 55000 | 275000 |  | sht | 6 | 58000 | 348000 |  | sht | 5 | 58000 | 290000 |  | sht | 5 | 38400 | 192000 |  | sht | 6 | 33220 | 199320
| 4'x8'x5mm MS Plain Sheet |  |  | sht | 2 | 9500 | 19000 |  | sht | 3 | 7300 | 21900 |  | sht | 2 | 10000 | 20000 |  | sht | 3 | 9564 | 28692 |  | sht | 3 | 9416 | 28248
| 4'x8'x3mm MS Plain Sheet |  |  | sht | 2 | 5500 | 11000 |  | sht | 3 | 5800 | 17400 |  | sht | 2 | 6000 | 12000 |  | sht | 4 | 5742 | 22968 |  | sht | 3 | 5665 | 16995
| 2"x10mm SS Plat Bar,SS 304 |  |  | le | 5 | 5500 | 27500 |  | le | 5 | 4500 | 22500 |  | le | 5 | 9400 | 47000 |  | le | 1 | 4320 | 4320 |  | le | 6 | 9350 | 56100
| 2" SS IDF Tube |  |  | le | 4 | 4500 | 18000 |  | le | 5 | 4200 | 21000 |  | le | 4 | 7000 | 28000 |  | le | 2 | 1656 | 3312 |  | le | 3 | 7865 | 23595
| 2"x3mm thck SS angle Bar | [12 empty] | le | 1 | 4700 | 4700
| Hinges | [12 empty] | pcs | 2 | 2400 | 4800
| Barrel bolt | [12 empty] | pcs | 2 | 6425 | 12850
| SS 304 Angle Bar 1"x1"x3mmthkx6m long | [22 empty] | le | 1 | 1496 | 1496
| Sub-Total | [5 empty] | 385500 |  |  |  |  | 479500 |  |  |  |  | 459650 |  |  |  |  | 287454 |  |  |  |  | 359799
E | SS Stairs
Fabrication works
| 4'x8'x6mm SS checkered Plate |  |  | sht | 1 | 55000 | 55000 |  | sht | 1 | 58000 | 58000 |  | sht | 1 | 58000 | 58000 |  | sht | 1 | 48240 | 48240 |  | sht | 1 | 54450 | 54450
| 2"x10mmthck SS 304 Flat Bar |  |  | le | 3 | 5400 | 16200 |  | le | 3 | 4500 | 13500 |  | le | 3 | 9400 | 28200 |  | le | 1 | 3600 | 3600 |  | le | 4 | 9350 | 37400
| 1.5"x5mm thck SS 304 Flat Bar | [17 empty] | le | 1 | 2760 | 2760 |  | le |  |  | 0
| 2" SS IDF Tube |  |  | le | 1 | 4500 | 4500 |  | le | 2 | 4200 | 8400 |  | le | 1 | 7000 | 7000 |  | le | 1 | 1656 | 1656 |  | le | 1 | 7865 | 7865
| SS Footing - 2 pcs |  |  | Set | 2 | 5520 | 11040 |  | set | 2 | 2500 | 5000 |  | pcs | 2 | 5500 | 11000 |  | Set | 2 | 5520 | 11040 |  | Set | 2 | 1500 | 3000
| SS Flat bar 10mm x200mmx2440 | [7 empty] | le | 2 | 18000 | 36000
| Steps Bendeng | [5 empty] | 0 | [11 empty] | lot | 1 | 4000 | 4000
| SS 304 10mm thk Plate 4'x8' | [5 empty] | 0 | [11 empty] | sht | 1 | 50025 | 50025
| 4'x8'x10mm SS checkered Plate |  |  | lot | 1 | 35000 | 35000 | [6 empty] | lot | 1 | 34000 | 34000 |  |  |  |  | 121321 |  |  |  |  | 102715
| Sub-Total | [5 empty] | 121740 |  |  |  |  | 120900 |  | Sub-Total |  |  | 138200 |  |  |  | 0 |  |  |  |  | 0
F | CONSUMABLES
1 | CONSUMABLES |  |  | lot | 1 | 120000 | 120000 |  | lot | 1 | 185000 | 185000 |  | lot | 1 | 84000 | 84000 |  | lot | 1 | 67353.49 | 67353.49 |  | lot | 1 | 387935 | 387935
| Sub-Total | [5 empty] | 120000 |  |  |  |  | 185000 |  |  |  |  | 84000 |  |  |  |  | 67353.49 |  |  |  |  | 387935
G | LABOR COSTING |  | Manpower |  | No. of Days | Rate |  | Manpower | No. of Days |  | Rate |  | Manpower |  | No. of Days | Rate |  | Manpower |  | No. of Days | Rate |  | Manpower |  | No. of Days | Rate
Fabrication
| Project Engineer/Supervisor |  | 1 | days | 21 | 1200 | 25200 | 1 | days | 21 | 980 | 20580 | 1 | days | 21 | 1000 | 21000 | 1 | days | 21 | 2055.09 | 43156.89 | 1 | days | 21 | 1527.39 | 32075.09
| Safety Officer |  | 1 | days | 21 | 1100 | 23100 | 1 | days | 21 | 900 | 18900 | 1 | days | 21 | 900 | 18900 | 1 | days | 21 | 1322.66 | 27775.86 | 1 | days | 21 | 1333.26 | 27998.51
| Welders |  | 3 | days | 21 | 1100 | 69300 | 2 | days | 21 | 850 | 35700 | 3 | days | 21 | 650 | 40950 | 2 | days | 21 | 1445.14 | 60695.88 | 4 | days | 21 | 1137.3 | 95533.52
| Fitter |  | 2 | days | 21 | 1100 | 46200 | 2 | days | 21 | 850 | 35700 | 2 | days | 21 | 600 | 25200 | 2 | days | 21 | 1445.14 | 60695.88 | 3 | days | 21 | 1137.3 | 71650.14
| Skilled Helpers/scaffolders |  | 4 | days | 21 | 1000 | 84000 | 6 | days | 21 | 800 | 100800 | 4 | days | 21 | 550 | 46200 | 4 | days | 21 | 1200.12 | 100810.08 | 10 | days | 21 | 859.1 | 180411.79
| Machinist | [16 empty] | 1 | days | 21 | 1710.13 | 35912.73
| Finisher | [16 empty] | 1 | days | 21 | 1445.14 | 30347.94
| Sub-Total | [5 empty] | 247800 |  |  |  |  | 211680 |  |  |  |  | 152250 |  |  |  |  | 359395.26 |  |  |  |  | 407669.04
Installation
| Project Engineer/Supervisor |  | 1 | days | 14 | 1200 | 16800 | 1 | days | 14 | 980 | 13720 | 1 | days | 14 | 1000 | 14000 | 1 | days | 14 | 2055.09 | 28771.26 | 1 | days | 14 | 1527.39 | 21383.46
| Safety Officer |  | 1 | days | 14 | 1100 | 15400 | 1 | days | 14 | 900 | 12600 | 1 | days | 14 | 900 | 12600 | 1 | days | 14 | 1322.66 | 18517.24 | 1 | days | 14 | 1333.26 | 18665.64
| Welders |  | 3 | days | 14 | 1100 | 46200 | 2 | days | 14 | 850 | 23800 | 3 | days | 14 | 650 | 27300 | 3 | days | 14 | 1445.14 | 60695.88 | 6 | days | 14 | 1137.3 | 95533.2
| Fitter |  | 2 | days | 14 | 1100 | 30800 | 2 | days | 14 | 850 | 23800 | 2 | days | 14 | 600 | 16800 | 2 | days | 14 | 1445.14 | 40463.92 | 4 | days | 14 | 1137.3 | 63688.8
| Skilled Helpers/scaffolders |  | 4 | days | 14 | 1000 | 56000 | 6 | days | 14 | 800 | 67200 | 4 | days | 14 | 550 | 30800 | 4 | days | 14 | 1200.12 | 67206.72 | 12 | days | 14 | 859.1 | 144328.8
| Scaffolder | [21 empty] | 2 | days | 7 | 1137.3 | 15922.2
| Mason | [21 empty] | 2 | days | 7 | 1137.3 | 15922.2
| Fire Watcher | [21 empty] | 1 | days | 14 | 859.1 | 12027.4
| Sub-Total | [5 empty] | 165200 |  |  |  |  | 141120 |  |  |  |  | 101500 |  |  |  |  | 215655.02 |  |  |  |  | 387472.98
| Sub-Total | [10 empty] | 352800
H | CARI.03% | [5 empty] | 14600 |  |  |  |  | 6013.28 |  |  |  |  | 6000 |  |  |  |  | 12747.14 |  |  |  |  | 10014
I | Administrative cost(10%) | [5 empty] | 120000 |  |  |  |  | 132130 |  |  |  |  | 150202 |  |  |  |  | 91051 |  |  |  |  | 100184.8
Summary:
| General Requirements | [5 empty] | 105000 |  |  |  |  | 110000 |  |  |  |  | 127000 |  |  |  |  | 145957 |  |  |  |  | 410366
| Materials & Consumables | [5 empty] | 898624 |  |  |  |  | 1211300 |  |  |  |  | 1115270 |  |  |  |  | 983842.09 |  |  |  |  | 1001848
| Labor cost | [5 empty] | 413000 |  |  |  |  | 352800 |  |  |  |  | 253750 |  |  |  |  | 642257 |  |  |  |  | 795142.02
| Mark-up / profit | [5 empty] | 212493.6 |  |  |  |  | 198195 |  |  |  |  | 270363.6 |  |  |  |  | 281378.14 |  |  |  |  | 347633.22
| GRAND TOTAL COST (VAT Exclusive) | [5 empty] | 1763717.6 |  |  |  |  | 2010438.28 |  |  |  |  | 1922585.6 |  |  |  |  | 2053434.23 |  |  |  |  | 2665188.04
| GRAND TOTAL COST (VAT Inclusive) | [5 empty] | 1975363.712 |  |  |  |  | 2251690.8736 |  |  |  |  | 2153295.872 |  |  |  |  | 2299846.3376 |  |  |  |  | 2985010.6048
| COMPLETION |  | 35 working days |  |  |  |  | 35 working days |  |  |  |  | 35 working days
| GRAND TOTAL |  |  |  |  | Php | 1763717.6 |  |  |  | Php | 2010438.28 |  |  |  | Php | 1922585.6 |  |  |  | Php | 2053434.23 |  |  |  | Php | 2665188.04
Visa | Submitted by: |  |  | Noted by:
Date
The Grand total indicated above constitute the Fixed Lump Sum Price of our bid which includes the cost of materials, labor, equipments, overhead profits and all other construction related costs to satisfactorily complete the work in accordance with the drawings, Scope of Work, Specifications and other related bid documents.
It is understood that the quantities and unit prices indicated above are complete and any item not shown but otherwise required to satisfactorily complete the work are considered built-in and included in our Fixed Lump Sum Price. It is also understood that this Bid Breakdown is part of our proposal and the Owner can use this as one of the basis for evaluation.
Construction Duration :
Submitted by:
(Company Name)

## SUMMARY
Subject: Supply of labor and consumables for the Installation of Mechanical Works for Dryblending Project Phase 2
Dated: July 19, 2021
ORIGINAL QUOTATION
|  | SCOPE OF WORKS | IN HOUSE | FEDCON | O AND J | ACEPACK | MEGANTECH
| A | GENERAL REQUIREMENTS | 105000 | 75000 | 100000 | 145957 | 420380
| B | MATERIALS COST AND CONSUMABLES | 869464 | 837595 | 855300 | 983842.09 | 1001848
| C | LABOR COST | 451500 | 253750 | 296800 | 642257 | 795142.01
| D | CARI | 12500 | 4272.25 | 4472.78
| E | ADMINISTRATIVE COST | 46045.76 | 119334.5 | 95530 |  | 100184.8
| F | OVERHEAD/CONTINGENCY
| G | MARK UP PROFIT | 213894.6 | 238669 | 143295 | 281378.14 | 347633.22
|  | GRAND TOTAL | 1698404.36 | 1528620.75 | 1495397.78 | 2053434.23 | 2665188.03
|  |  | 100% | 90% | 88.05% | 120.9% | 156.9%
RECONCILED QUOTATION
|  | SCOPE OF WORKS | IN HOUSE | FEDCON | O AND J
| A | GENERAL REQUIREMENTS | 105000 | 127000 | 110000
| B | MATERIALS COST AND CONSUMABLES | 898624 | 1115270 | 1211300
| C | LABOR COST | 413000 | 253750 | 352800
| D | CARI | 14600 | 6000 | 6013.28
| E | ADMINISTRATIVE COST | 120000 | 150202 | 132130
| F | OVERHEAD/CONTINGENCY
| G | MARK UP PROFIT | 212493.6 | 270363.6 | 198195
|  | GRAND TOTAL | 1763717.6 | 1922585.6 | 2010438.28 | 0 | 0
|  |  | 100% | 109% | 114%