## RAW
notes | <tags.name> | name | <created_at> | <memberships.section.name> | Get this from stories (another function) | additional dimenion | additional dimenion | <assignee.name> | Get this from stories (another function) | <tags.name> | <tags.name> | <tags.name> | <tags.name> | <tags.name>
PART / MPLAN NO. | PROJECT | DESCRIPTION | INIT DATE | STATUS | TIMESTAMP | INIT_AGE (DAYS) | AGE (DAYS) | PIC | REMARKS | PROJECT_TYPE | AREA | TYPE | DOC_TYPE | SWITCH
| AUTOCOMPACTOR | DOOR FLAP PNUEMATIC CYLINDER - REPAIR | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 14W ENERGY CHAIN - INSPECTION | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 6M DRIVE GEAR MOTOR - PM INSPECTION | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 3Y DRIVE GEAR MOTOR PM CHANGE GEAR OIL | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 3W VIBRATOR - INSPECTION - | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 3W DRIVE GEAR MOTOR - INSPECTION - | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 3W COMPACTOR HOIST - PM - | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 3M VIBRATOR - INSPECTION - | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 3M KNOCKER HAMMER Inspection | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 3M DRIVE GEAR MOTOR - INSPECTION - | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 3M COMPACTOR HOIST - INSPECTION - | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 1Y VIBRATOR MOTOR - INSPECTION | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 1Y DRIVE GEAR MOTOR - INSPECTION - | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 1Y COMPACTOR HOIST - INSPECTION | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 1M VIBRATOR MOTOR - INSPECTION | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 1M KNOCKER HAMMER Inspection | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | 1D VIBRATOR MOTOR - INSPECTION | 2024-03-01 | DONE | 2024-08-02 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | EXPULSION VALVE CYLINDER SERVICING E54 2.5Y | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC BYPASS VALVE SERVICING E54 | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC LID CYLINDER SERVICING E54 2Y | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC LID LOCK CYLINDER SERVICING E542Y | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC OVER CENTRE VALVE SERVICING E54 | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC PRESSURE RELIEF VALVE SERVICING | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC QUICK ACTING VALVE SERVICING E54 | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC SPEED REGULATOR VALVE SERVICING | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC STOP VALVE (HS-22W-6M) SERVICING | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC VALVE (HS-43W-6) SERVICING E54 | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| HYDRAULIC PROJECT | HYDRAULIC VALVE (HS-43W-6V) SERVICING E54 | 2024-03-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 163.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| GCU+ | <to utilize existing MPLAN> | 2024-03-01 | DONE | 2024-07-29 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| WATER HEATER | <to utilize existing MPLAN> | 2024-03-01 | DONE | 2024-07-29 | 163.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| GCCD Transport Phase 1 | 2Y (15000H) Diverter Maintenance | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 102.7642 | 8.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| GCCD Transport Phase 1 | 6M (4000H) Diverter Maintenance | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 102.7642 | 8.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| GCCD Transport Phase 1 | 3Y DRIVE GEAR MOTOR PM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 102.7642 | 8.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| GCCD Transport Phase 1 | 6M DRIVE GEAR MOTOR PM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 102.7642 | 8.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| GCCD Transport Phase 1 | Rotary Valve GL 300 - 3M (2500OH) Inspection | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 102.7642 | 8.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| GCCD Transport Phase 1 | Rotary Valve GL 300 - 12M (10000OH) Servicing | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 102.7642 | 8.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| SIR | Sealing or Quenching Liquid Check 2Y | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| SIR | Sealing or Quenching Liquid Check 1D | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| SIR | Replacement of Shaft Seal 2Y | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| SIR | Replacement of Motor 2Y (Existing MPLAN) | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| SIR | Calibration of Pressure Transmitter 52W | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| SIR | Replacement of Valve Terminal | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| SIR | 3M 2000L Sludge Tank Agitator Gearbox - INSPECTION | 2024-06-01 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 71.7642 | 6.7642 | Jenelyn Allado | Hand over to Maam Allado for review. | OLD | Coffee | TARGET | MPLAN | 1
| SIR | 3Y 2000L Sludge Tank Agitator Gearbox - CHANGE GEAR OIL | 2024-06-01 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 71.7642 | 6.7642 | Jenelyn Allado | Hand over to Maam Allado for review. | OLD | Coffee | TARGET | MPLAN | 1
| SIR | 6M 2000L Sludge Tank Agitator Gearbox - INSPECTION | 2024-06-01 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 71.7642 | 6.7642 | Jenelyn Allado | Hand over to Maam Allado for review. | OLD | Coffee | TARGET | MPLAN | 1
| IPTA VACUUM PUMP | 12W VACUUM PUMP LEMA 251 9Z Inspection | 2024-07-08 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-09 | 34.7642 | 2.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| IPTA VACUUM PUMP | 12W VACUUM PUMP LEMA 425 AZ Inspection | 2024-07-08 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-09 | 34.7642 | 2.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| ICIP | MPlan1_Butterfly Valves.FS | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| ICIP | MPlan2_Mixproof Valves.FS | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| ICIP | MPlan3_Pneumatic Actuator Replacement.FS | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| ICIP | Replacement of Motor - 801 | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| ICIP | Replacement of Shaft Seal - 803 | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| ICIP | Sealing or Quenching Liquid Check - 802 | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| ICIP | Replacement of Motor - 798 | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| ICIP | Replacement of Shaft Seal - 800 | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| ICIP | Sealing or Quenching Liquid Check - 799 | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 223.7642 | 223.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | MPLAN | 1
| AUTOCOMPACTOR | Nozzle Spray 1/4 | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 223.7642 | 132.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Hoist Control Set DEMAG | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 223.7642 | 132.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Hoist Electric DEMAG | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 223.7642 | 132.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Hose pre-wet ESI-NEP 6 | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 223.7642 | 132.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Hose water nipple union | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 223.7642 | 132.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Hose water pipe union | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 223.7642 | 132.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Hose water nipple union ESIC BSP 4mtrs | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 223.7642 | 132.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Motor vibrating flap ESIC VV40B | 2024-01-01 | DONE | 2024-04-01 | 223.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Valve Solenoid Spray | 2024-01-01 | DONE | 2024-04-01 | 223.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Valve Solenoid Spray 1 1/2" DP100 | 2024-01-01 | DONE | 2024-04-01 | 223.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Chain Duplex ESIC | 2024-01-01 | DONE | 2024-04-01 | 223.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Motor Gear SW Helical | 2024-01-01 | DONE | 2024-04-01 | 223.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | MaghSpare Partser Knocker Nippon SIC-1AS | 2024-01-01 | DONE | 2024-04-01 | 223.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | MaghSpare Partser Knocker Nippon SB-1A | 2024-01-01 | DONE | 2024-04-01 | 223.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Actuator Door Flap ESIC MDUH 1003 | 2024-01-01 | DONE | 2024-04-01 | 223.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | Switch Proximity | 2024-01-01 | DONE | 2024-04-01 | 223.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| AUTOCOMPACTOR | SKF Bearing FYTB 15 FM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 102.7642 | 2.7642 | John Rey Santander |  | OLD | Coffee | ADDITIONAL | AMM | 1
| AUTOCOMPACTOR | Spring Compression, OD 50-51mm 100mm L | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 102.7642 | 132.7642 | Jenelyn Allado |  | OLD | Coffee | ADDITIONAL | AMM | 1
| AUTOCOMPACTOR | Cylinder Pneumatic 160x100 mm 12kN Festo | 2024-05-01 | DONE | 2024-04-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | AMM | 1
| AUTOCOMPACTOR | Hose PTFE Exitflex EF179 1/4" OL=30cm | 2024-05-01 | DONE | 2024-04-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | AMM | 1
| AUTOCOMPACTOR | Vibrator Assembly | 2024-05-01 | DONE | 2024-04-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | AMM | 1
| HYDRAULIC PROJECT | Hydraulic cylinder - Expulsion valve - D130L09E0254028 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Tubing Flexible Compair 1089041000205 1000mm nipples FL6.35/FL6.35, Inox | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1089041050201 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1178012011 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2318N001 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2018N002 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2102N001 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2218N001 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - 1118072 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V1502A001 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - D150L11C0330019 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1122120700002 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1122120800003 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - V2818B001 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - V2418B005 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1089040850202 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1089040950202 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1115006144 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - D090L11C0155007 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1122120800002 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1122120850002 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040570202 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - E050A05F0020012 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Silverpress Flexible Tubing - 1089040550204 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - E125B09E0010124 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - 1089041100202 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1119002 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1116014 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1096160003 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1107006 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 10990016002 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1107007 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079D130L10014 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079D150L12011 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079D090L12009 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2018002 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2118002 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079E125A10042 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V0100001 | 2024-05-01 | DONE | 2024-07-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Hose Flex Compair 1122120800001 800mm type: 15L-1ST-15K90L, 800 mm long | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 189041100202 | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Hydraulic valve - V2318N002 type: HS-4/3W-6 | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Hydraulic valve - V2318N004 type: HS-2/2W-6/M | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Pneum.- throttle-check valve - 1135016001 type: DRV-18 | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Hydraulic solenoid valve 4/2 - 1096000022 type: MS-W 4/2W-10 | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Stiffener sleeve INOX - 1115006061 Type: SO 50003-6-4 | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Repair kit for pneum. locking-cylinder - 1079E050A06008 V50-20EdK/spez.9 | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Hose Flexible Compair 1122120950002 950mm | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1178012012 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1115006117 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1089081200001 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040610201 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040630201 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040500205 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - 1089040950203 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - 1115006497 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1096100001 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1144007 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1115006439 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2318002 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2318001 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2118001 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2418004 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079E125A10041 | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 102.7642 | 13.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Silverpress flexible tubing - 1089041000201 | 2024-05-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Silverpress Tubing - 10890812200002 | 2024-05-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Hydraulic Flexible Tubing - 1122120500004 | 2024-05-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Baering Bush DA115 - 1005115004 | 2024-05-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Thermal Sleeve Braided Fibreglass - 398-896 | 2024-05-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Oil Level switch | 2024-05-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Hydraulic Internal Gear Pump | 2024-05-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Shaft Socket - | 2024-05-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| HYDRAULIC PROJECT | Suction filter - 10990040001 type: S45 - G1"-A | 2024-05-01 | ON-GOING REFLECTING COMMENTS | 2024-08-08 | 102.7642 | 3.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| GCU+ | Gasket Klinger C4408 107x52x1.5mm | 2024-05-01 | DONE | 2024-05-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| GCU+ | Gasket Klinger C4408 145x80x1.5mm | 2024-05-01 | DONE | 2024-05-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| GCU+ | Gasket Klinger C4408 107x50x1.5mm | 2024-05-01 | DONE | 2024-05-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| GCU+ | Gasket Steelflon 98x50x2mm | 2024-05-01 | DONE | 2024-05-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| WATER HEATER | Gasket head Ginox 3813/22A 735x3mm | 2024-05-01 | DONE | 2024-05-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| WATER HEATER | Gasket head Ginox 3813/22A 585x3mm | 2024-05-01 | DONE | 2024-05-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| WATER HEATER | Gasket head Ginox 3813/22B 735x3mm | 2024-05-01 | DONE | 2024-05-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| WATER HEATER | Gasket head Ginox 3813/22B 585x3mm | 2024-05-01 | DONE | 2024-05-01 | 102.7642 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| WATER HEATER | 3/4"W Flanges Stud A193 Gr B7 (ZN) SET (+ 3/4"W Stud nuts ASTM A184 Gr 2H DIN-934,3/4"W Stud washer HV140 (ZN) dia21 DIN125) | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-03 | 102.7642 | 8.7642 | John Rey Santander | Forwarded to Maam Jen for review last July 4 but no feedback. Decided to proceed with docusign. | OLD | Coffee | ADDITIONAL | AMM | 1
| GCCD Transport Phase 1 | Gearmotor SEW EURODRIVE R57 DRN80M4/TF | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 71.7642 | 2.7642 | John Rey Santander |  | OLD | Coffee | TARGET | AMM | 1
| GCCD Transport Phase 1 | Ball-bearing 6314-2RS1 PN:03431534 | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 71.7642 | 102.7642 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | AMM | 1
| GCCD Transport Phase 1 | Nilos ring 6314 ZJV PN:03433034 | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 71.7642 | 102.7642 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | AMM | 1
| GCCD Transport Phase 1 | Key 10x8x50 St PN:46016050 | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 71.7642 | 102.7642 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | AMM | 1
| GCCD Transport Phase 1 | Packingset AL-BL 300/350 TEADIT 2005 FDA EC 1935/2004 PN:20803094 | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 71.7642 | 102.7642 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | AMM | 1
| GCCD Transport Phase 1 | Chain wheel 3/4''-21t-dia38 St PN:CW0202138 | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 71.7642 | 102.7642 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | AMM | 1
| GCCD Transport Phase 1 | Chain wheel 3/4''-13t-dia35 St PN:CW0201335 | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 71.7642 | 102.7642 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | AMM | 1
| GCCD Transport Phase 1 | 12B-1 Roller Chain L=43.52in | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 71.7642 | 2.7642 | John Rey Santander |  | OLD | Coffee | TARGET | AMM | 1
817330413 | SIR | Spare mec. seal 9.667a 2K 10V2/2N 5V2 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
180350376 | SIR | O-Ring 376 ARP Ø247,02x5,33 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
180350029 | SIR | O-Ring 029 ARP Ø37,82x1,78 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
817330413 | SIR | Spare mec. seal 9.667a 2K 10V2/2N 5V2 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
180350376 | SIR | O-Ring 376 ARP Ø247,02x5,33 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
180350029 | SIR | O-Ring 029 ARP Ø37,82x1,78 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
816310629 | SIR | Spare mec. seal 9.468 2N 5V2 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
180350364 | SIR | O-Ring 364 ARP Ø170,82x5,33 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
180350022 | SIR | O-Ring 022 ARP Ø25,12x1,78 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
816330271 | SIR | Seal Mechanical Fristam (Model: Fristam 752/250 VA) | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
1803500377 | SIR | O-Ring Ø253 37x5 | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 9.7642 | 9.7642 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | AMM | 1
| SIR | Seal Mechanical Fristam FPE 752/250 VA | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | O-ring Firstam FPE 752/250 VA 376 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | O-ring Firstam FPE 752/250 VA 029 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Pneumatic Control Valve 3730-3 | 2024-07-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-07-01 | 41.7642 | 41.7642 | Zaira April Flores | For docusign Sir JC | OLD | Coffee | TARGET | AMM | 1
| SIR | O-Ring Fristam 180350377 Ø253 37x5 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Seal Mechanical Fristam 816330271 9.467a 2K 10V2 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Transmitter Temperature Rosemount 248 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Transmitter Temperature Rosemount 2051TG3A2B21AS5B4Q4 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Transmitter Temperature Rosemount 2051 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Sensor Magnetic Flow Meter Rosemount 8705 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Valve Terminal Festo HY-MPA-FB-VI-MSB6 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Base-sub VMPA1-FB-AP-4-1 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Seal VMPA1-DP | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Module Electrical Manifold VMPA1-FB-EV-AB | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Module Electronics VMPA1-FB-EMG-8 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Valve Solenoid VMPA1-M1H-J-PI | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Module Input CVX-16DE | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Module Analogue Input CVX-4AE-1 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Module Analogue Output CPX-2AA-U-I | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Transmitter Pressure UPT-20 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Load cell Controller Minebea PR 5230/02 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Valve Pneumatic Samson 3730-3 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| SIR | Valve Control Samson 3241-7 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 41.7642 | 41.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Digital Conductivity | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Control Board Pneumatic V70 Think Top | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Control Board Pneumatic V50 Think Top | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Control Unique RV-P | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Flowmeter Magnetic Rosemount | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Sensor Toroidal Conductivity Rosemount | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Power Supply Board for 1056-01 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | O-Ring Cover Fristman 3552/215 B | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Impeller Nut O-Ring | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Seal Mechanical Fristam 3552/215B | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Motor Theo Halter GmbH Elektromotoren | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Unique Mixproof Welded DN 50/50 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Unique Mixproof Welded DN 40/40 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Pneumatic Macainox 3"DIA | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Pneumatic Macainox 2"DIA | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Pneumatic Ball SS Macainox 2"DIA | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Mixproof Unique Mecainox 3-Body ISO-DN 100/110 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Mixproof Unique Mecainox 3-Body ISO-DN 76/76 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Butterfly w/ Actuator LKB-F ISO WELD-38 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Butterfly w/ Actuator LKB-F ISO WELD-51 | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Manual Ball Mecainox 1" | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Manual Ball Mecainox 3/4" | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Manual Ball SS Macainox 1"DIA | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Non-Return LKC-2 ISO- SMS -51 EPDM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve Non-Return LKC-2 ISO- SMS -76 EPDM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve ButterFly Macainox 6"DIA | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| ICIP | Valve ButterFly Macainox 4" DIA | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 41.7642 | 27.7642 | Jenelyn Allado |  | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | LEMA 251 9Z BLU 4B : 20044252 - Guide disc | 2024-07-25 | WAITING FOR QUOTATION | 2024-07-29 | 17.7642 | 13.7642 | Francis Carlo Tadena | Already have qoutation, waiting for guide disc to be included | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | LEMA 251 9Z BLU 4B : 20072583 - Vane wheel impeller assy | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-03 | 17.7642 | 8.7642 | Francis Carlo Tadena | Already have qoutation, waiting for guide disc to be included | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | LEMA 251 9Z BLU 4B : 65008395 - basic repair kit | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-03 | 17.7642 | 8.7642 | Francis Carlo Tadena | Already have qoutation, waiting for guide disc to be included | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | LEMA 251 9Z BLU 4B : Level indicator LV-300 L=300 | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-02 | 17.7642 | 9.7642 | Francis Carlo Tadena | Not included in the qoutation P124-2034-2 | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | LEMA 425 AZ AA1 4B : 20017164 - guide disc assy | 2024-07-25 | WAITING FOR QUOTATION | 2024-07-29 | 17.7642 | 13.7642 | Francis Carlo Tadena | Already have qoutation, waiting for guide disc to be included | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | LEMA 425 AZ AA1 4B : 20017131 - vane wheel impeller assy | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-03 | 17.7642 | 8.7642 | Francis Carlo Tadena | Already have qoutation, waiting for guide disc to be included | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | LEMA 425 AZ AA1 4B : 65007942 - basic repair kit | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-03 | 17.7642 | 8.7642 | Francis Carlo Tadena | Already have qoutation, waiting for guide disc to be included | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | LEMA 251 9Z BLU 4B : Level indicator LV-300 L=500 | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-02 | 17.7642 | 9.7642 | Francis Carlo Tadena | Not included in the qoutation P124-2034-2 | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | Motor Sterling SIHI GmbH 8.0KW 1750RPM | 2024-08-05 | WAITING FOR QUOTATION | 2024-08-10 | 6.7642 | 1.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | Motor Sterling SIHI GmbH 18KW 1765RPM | 2024-08-05 | WAITING FOR QUOTATION | 2024-08-10 | 6.7642 | 1.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | Heat Exchanger (AMM) | 2024-08-05 | NOT STARTED | 2024-08-05 | 6.7642 | 6.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | AMM | 1
| IPTA VACUUM PUMP | Heat Exchanger (MPLAN) | 2024-08-05 | NOT STARTED | 2024-08-05 | 6.7642 | 6.7642 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | MPLAN | 1
| GC Van Unloading Facility | 1M Green Coffee Transport Unimaster Dust Collector Inspection | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 20.7642 | 6.7642 | Jenelyn Allado |  | NEW | Coffee | TARGET | MPLAN | 1
| GC Van Unloading Facility | 1W Green Coffee Transport Unimaster Dust Collector Inspection | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 20.7642 | 6.7642 | Jenelyn Allado |  | NEW | Coffee | TARGET | MPLAN | 1
| GC Van Unloading Facility | 1Y Green Coffee Transport Unimaster Dust Collector Inspection | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 20.7642 | 6.7642 | Jenelyn Allado |  | NEW | Coffee | TARGET | MPLAN | 1
| GC Van Unloading Facility | 6M Green Coffee Transport Unimaster Dust Collector Inspection | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 20.7642 | 6.7642 | Jenelyn Allado |  | NEW | Coffee | TARGET | MPLAN | 1
| PEC 2020: PE Panel Cooling | <all MPLAN> | 2024-07-01 | WAITING FOR OTHER DOCS | 2024-07-22 | 41.7642 | 20.7642 | Rosiell Suello | Material list from SE for equipment data | NEW | Coffee | TARGET | MPLAN | 0
| PEC 2020: PE Panel Cooling | <all AMM> | 2024-07-01 | WAITING FOR OTHER DOCS | 2024-07-22 | 41.7642 | 20.7642 | Rosiell Suello | Material list from SE for equipment data | NEW | Coffee | TARGET | AMM | 1
| PEC 2020: Process adaptation | <all> | 2024-07-01 | NOT STARTED | 2024-08-03 | 41.7642 | 8.7642 | Francis Carlo Tadena |  | NEW | Coffee | TARGET |  | 0
| FFE-RARE | <all> | 2024-07-01 | NOT STARTED | 2024-08-03 | 41.7642 | 8.7642 | Francis Carlo Tadena |  | NEW | Coffee | TARGET |  | 0
| PEC 2020: Spot Cooling | <Dosusign to inform stakeholders of the unnecessary MPLAN> | 2024-07-01 | WAITING FOR OTHER DOCS | 2024-08-03 | 41.7642 | 8.7642 | Rosiell Suello | Waiting for docu assessment form to be fully signed by Sir Mark | NEW | Coffee | TARGET | MPLAN | 1
| PEC 2020: Spot Cooling | <Dosusign to inform stakeholders of the unnecessary AMM> | 2024-07-01 | WAITING FOR OTHER DOCS | 2024-08-03 | 41.7642 | 8.7642 | Rosiell Suello | Waiting for docu assessment form to be fully signed by Sir Mark | NEW | Coffee | TARGET | AMM | 1

## Sheet1
AUTOCOMPACTOR
HYDRAULIC PROJECT
GCU+
WATER HEATER
GCCD Transport Phase 1
SIR
IPTA VACUUM PUMP
ICIP
GC Van Unloading Facility
PEC 2020: PE Panel Cooling
PEC 2020: Process adaptation
FFE-RARE
PEC 2020: Spot Cooling

## Sheet4
STATUS | Count of STATUS
ON-GOING FIRST DRAFT | 4
WAITING FOR OTHER DOCS | 4
NOT STARTED | 5
ON-GOING ROUTING/REVIEW (PHYSICAL) | 7
WAITING FOR QUOTATION | 16
ON-GOING ROUTING/REVIEW (DOCUSIGN) | 27
DONE | 89
FULLY SIGNED - FOR ENROLLMENT | 95

## list
| <tags.name> | <tags.name> |  | <tags.name> | <tags.name> | <tags.name> | <tags.name>
STATUS | TYPE | DOC_TYPE | PIC | AREA | PROJECT | PROJECT_TYPE | doc_status | gen_status | Motor Vibrating VV40B/4
DONE | TARGET | AMM | Alan Cris Caintic | Coffee | AUTOCOMPACTOR | OLD | Complete | NOT-AVAILABLE | Peripheral rVibrating Rods
FULLY SIGNED - FOR ENROLLMENT | ADDITIONAL | MPLAN | Alfred Martin Torcende | Milks | FFE-RARE | NEW | Lacking | COMPLETE | Switch Limit General Purpose 500V 10A
NOT STARTED |  |  | Allan Cuarteros | IS | GC Van Unloading Facility |  | No available |  | Hoist Electric ZNK 100 A8/2
ON-GOING FIRST DRAFT |  |  | Andrean Candeloza | Others | GCCD Transport Phase 1 |  | Incomplete |  | Motor Gear Sew SEW R 27 DRN71M4/BE1, Hel
ON-GOING REFLECTING COMMENTS |  |  | April Kaye Uayan |  | GCU+ |  |  |  | Sensor Proximity Inductive PA 40mm
ON-GOING ROUTING/REVIEW (DOCUSIGN) |  |  | Celerito Cardines |  | HYDRAULIC PROJECT |  |  |  | Cylinder SMC CP96SDB80-150C Bore Size 80
ON-GOING ROUTING/REVIEW (PHYSICAL) |  |  | Christine Estoque |  | ICIP |  |  |  | Controller Unit SMC AS3001F-12
WAITING FOR OTHER DOCS |  |  | Christopher Donguines |  | PEC 2020: PE Panel Cooling |  |  |  | Knocker Controller SB-1A SIC Maghammer
WAITING FOR QUOTATION |  |  | Elleh Jipos |  | PEC 2020: Process adaptation |  |  |  | Knocker Nippon Maghammer SIC-1AS
WAITING FOR STAKEHOLDER INPUT |  |  | Emmanuel Ben Jr. Roa |  | PEC 2020: Spot Cooling |  |  |  | Chain Link
|  |  | Francis Carlo Tadena |  | SIR |  |  |  | End Bracket
|  |  | Janeth Jabien |  | WATER HEATER |  |  |  | Switch Selector 3 10A at 400V 2NO
|  |  | Jenelyn Allado |  | IPTA VACUUM PUMP |  |  |  | Switch Selector 12VDC 25A
|  |  | Joel Echem | [5 empty] | Switch Pushbutton Momentary 600VAC 10A
|  |  | John Carlo Baltazar | [5 empty] | Switch Selector 3 3P CA10A212624FT6V
|  |  | John Rey Santander | [5 empty] | Gauge Temp 100mm 0-120C Direct
|  |  | Madeleine Parojinog | [5 empty] | Relay Safety 1P 24VDC 5-110VDC SPDT
|  |  | Maria Jean Walag | [5 empty] | Relay Em Screw Terminal or Spring Clamp
|  |  | Marian Louise Rosaldo | [5 empty] | Hoist Demag (DC PRO 10-2000 2/1)
|  |  | Marian Zarate | [5 empty] | Energy Chaing, IGUS E4.42.20.200
Mark Anthony Pana
Marlon Pingoy
Merachell Escobido
Zaira April Flores
Rosiell Suello