## original
F O R M S
BID BREAKDOWN DATA SHEET
PROJECT TITLE: |  |  |  |  | Date: | 2023-12-08
SUPPLY OF MATERIALS, LABOR, CONSUMABLES, TOOLS TECHNICAL SUPERVISION, AND TESTING FOR THE PROPOSED INSTALLATION OF GREEN COFFEE TRANSPORT LINE
COST CENTER: |  |  |  |  | Reference:
|  |  | IN HOUSE |  |  |  |  | RHAJTEK |  |  |  |  | BP INDUSTRIAL |  |  |  |  | APCI
ITEM NO. | DESCRIPTION |  | Man'r | Unit | Qty | UNIT COST | AMOUNT | Man'r | Unit | Qty | UNIT COST | AMOUNT | Man'r | Unit | Qty | UNIT COST | AMOUNT | Man'r | Unit | Qty | UNIT COST | AMOUNT
A. | GENERAL REQUIREMENTS
1 | Mobilization/Temfacil/Housing, Personnel travel, etc. |  |  | lot | 1 | 30000 | 30000 |  | lot |  |  | 350000 |  | lot | 1 | 10500 | 10500 |  | lot | 1 | 160600 | 160600
| Demobilization |  |  | lot | 1 | 20000 | 20000 |  | lot |  |  | 190000 |  | lot | 1 | 10500 | 10500 |  | lot | 1 | 110000 | 110000
2 | Safety Provisions
| a. Comfort grip gloves |  |  | pairs | 300 | 50 | 15000 |  | pairs | 455 | 62.5 | 28437.5 |  | pairs | 20 | 200 | 4000 |  | pairs | 100 | 50 | 5000
| b. Dust Mask N95 |  |  | bxs | 30 | 150 | 4500 |  | bxs | 56 | 187 | 10472 |  | bxs | 30 | 400 | 12000 |  | bxs | 6 | 650 | 3900
| c. Caution Tape |  |  | roll | 1 | 1500 | 1500 |  | roll | 2 | 1500 | 3000 |  | roll | 1 | 1300 | 1300 |  | roll | 2 | 2000 | 4000
| d. Safety Signages |  |  | lot | 1 | 2000 | 2000 |  | lot | 1 | 12500 | 12500 |  | lot | 1 | 3000 | 3000 |  | lot | 1 | 10000 | 10000
| e. Fire Blanket (Size: 2m x 2m, temperatures up to 500°C Maximum) |  |  | pcs | 3 | 1500 | 4500 |  | pcs | 4 | 1250 | 5000 |  | pcs | 3 | 2500 | 7500 |  | pcs | 4 | 4500 | 18000
| f. Welding blanket Size: 2m x 2m, Minimum Type Rating = Heavy Duty = 1200 - 1500°C) |  |  | pcs | 3 | 1500 | 4500 |  | pcs | 4 | 1250 | 5000 |  | pcs | 3 | 1500 | 4500 |  | pcs | 4 | 6500 | 26000
| g. hygiene uniform (2 upper x 1 lower) per personnel |  |  | pairs | 32 | 1300 | 41600 |  | lot | 1 | 43750 | 43750 |  | pairs | 57 | 500 | 28500 |  | pairs | 16 | 3500 | 56000
| h. Safety shoes |  |  | pairs | 16 | 2000 | 32000 |  | pairs | 16 | 1562 | 24992 |  | pairs | 20 | 2000 | 40000 |  | pairs | 16 | 2000 | 32000
| i. Safety harness |  |  | pcs | 10 | 2000 | 20000 |  | pcs | 6 | 3125 | 18750 |  | pcs | 10 | 2000 | 20000 |  | pcs | 10 | 3900 | 39000
| j. Safety vest |  |  | pcs | 16 | 300 | 4800 |  | pcs | 16 | 250 | 4000 |  | pcs | 20 | 300 | 6000 |  | pcs | 16 | 200 | 3200
| k. Welding gloves |  |  | pairs | 8 | 300 | 2400 |  | pairs | 8 | 562 | 4496 |  | pairs | 8 | 300 | 2400 |  | pairs | 8 | 1200 | 9600
| l. Welding mask |  |  | pcs | 8 | 800 | 6400 |  | pcs | 4 | 500 | 2000 |  | pcs | 8 | 1500 | 12000 |  | pcs | 4 | 3500 | 14000
| m. Safety ear plugs |  |  | pcs | 20 | 100 | 2000 |  | pcs | 16 | 150 | 2400 |  | pcs | 40 | 100 | 4000 |  | pcs | 16 | 100 | 1600
| m. Safety googles |  |  | pcs | 20 | 300 | 6000 |  | pcs | 16 | 200 | 3200 |  | pcs | 20 | 300 | 6000 |  | pcs | 32 | 250 | 8000
3 | Tools & Equipment Rentals
| GTAW or Tig welding machine |  |  | unit | 3 | 2000 | 6000 |  | unit | 4 | 5625 | 22500 |  | unit | 3 | 3000 | 9000 |  | unit | 4 | 10000 | 40000
| Portable Grinders 7"Ø with double insulation standard |  |  | unit | 3 | 2500 | 7500 |  | unit | 2 | 3125 | 6250 |  | unit | 3 | 2000 | 6000 |  | unit | 4 | 2000 | 8000
| Portable Grinders 4"Ø with double insulation standard |  |  | unit | 4 | 1500 | 6000 |  | unit | 4 | 2500 | 10000 |  | unit | 3 | 2000 | 6000 |  | unit | 8 | 1000 | 8000
| Portable hand drill with double insulation standard |  |  | unit | 3 | 2000 | 6000 |  | unit | 2 | 1875 | 3750 |  | unit | 3 | 2000 | 6000 |  | unit | 2 | 1000 | 2000
| portable jack hammer |  |  | unit | 3 | 2000 | 6000 |  | unit | 1 | 2500 | 2500 |  | unit | 3 | 2000 | 6000 |  | unit | 1 | 2000 | 2000
| Extension wire |  |  | unit | 5 | 1500 | 7500 |  | rolls | 6 | 1500 | 9000 |  | unit | 5 | 1500 | 7500 |  | unit | 4 | 1200 | 4800
| Hand Tools (Complete set of combination wrenches) metric and english standard with torque wrench (4 sets in two groups) |  |  | lot | 1 | 2000 | 2000 |  | lot | 2 | 1900 | 3800 |  | lot | 1 | 2000 | 2000 |  | lot | 4 | 3000 | 12000
| Welding Panel (both for 440 and 220 volts supply ) w/ meter |  |  | unit | 1 | 2000 | 2000 |  | unit | 1 | 6200 | 6200 |  | unit | 1 | 2000 | 2000 |  | unit | 1 | 15000 | 15000
| Chain Block, shackles, Lifting belt, lifting lugs, rope & etc. with certificate |  |  | lot | 1 | 20000 | 20000 |  | lot | 2 | 3700 | 7400 |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 3000 | 3000
| Structural analysis for lifting lugs & erected scaffoldings |  |  | lot | 1 | 50000 | 50000 |  | lot | 1 | 25000 | 25000 |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 20000 | 20000
| Scaffolding with blind caps |  |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 75000 | 75000 |  | lot | 1 | 100000 | 100000 |  | lot | 30 | 2500 | 75000
| Enclosure (scaffolding and tarp) |  |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 18000 | 18000 |  | lot | 1 | 210000 | 210000 |  | lot | 1 | 10000 | 10000
| Lighting |  |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 10000 | 10000 |  | lot | 10 | 500 | 5000
| Exhaust fan with duct and filter box |  |  | lot | 1 | 30000 | 30000 |  | units | 2 | 2500 | 5000 |  | lot | 1 | 150000 | 150000 |  | lot | 4 | 3500 | 14000
| Concrete works (demolition & repair) |  |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 35000 | 35000 |  | lot |  |  | 0 |  | lot | 1 | 45000 | 45000
| Methodology of the project |  |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 4500 | 4500 |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 5000 | 5000
| As built drawing |  |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 15000 | 15000
| Sub-Total | [5 empty] | 425200 |  |  |  |  | 966897.5 |  |  |  |  | 751700 |  |  |  |  | 784700
B. | Design, Supply & Install of Pulse Jet Dust Collector with Specification Below | [7 empty] | lot | 1 | 4300000 | 4300000
Capacity: 10,000 CFM (Base on the openingof the enclosure w/out plastic curtain)
Filtering Area: 1,648 ft2
Air to Cloth Area: 6 ft/min
No. of filter bags: 100 pcs
Type of Cleaning System : Pulse on Demand (POD)
| Size & Type of Filter Bags: 160mm dia x 3000mm L with Snap band, anti static polyester | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
| Explosion Vent type: Membrane Type - ATEX Certified or Brixxon Safety Latches | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
Dust discharger: Rotar valve drivenby a 1 hp Generator
| No. of Collecting Drums: 2 pcs of collecting drums with roller | [10 empty] | 0
| Sub-Total | [5 empty] | 0 |  |  |  |  | 4300000 |  |  |  |  | 0
B.1 | Installation of Rooms
| I beam 6x6 | [10 empty] | 0 |  | lx | 20 | 23931 | 478620
| SS plate 3mm | [12 empty] | shts | 57 | 13506 | 769842
| Channel bar 6x2x6mm | [10 empty] | 0 |  | lx | 9 | 10140 | 91260
| Top coat paint | [10 empty] | 0 |  | gal | 3 | 1465 | 4395
| Primer paint | [12 empty] | gal | 3 | 1465 | 4395
| Cup sanding | [10 empty] | 0 |  | pcs | 10 | 162 | 1620
| Angle bar2x2x6mm | [10 empty] | 0 |  | lx | 50 | 2604 | 130200
| PVC Curtain | [12 empty] | lot | 1 | 30000 | 30000
| Stranded wire # 14 | [10 empty] | 0 |  | box | 2 | 2500 | 5000
| Expansion bolt | [10 empty] | 0 |  | pcs | 16 | 200 | 3200
| Steel Plate | [12 empty] | shts | 2 | 10676 | 21352
| Oxy/Acy | [10 empty] | 0 |  | sets | 3 | 4884 | 14652
0
| Sub-Total | [15 empty] | 1036712
B.2 | Installation and Supply of Dust Collector Body, Blowers
| SS304 3mm thk x 4' x 8' sheet | [17 empty] | sheets | 4 | 18000 | 72000
| SS304 4" dia ferrule assembly | [17 empty] | pc | 1 | 2280 | 2280
| SS304 9mm thk x 4' x 8' sheet | [17 empty] | sheet | 1 | 55200 | 55200
| SS304 6mm dia x 20ft round bar | [17 empty] | lengths | 5 | 480 | 2400
| SS304 3mm thk x 20" x 20" ss plate | [17 empty] | pc | 1 | 1440 | 1440
| 5" dia filter sleeve w/ snap band x 600mm length | [17 empty] | pcs | 6 | 2766 | 16596
| SS304 2" dia x 20ft shaft | [17 empty] | pc | 1 | 27660 | 27660
| SS304 10mm thk x 10" x 10" ss plate | [17 empty] | pcs | 2 | 4440 | 8880
| air filter with regulator 1/2" dia opening 5 microns | [17 empty] | PC | 1 | 5820 | 5820
| SS304 1 1/2" dia ferrule assembly T304 | [17 empty] | sets | 2 | 1080 | 2160
| diapragm valve goyen 3/4" dia | [17 empty] | pc | 1 | 18000 | 18000
| SS304 3mm thk x 500mm x 500mm neoprene gasket white | [17 empty] | pcs | 3 | 1653.6 | 4960.8
| SS304 3/8" x 2" dia nipple sch 30 | [17 empty] | pc | 1 | 192 | 192
| SS304 3/8" dia ball valve | [17 empty] | pc | 1 | 1200 | 1200
| SS304 3/4" dia coupling #150 | [17 empty] | pc | 1 | 276 | 276
| SS304 3/4" dia nipple sch.30 | [17 empty] | pcs | 3 | 186 | 558
| SS304 1/2" dia ball valve | [17 empty] | pc | 1 | 1200 | 1200
| SS304 4.5mm thk x 1 1/2" x 8ft flat bar | [17 empty] | pc | 0.5 | 1051.2 | 525.6
| SS304 3/8" dia x 1 1/4"L Bolt & nut | [17 empty] | pcs | 4 | 30 | 120
| SS304 3/4" dia x 90deg weld ends elbow sch.30 | [17 empty] | pcs | 2 | 372 | 744
| SS304 1/2" dia x 20ft pipe sch. 30 | [17 empty] | lengths | 3 | 2580 | 7740
| SS304 1/2" dia x 90 deg weld ends elbow | [17 empty] | pcs | 5 | 348 | 1740
| SS304 1/2" dia union patente | [17 empty] | pc | 1 | 492 | 492
| SS304 1/2" dia nipple | [17 empty] | pcs | 5 | 168 | 840
| SS304 1/2" dia ball valve | [17 empty] | pcs | 2 | 1200 | 2400
C. | Design, Supply & Install of Air base Stainless Duct SystemComplete Individual Dumper, Suction Hood & Necessary Support Bracket, Discharge of Clean Air to Outside the Building | [7 empty] | lot | 1 | 2200000 | 2200000
Material of Construction shall be SS304 Spiral Duct Type for Straight Duct & Elbow Gage 16 for Transition- For Suction Ducts
Material of Construction shall be GI Plate Spiral Duct Type for Straight Duct & Elbow Gage 14 for Manifold- For Discharge Duct only meaning from Dust Collector to Discharge of Blower to be painted with Aluminum Silver
| Sub-Total | [10 empty] | 2200000
C.1 | Installation of Dust Collector Unit
| Donaldson UMA 253 Dust Collector |  |  | unit | 1 | 1600000 | 1600000 | [6 empty] | unit | 1 | 1716338 | 1716338
| Stranded wire # 14mm |  |  | box | 4 | 55000 | 220000 | [6 empty] | box | 4 | 65000 | 260000
| Electrical tubing |  |  | lot | 1 | 70000 | 70000 | [6 empty] | lot | 1 | 80000 | 80000
| Sub-Total | [5 empty] | 1890000 | [9 empty] | 2056338
C.2 | Installation and Supply of Hood and Piping
| 4" dia ss sanitary butterfly valve ferrule ends | [17 empty] | pcs | 2 | 10200 | 20400
| 4" dia ferrule assembly T304 | [17 empty] | pcs | 8 | 2280 | 18240
| 4" dia x 20ft ss sanitary tube T304 | [17 empty] | lengths | 4 | 25200 | 100800
| 4.5mm dia x 20ft ss round bar T304 | [17 empty] | length | 2 | 312 | 624
| 4" dia x90 deg ss sanitary elbow T304 | [17 empty] | pc | 8 | 2520 | 20160
| Sub-Total | [20 empty] | 395648.4
D. | Design, Supply & Install of Centrifugal Fan complete with 40HP motor | [7 empty] | lot | 1 | 1200000 | 1200000
NYB Centrifugal Fan radial wheel (S20), Powder Coat Finish, Size 364 with DH wheel
Statically & dynamically balance, heavy duty scroll housing, arrangement 9. Complete with
Service Handhole, drain plug, common base, inlet & outlet flange, rubber type vibration
| isolators, pillow block bearings, shaft flexible coupling, shaft bearing guard, coupling guard | [10 empty] | 0
| direct coupled to 40hp motor, 3 phase 220/440 Vac, 60hz, TEFC Electric Motor. | [10 empty] | 0
| Sub-Total | [5 empty] | 0 |  |  |  |  | 1200000 |  |  |  |  | 0
D.1 | Installation of Ducting and hood
| Fabricated stainless ducting |  |  | lot | 1 | 300000 | 300000 | [6 empty] | lot | 1 | 405190 | 405190
| Stainless elbow 12" |  |  | lot | 1 | 40000 | 40000 | [6 empty] | lot | 1 | 48840 | 48840
| Fabricated stainless hood |  |  | lot | 1 | 200000 | 200000 | [6 empty] | lot | 1 | 215000 | 215000
[7 empty] | 540000 | [9 empty] | 669030
D.2 | Installation and Supply of Dust Collector Electrical System
| Control panel 24"L x 15"W x 8" depth SS | [17 empty] | pc | 1 | 48000 | 48000
| 10amp circuit breaker | [17 empty] | pc | 1 | 1890 | 1890
| Omron timer with base 11pins | [17 empty] | pcs | 2 | 3120 | 6240
| 10amp magnetic contactor | [17 empty] | pc | 1 | 1164 | 1164
| Overload relay 10amp | [17 empty] | pc | 1 | 1884 | 1884
| 300watts step down transformer | [17 empty] | pc | 1 | 3960 | 3960
| Push button red/green | [17 empty] | pcs | 2 | 1008 | 2016
| Pilot light green/red | [17 empty] | pcs | 2 | 432 | 864
| 1000CFM Blower with motor | [17 empty] | lot | 1 | 42000 | 42000
| Electric Motor 3Hp TEFC | [17 empty] | pc | 1 | 14688 | 14688
| Sub-Total | [20 empty] | 66018
E. | Design, Supply & Install of Electric Motor Controllers | [7 empty] | lot | 1 | 650000 | 650000
Components of Motor Controllers:
Stainless Panel Board, size: 700mm x 600mm x 300mm
MCCB 125A, 3 Phase Schneider, Soft Starte Alti Start 22, Schneider brand
| Motor Circuit Breaker GV3- L50, Schneider brand | [10 empty] | 0
| Motor Circuit Breaker GV2- L07, Schneider Brand | [10 empty] | 0
| Control Transformer, 1 phase, 440/ 220 VAC, Yokohama | [10 empty] | 0
| Omron Relay 8 pin with base MY4N | [10 empty] | 0
Miniature Circuit breakers 3 & 6 A, 2 poles Schneider
Autel EcoSerial S12, Made in Italy for Purging System
Conduit Pipes & Fittings
| Consumables | [10 empty] | 0
| Sub-Total | [5 empty] | 0 |  |  |  |  | 650000 |  |  |  |  | 0 |  |  |  |  | 0
E.1 | Installation and Supply of Service Platform
| SS304 3mm thk x 4' x 8' checkered plate | [17 empty] | sheets | 1 | 30000 | 30000
| SS304 channel 4 x 20ft | [17 empty] | lengths | 3 | 15000 | 45000
| SS304 3" dia pipe sch. 20 | [17 empty] | lengths | 2 | 17040 | 34080
| SS304 1 1/4" dia x 20ft pipe sch. 30 | [17 empty] | lengths | 4 | 6000 | 24000
| SS304 1 1/4" dia x 90deg elbow | [17 empty] | pcs | 6 | 612 | 3672
| SS304 15mm thk x 100 x 100 plate | [17 empty] | pc | 1 | 1200 | 1200
| SS304 20mm thk x 150 x 150 plate | [17 empty] | pc | 1 | 2400 | 2400
F. | CONSUMABLES FOR DOC. NO. 04,05,07,09,12,25 & 27
1 | Cutting Discs, 7"Ø, "Tyrolit" brand, 8,600 rated rpm |  |  | pcs | 50 | 190 | 9500 |  | pcs | 50 | 181 | 9050 |  | pcs | 50 | 450 | 22500 |  | pcs | 50 | 196.8 | 9840
2 | Cutting Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm |  |  | pcs | 200 | 90 | 18000 |  | pcs | 200 | 56 | 11200 |  | pcs | 200 | 300 | 60000 |  | pcs | 100 | 133.2 | 13320
3 | Grinding Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm |  |  | pcs | 50 | 85 | 4250 |  | pcs | 15 | 56 | 840 |  | pcs | 100 | 150 | 15000 |  | pcs | 30 | 140.4 | 4212
4 | Tungsten Rod |  |  | pcs | 30 | 150 | 4500 |  | pcs | 16 | 125 | 2000 |  | pcs | 100 | 80 | 8000 |  | pcs | 10 | 146.4 | 1464
5 | SS304 Filler Rod |  |  | kgs | 30 | 1500 | 45000 |  | kgs | 15 | 1500 | 22500 |  | kgs | 30 | 700 | 21000 |  | kgs | 10 | 1032 | 10320
6 | Tig cleene |  |  | jar | 20 | 900 | 18000 |  | jar | 4 | 812 | 3248 |  | jar | 20 | 2920 | 58400 |  | jar | 2 | 2580 | 5160
7 | 6011 welding rod |  |  | kgs | 100 | 200 | 20000 |  | kgs | 40 | 162 | 6480 |  | kgs | 100 | 450 | 45000 |  | kgs | 5 | 156 | 780
7 | 7018 welding rod |  |  | kgs | 50 | 200 | 10000 |  | kgs | 20 | 200 | 4000 |  | kgs | 100 | 450 | 45000 |  | kgs | 5 | 180 | 900
8 | Argon Gas |  |  | cyl | 10 | 2200 | 22000 |  | cyl | 30 | 4625 | 138750 |  | cyl | 10 | 2100 | 21000 |  | cyl | 5 | 3480 | 17400
9 | Sand Paper, # 120 |  |  | pcs | 90 | 50 | 4500 |  | pcs | 30 | 12 | 360 |  | pcs | 90 | 50 | 4500 |  | pcs | 2000 | 19.2 | 38400
10 | Flap Wheel, 4"Ø |  |  | pcs | 50 | 190 | 9500 |  | pcs | 8 | 187 | 1496 |  | pcs | 50 | 300 | 15000 |  | pcs | 15 | 102 | 1530
11 | drill bit/ carbide |  |  | lot | 1 | 3000 | 3000 |  | lot | 0 |  | 0 |  | lot | 1 | 10000 | 10000 |  | lot | 2 | 3000 | 6000
12 | Miscelleneous |  |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 50000 | 50000 |  | lot | 1 | 10932 | 10932
13
| Sub-Total | [5 empty] | 183250 |  |  |  |  | 229924 |  |  |  |  | 375400 |  |  |  |  | 120258
G. | LABOR COSTING FOR FABRICATION
| Project Engineer |  | 1 | days | 10 | 2000 | 20000 | 1 | days | 10 | 1875 | 18750 | 1 | days | 10 | 2500 | 25000 | 1 | days | 35 | 3681.876 | 128865.66
| Quality Officer |  | 1 | days | 10 | 1600 | 16000 | 1 | days | 10 | 1375 | 13750 | 1 | days | 10 | 1500 | 15000 | 1 | days | 35 | 2642.688 | 92494.08
| Safety Officer |  | 1 | days | 10 | 1200 | 12000 | 1 | days | 10 | 1375 | 13750 | 1 | days | 10 | 1000 | 10000 | 1 | days | 35 | 2358.66 | 82553.1
| Foreman |  | 1 | days | 10 | 1200 | 12000 | 1 | days | 10 | 1500 | 15000 |  | days |  |  | 0 |  | days |  |  | 0
| Fabricators/Fitter |  | 4 | days | 10 | 1100 | 44000 | 2 | days | 10 | 1250 | 25000 | 4 | days | 10 | 1200 | 48000 | 2 | days | 35 | 3125.46 | 218782.2
| Welders |  | 4 | days | 10 | 1000 | 40000 | 4 | days | 10 | 1187.5 | 47500 | 4 | days | 10 | 1200 | 48000 | 4 | days | 35 | 2896.92 | 405568.8
| Skilled Helpers/cladder |  | 4 | days | 10 | 900 | 36000 | 5 | days | 10 | 1062.5 | 53125 | 4 | days | 10 | 800 | 32000 | 6 | days | 35 | 2871.528 | 603020.88
| Fire watcher |  | 1 | days | 10 | 900 | 9000 | [5 empty] | 1 | days | 10 | 1000 | 10000 | 1 | days | 35 | 2492.976 | 87254.16
| Sub-Total |  | 17 |  |  |  | 189000 | 15 |  |  |  | 186875 | 16 |  |  |  | 188000 | 16 |  |  |  | 1618538.88
H. | LABOR COSTING FOR INSTALLATION (with overtime)
| Project Engineer |  | 1 | days | 12 | 1600 | 19200 | 1 | days | 21 | 3046.88 | 63984.48 | 1 | days | 20 | 2500 | 50000 | 1 | days | 35 | 3681.876 | 128865.66
| Quality Officer |  | 1 | days | 12 | 1200 | 14400 | 1 | days | 21 | 2234.38 | 46921.98 | 1 | days | 20 | 1300 | 26000 | 1 | days | 35 | 2642.688 | 92494.08
| Safety Officer |  | 1 | days | 12 | 1000 | 12000 | 1 | days | 21 | 2234.38 | 46921.98 | 1 | days | 20 | 1000 | 20000 | 1 | days | 35 | 2358.66 | 82553.1
| Foreman |  | 1 | days | 12 | 1500 | 18000 | 1 | days | 21 | 2437.5 | 51187.5 | 1 | days | 20 | 1500 | 30000 | 1 | days | 35 | 3250 | 113750
| Fabricators/Fitter |  | 4 | days | 12 | 1200 | 57600 | 2 | days | 21 | 2031.25 | 85312.5 | 4 | days | 20 | 1200 | 96000 | 2 | days | 35 | 3125.46 | 202784.4
| Welders |  | 4 | days | 12 | 1100 | 52800 | 4 | days | 21 | 1929.69 | 162093.96 | 4 | days | 20 | 1200 | 96000 | 4 | days | 35 | 2896.92 | 402013.92
| Skilled Helpers/cladder |  | 4 | days | 12 | 800 | 38400 | 5 | days | 21 | 1726.56 | 181288.8 | 4 | days | 20 | 800 | 64000 | 4 | days | 35 | 2871.528 | 349016.64
| Fire watcher |  | 1 | days | 12 | 1000 | 12000 | 0 | days |  |  | 0 | 1 | days | 20 | 1000 | 20000 | 1 | days | 35 | 2492.976 | 87254.16
| Electrician |  | 1 | days | 12 | 1100 | 13200 | 1 | days | 21 | 1828.12 | 38390.52 | 1 | days | 20 | 1100 | 22000 |  | days |  |  | 0
| Scaffold inspector |  | 1 | days | 12 | 800 | 9600 |  | days | 0 |  | 0 | 1 | days | 20 | 800 | 16000 | 1 | days | 35 | 2800 | 98000
| Autocadd operator |  | 1 | days | 1 | 5000 | 5000 |  | days | 0 |  | 0 | 1 | days | 1 | 10000 |  | 1 | days | 10 | 2900 | 29000
| Sub-Total |  | 20 |  |  |  | 252200 | 16 |  |  |  | 676101.72 | 20 |  |  |  | 440000 | 17 |  |  |  | 1585731.96
I. | COMMISSIONING TEAM (3days)
| Project Engineer |  |  | days |  |  | 0 | 1 | days | 4 | 1875 | 7500 |  | days |  |  | 0 |  | days |  |  | 0
| Safety Officer |  | 2 | days | 3 | 1000 | 6000 | 1 | days | 4 | 1375 | 5500 | 1 | days | 3 | 1000 | 3000 | 1 | days | 7 | 2358.66 | 16510.62
| Fabricators/ Fitter |  |  | days |  |  | 0 | 1 | days | 4 | 1250 | 5000 |  | days |  |  | 0 |  | days |  |  | 0
| Welders |  | 2 | days | 3 | 1000 | 6000 | 1 | days | 4 | 1187.5 | 4750 | 4 | days | 3 | 1200 | 14400 | 1 | days | 7 | 2896.92 | 20278.44
| Skilled Helpers/cladder |  | 2 | days | 3 | 800 | 4800 | 2 | days | 4 | 1062.5 | 8500 | 4 | days | 3 | 800 | 9600 | 1 | days | 7 | 2492.976 | 17450.832
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
| Sub-Total |  | 6 |  |  |  | 16800 | 6 |  |  |  | 31250 | 9 |  |  |  | 27000 | 3 |  |  |  | 54239.892
K. | CARI
| 0.3% of Total Project Cost | [5 empty] | 10360.35 |  |  |  |  | 31323.1447 |  |  |  |  | 16503.54 |  |  |  |  | 13719.8857
L. | Administrative | [5 empty] | 172672.5 |  |  |  |  | 522052.411 |  |  |  |  | 275059 |  |  |  |  | 228664.762
Summary:
| General Requirements | [5 empty] | 425200 |  |  |  |  | 966897.5 |  |  |  |  | 751700 |  |  |  |  | 784700
| Material cost | [5 empty] | 2613250 |  |  |  |  | 8579924 |  |  |  |  | 4137480 |  |  |  |  | 584324.4
| Labor cost | [5 empty] | 415000 |  |  |  |  | 894226.72 |  |  |  |  | 612000 |  |  |  |  | 3204270.84
| Mark-up / profit | [5 empty] | 518017.5 |  |  |  |  | 522052.411 |  |  |  |  | 825177 |  |  |  |  | 685994.286
| GRAND TOTAL COST (VAT Exclusive) | [5 empty] | 4154500.35 |  |  |  |  | 11516476.1867 |  |  |  |  | 6617919.54 |  |  |  |  | 5501674.1737
| COMPLETION |  | 20 working days |  |  |  |  | 31 working days |  |  |  |  | 30 working days |  |  |  |  | 30 working days
| GRAND TOTAL |  |  |  |  | Php | 4154500.35 |  |  |  | Php | 11516476.1867 |  |  |  | Php | 6617919.54 |  |  |  | Php | 5501674.1737
Prepared by:
WELLERT G. EGUIA
Project Engineer
Noted by:
MARK ANTHONY P. PANA
Project Head

## fina (hidden)
F O R M S
BID BREAKDOWN DATA SHEET
PROJECT TITLE:
SUPPLY OF MATERIALS, LABOR, CONSUMABLES, TOOLS TECHNICAL SUPERVISION, AND TESTING FOR THE PROPOSED INSTALLATION OF GREEN COFFEE TRANSPORT LINE
COST CENTER:
|  |  | RHAJTEK |  |  |  |  | BP INDUSTRIAL
ITEM NO. | DESCRIPTION |  | Man'r | Unit | Qty | UNIT COST | AMOUNT | Man'r | Unit | Qty | UNIT COST | AMOUNT
A. | GENERAL REQUIREMENTS
1 | Mobilization/Temfacil/Housing, Personnel travel, etc. |  |  | lot |  |  | 350000 |  | lot | 1 | 10560 | 10560
| Demobilization |  |  | lot |  |  | 190000 |  | lot | 1 | 10560 | 10560
2 | Safety Provisions
| a. Comfort grip gloves |  |  | pairs | 455 | 62.5 | 28437.5 |  | pairs | 20 | 200 | 4000
| b. Dust Mask N95 |  |  | bxs | 56 | 187 | 10472 |  | bxs | 30 | 400 | 12000
| c. Caution Tape |  |  | roll | 2 | 1500 | 3000 |  | roll | 1 | 1300 | 1300
| d. Safety Signages |  |  | lot | 1 | 12500 | 12500 |  | lot | 1 | 3000 | 3000
| e. Fire Blanket (Size: 2m x 2m, temperatures up to 500°C Maximum) |  |  | pcs | 4 | 1250 | 5000 |  | pcs | 3 | 2500 | 7500
| f. Welding blanket Size: 2m x 2m, Minimum Type Rating = Heavy Duty = 1200 - 1500°C) |  |  | pcs | 4 | 1250 | 5000 |  | pcs | 3 | 1500 | 4500
| g. hygiene uniform (2 upper x 1 lower) per personnel |  |  | lot | 1 |  | 0 |  | pairs | 57 | 500 | 28500
| h. Safety shoes |  |  | pairs | 16 | 1562 | 24992 |  | pairs | 20 | 2000 | 40000
| i. Safety harness |  |  | pcs | 6 | 3125 | 18750 |  | pcs | 10 | 2000 | 20000
| j. Safety vest |  |  | pcs | 16 | 250 | 4000 |  | pcs | 20 | 300 | 6000
| k. Welding gloves |  |  | pairs | 8 | 562 | 4496 |  | pairs | 8 | 300 | 2400
| l. Welding mask |  |  | pcs | 4 | 500 | 2000 |  | pcs | 8 | 1500 | 12000
| m. Safety ear plugs |  |  | pcs | 16 | 150 | 2400 |  | pcs | 40 | 100 | 4000
| m. Safety googles |  |  | pcs | 16 | 200 | 3200 |  | pcs | 20 | 300 | 6000
3 | Tools & Equipment Rentals
| GTAW or Tig welding machine |  |  | unit | 4 | 5625 | 22500 |  | unit | 3 | 3000 | 9000
| Portable Grinders 7"Ø with double insulation standard |  |  | unit | 2 | 3125 | 6250 |  | unit | 3 | 2000 | 6000
| Portable Grinders 4"Ø with double insulation standard |  |  | unit | 4 | 2500 | 10000 |  | unit | 3 | 2000 | 6000
| Portable hand drill with double insulation standard |  |  | unit | 2 | 1875 | 3750 |  | unit | 3 | 2000 | 6000
| portable jack hammer |  |  | unit | 1 | 2500 | 2500 |  | unit | 3 | 2000 | 6000
| Extension wire |  |  | rolls | 6 | 1500 | 9000 |  | unit | 5 | 1500 | 7500
| Hand Tools (Complete set of combination wrenches) metric and english standard with torque wrench (4 sets in two groups) |  |  | lot | 2 | 1900 | 3800 |  | lot | 1 | 1500 | 1500
| Welding Panel (both for 440 and 220 volts supply ) w/ meter |  |  | unit | 1 | 6200 | 6200 |  | unit | 2 | 2000 | 4000
| Chain Block, shackles, Lifting belt, lifting lugs, rope & etc. with certificate |  |  | lot | 2 | 3700 | 7400 |  | lot | 1 | 20000 | 20000
| Structural analysis for lifting lugs & erected scaffoldings |  |  | lot | 1 | 150000 | 150000 |  | lot | 1 | 20000 | 20000
| Scaffolding with blind caps |  |  | lot | 1 | 250000 | 250000 |  | lot | 1 | 80000 | 80000
| Enclosure (scaffolding and tarp) |  |  | lot | 1 | 85000 | 85000 |  | lot | 1 | 100000 | 100000
| Lighting |  |  | lot | 1 |  | 0 |  | lot | 1 | 10000 | 10000
| Exhaust fan with duct and filter box |  |  | units | 2 | 2500 | 5000 |  | lot | 1 | 90000 | 90000
| Concrete works (demolition & repair) |  |  | lot | 1 |  | 0 |  | lot |  |  | 0
| Methodology of the project |  |  | lot | 1 |  | 0 |  | lot | 1 | 15000 | 15000
| As built drawing |  |  | lot | 1 |  | 0 |  | lot | 1 | 5000 | 5000
| Sub-Total | [5 empty] | 1218247.5 |  |  |  |  | 558320
B. | Design, Supply & Install of Pulse Jet Dust Collector with Specification Below |  |  | lot | 1 | 3500000 | 3500000
Capacity: 10,000 CFM (Base on the openingof the enclosure w/out plastic curtain)
Filtering Area: 1,648 ft2
Air to Cloth Area: 6 ft/min
No. of filter bags: 100 pcs
Type of Cleaning System : Pulse on Demand (POD)
| Size & Type of Filter Bags: 160mm dia x 3000mm L with Snap band, anti static polyester | [5 empty] | 0 |  |  |  |  | 0
| Explosion Vent type: Membrane Type - ATEX Certified or Brixxon Safety Latches | [5 empty] | 0 |  |  |  |  | 0
Dust discharger: Rotar valve drivenby a 1 hp Generator
| No. of Collecting Drums: 2 pcs of collecting drums with roller | [5 empty] | 0
| Sub-Total | [5 empty] | 3500000 |  |  |  |  | 0
B.1 | Installation of Rooms
| I beam 6x6 | [5 empty] | 0
SS plate 3mm
| Channel bar 6x2x6mm | [5 empty] | 0
| Top coat paint | [5 empty] | 0
Primer paint
| Cup sanding | [5 empty] | 0
| Angle bar2x2x6mm | [5 empty] | 0
PVC Curtain
| Stranded wire # 14 | [5 empty] | 0
| Expansion bolt | [5 empty] | 0
Steel Plate
| Oxy/Acy | [5 empty] | 0 |  |  |  |  | 0
0
Sub-Total
C. | Design, Supply & Install of Air base Stainless Duct SystemComplete Individual Dumper, Suction Hood & Necessary Support Bracket, Discharge of Clean Air to Outside the Building |  |  | lot | 1 | 1800000 | 1800000
Material of Construction shall be SS304 Spiral Duct Type for Straight Duct & Elbow Gage 16 for Transition- For Suction Ducts
Material of Construction shall be GI Plate Spiral Duct Type for Straight Duct & Elbow Gage 14 for Manifold- For Discharge Duct only meaning from Dust Collector to Discharge of Blower to be painted with Aluminum Silver
| Sub-Total | [5 empty] | 1800000 |  | unit | 1 | 1716338 | 1716338
C.1 | Installation of Dust Collector Unit | [7 empty] | box | 4 | 65000 | 260000
| Donaldson UMA 253 Dust Collector | [7 empty] | lot | 1 | 80000 | 80000
| Stranded wire # 14mm | [10 empty] | 2056338
Electrical tubing
Sub-Total
D. | Design, Supply & Install of Centrifugal Fan complete with 40HP motor |  |  | lot | 1 | 950000 | 950000
NYB Centrifugal Fan radial wheel (S20), Powder Coat Finish, Size 364 with DH wheel
Statically & dynamically balance, heavy duty scroll housing, arrangement 9. Complete with
Service Handhole, drain plug, common base, inlet & outlet flange, rubber type vibration
| isolators, pillow block bearings, shaft flexible coupling, shaft bearing guard, coupling guard | [5 empty] | 0 |  |  |  |  | 0
| direct coupled to 40hp motor, 3 phase 220/440 Vac, 60hz, TEFC Electric Motor. | [5 empty] | 0
| Sub-Total | [5 empty] | 950000 |  | lot | 1 | 195840 | 195840
D.1 | Installation of Ducting and hood | [7 empty] | lot | 1 | 28840 | 28840
| Fabricated stainless ducting | [7 empty] | lot | 1 | 165000 | 165000
| Stainless elbow 12" | [7 empty] | lot | 1 | 30000 | 30000
| Fabricated stainless hood | [7 empty] | length | 3 | 23931 | 71793
491473
E. | Design, Supply & Install of Electric Motor Controllers |  |  | lot | 1 | 650000 | 650000
Components of Motor Controllers:
Stainless Panel Board, size: 700mm x 600mm x 300mm
MCCB 125A, 3 Phase Schneider, Soft Starte Alti Start 22, Schneider brand
| Motor Circuit Breaker GV3- L50, Schneider brand | [5 empty] | 0
| Motor Circuit Breaker GV2- L07, Schneider Brand | [5 empty] | 0
| Control Transformer, 1 phase, 440/ 220 VAC, Yokohama | [5 empty] | 0
| Omron Relay 8 pin with base MY4N | [5 empty] | 0
Miniature Circuit breakers 3 & 6 A, 2 poles Schneider
Autel EcoSerial S12, Made in Italy for Purging System
Conduit Pipes & Fittings
| Consumables | [5 empty] | 0
| Sub-Total | [5 empty] | 650000 |  |  |  |  | 0
F. | CONSUMABLES FOR DOC. NO. 04,05,07,09,12,25 & 27
1 | Cutting Discs, 7"Ø, "Tyrolit" brand, 8,600 rated rpm |  |  | pcs | 50 | 181 | 9050 |  | pcs | 50 | 450 | 22500
2 | Cutting Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm |  |  | pcs | 200 | 56 | 11200 |  | pcs | 200 | 300 | 60000
3 | Grinding Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm |  |  | pcs | 15 | 56 | 840 |  | pcs | 100 | 150 | 15000
4 | Tungsten Rod |  |  | pcs | 16 | 125 | 2000 |  | pcs | 100 | 80 | 8000
5 | SS304 Filler Rod |  |  | kgs | 15 | 1500 | 22500 |  | kgs | 30 | 700 | 21000
6 | Tig cleene |  |  | jar | 4 | 812 | 3248 |  | jar | 20 | 2920 | 58400
7 | 6011 welding rod |  |  | kgs | 40 | 162 | 6480 |  | kgs | 100 | 450 | 45000
7 | 7018 welding rod |  |  | kgs | 20 | 200 | 4000 |  | kgs | 100 | 450 | 45000
8 | Argon Gas |  |  | cyl | 30 | 4625 | 138750 |  | cyl | 10 | 2100 | 21000
9 | Sand Paper, # 120 |  |  | pcs | 30 | 12 | 360 |  | pcs | 90 | 50 | 4500
10 | Flap Wheel, 4"Ø |  |  | pcs | 8 | 187 | 1496 |  | pcs | 50 | 300 | 15000
11 | drill bit/ carbide |  |  | lot | 0 |  | 0 |  | lot | 1 | 10000 | 10000
12 | Miscelleneous |  |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 20000 | 20000
13
| Sub-Total | [5 empty] | 229924 |  |  |  |  | 345400
G. | LABOR COSTING FOR FABRICATION
| Project Engineer |  | 1 | days | 10 | 1875 | 18750 | 1 | days | 5 | 2500 | 12500
| Quality Officer |  | 1 | days | 10 | 1375 | 13750 | 1 | days | 5 | 1500 | 7500
| Safety Officer |  | 1 | days | 10 | 1375 | 13750 | 1 | days | 5 | 1000 | 5000
| Foreman |  | 1 | days | 10 | 1500 | 15000 |  | days |  |  | 0
| Fabricators/Fitter |  | 2 | days | 10 | 1250 | 25000 | 4 | days | 5 | 1200 | 24000
| Welders |  | 4 | days | 10 | 1187.5 | 47500 | 4 | days | 5 | 1200 | 24000
| Skilled Helpers/cladder |  | 5 | days | 10 | 1062.5 | 53125 | 4 | days | 5 | 800 | 16000
| Fire watcher | [6 empty] | 1 | days | 5 | 1000 | 5000
| Sub-Total |  | 15 |  |  |  | 186875 | 16 |  |  |  | 94000
H. | LABOR COSTING FOR INSTALLATION (with overtime)
| Project Engineer |  | 1 | days | 21 | 3046.88 | 63984.48 | 1 | days | 7 | 2500 | 17500
| Quality Officer |  | 1 | days | 21 | 2234.38 | 46921.98 | 1 | days | 7 | 1300 | 9100
| Safety Officer |  | 1 | days | 21 | 2234.38 | 46921.98 | 1 | days | 7 | 1000 | 7000
| Foreman |  | 1 | days | 21 | 2437.5 | 51187.5 | 1 | days | 7 | 1500 | 10500
| Fabricators/Fitter |  | 2 | days | 21 | 2031.25 | 85312.5 | 4 | days | 7 | 1200 | 33600
| Welders |  | 4 | days | 21 | 1929.69 | 162093.96 | 4 | days | 7 | 1200 | 33600
| Skilled Helpers/cladder |  | 5 | days | 21 | 1726.56 | 181288.8 | 4 | days | 7 | 800 | 22400
| Fire watcher |  | 0 | days |  |  | 0 | 1 | days | 7 | 1000 | 7000
| Electrician |  | 1 | days | 21 | 1828.12 | 38390.52 |  | days |  |  | 0
| Scaffold inspector |  |  | days | 0 |  | 0 | 1 | days | 7 | 1100 | 7700
| Autocadd operator |  |  | days | 0 |  | 0 | 1 | days | 1 | 10000
| Sub-Total |  | 16 |  |  |  | 676101.72 | 19 |  |  |  | 148400
I. | COMMISSIONING TEAM (3days)
| Project Engineer |  | 1 | days | 4 | 1875 | 7500 |  | days |  |  | 0
| Safety Officer |  | 1 | days | 4 | 1375 | 5500 | 1 | days | 3 | 1000 | 3000
| Fabricators/ Fitter |  | 1 | days | 4 | 1250 | 5000 |  | days |  |  | 0
| Welders |  | 1 | days | 4 | 1187.5 | 4750 | 4 | days | 3 | 1200 | 14400
| Skilled Helpers/cladder |  | 2 | days | 4 | 1062.5 | 8500 | 4 | days | 3 | 800 | 9600
[7 empty] | 0 |  |  |  |  | 0
| Sub-Total |  | 6 |  |  |  | 31250 | 9 |  |  |  | 27000
K. | CARI
| 0.3% of Total Project Cost | [5 empty] | 20000.0003 |  |  |  |  | 11081.793
L. | Administrative | [5 empty] | 480000.0002 |  |  |  |  | 184696.55
Summary:
| General Requirements | [5 empty] | 1218247.5 |  |  |  |  | 558320
| Material cost | [5 empty] | 7100000 |  |  |  |  | 2893211
| Labor cost | [5 empty] | 1124150.72 |  |  |  |  | 242400
| Mark-up / profit | [5 empty] | 499999.9987 |  |  |  |  | 554089.65
| GRAND TOTAL COST (VAT Exclusive) | [5 empty] | 9942398.2192 |  |  |  |  | 4443798.993
| COMPLETION |  | 31 working days |  |  |  |  | 30 working days
| GRAND TOTAL |  |  |  |  | Php | 9942398.2192 |  |  |  | Php | 4443798.993
0.0021181
Prepared by: | [6 empty] | 0.0050835
0.052953
WELLERT G. EGUIA
Project Engineer
Noted by:
MARK ANTHONY P. PANA
Project Head

## final
F O R M S
BID BREAKDOWN DATA SHEET
PROJECT TITLE: |  |  |  |  | Date: | 2024-01-13
SUPPLY OF MATERIALS, LABOR, CONSUMABLES, TOOLS TECHNICAL SUPERVISION, AND TESTING FOR THE PROPOSED INSTALLATION OF GREEN COFFEE TRANSPORT LINE
COST CENTER: |  |  |  |  | Reference:
|  |  | IN HOUSE |  |  |  |  | RHAJTEK |  |  |  |  | BP INDUSTRIAL
ITEM NO. | DESCRIPTION |  | Man'r | Unit | Qty | UNIT COST | AMOUNT | Man'r | Unit | Qty | UNIT COST | AMOUNT | Man'r | Unit | Qty | UNIT COST | AMOUNT
A. | GENERAL REQUIREMENTS
1 | Mobilization/Temfacil/Housing, Personnel travel, etc. |  |  | lot | 1 | 30000 | 30000 |  | lot | 1 |  | 350000 |  | lot | 1 | 10560 | 10560
| Demobilization |  |  | lot | 1 | 20000 | 20000 |  | lot | 1 |  | 190000 |  | lot | 1 | 10560 | 10560
2 | Safety Provisions
| a. Comfort grip gloves |  |  | pairs | 300 | 50 | 15000 |  | pairs | 300 | 62.5 | 18750 |  | pairs | 300 | 200 | 60000
| b. Dust Mask N95 |  |  | bxs | 30 | 150 | 4500 |  | bxs | 30 | 187 | 5610 |  | bxs | 30 | 400 | 12000
| c. Caution Tape |  |  | roll | 1 | 1500 | 1500 |  | roll | 1 | 1500 | 1500 |  | roll | 1 | 1300 | 1300
| d. Safety Signages |  |  | lot | 1 | 2000 | 2000 |  | lot | 1 | 12500 | 12500 |  | lot | 1 | 3000 | 3000
| e. Fire Blanket (Size: 2m x 2m, temperatures up to 500°C Maximum) |  |  | pcs | 3 | 1500 | 4500 |  | pcs | 3 | 1250 | 3750 |  | pcs | 3 | 2500 | 7500
| f. Welding blanket Size: 2m x 2m, Minimum Type Rating = Heavy Duty = 1200 - 1500°C) |  |  | pcs | 3 | 1500 | 4500 |  | pcs | 3 | 1250 | 3750 |  | pcs | 3 | 1500 | 4500
| g. hygiene uniform (2 upper x 1 lower) per personnel |  |  | pairs | 36 | 1300 | 46800 |  | pairs | 32 | 2295 | 73440 |  | pairs | 36 | 1500 | 54000
| h. Safety shoes |  |  | pairs | 19 | 2000 | 38000 |  | pairs | 16 | 1562 | 24992 |  | pairs | 19 | 2000 | 38000
| i. Safety harness |  |  | pcs | 5 | 2000 | 10000 |  | pcs | 6 | 3125 | 18750 |  | pcs | 5 | 2000 | 10000
| j. Safety vest |  |  | pcs | 19 | 300 | 5700 |  | pcs | 5 | 250 | 1250 |  | pcs | 19 | 300 | 5700
| k. Welding gloves |  |  | pairs | 8 | 300 | 2400 |  | pairs | 8 | 562 | 4496 |  | pairs | 8 | 300 | 2400
| l. Welding mask |  |  | pcs | 8 | 800 | 6400 |  | pcs | 4 | 500 | 2000 |  | pcs | 8 | 1500 | 12000
| m. Safety ear plugs |  |  | pcs | 20 | 100 | 2000 |  | pcs | 16 | 150 | 2400 |  | pcs | 40 | 100 | 4000
| m. Safety googles |  |  | pcs | 20 | 300 | 6000 |  | pcs | 16 | 200 | 3200 |  | pcs | 20 | 300 | 6000
3 | Tools & Equipment Rentals
| GTAW or Tig welding machine |  |  | unit | 2 | 2000 | 4000 |  | unit | 3 | 5625 | 16875 |  | unit | 2 | 3000 | 6000
| Portable Grinders 7"Ø with double insulation standard |  |  | unit | 1 | 2500 | 2500 |  | unit | 3 | 3125 | 9375 |  | unit | 1 | 2000 | 2000
| Portable Grinders 4"Ø with double insulation standard |  |  | unit | 2 | 1500 | 3000 |  | unit | 4 | 2500 | 10000 |  | unit | 2 | 2000 | 4000
| Portable hand drill with double insulation standard |  |  | unit | 3 | 2000 | 6000 |  | unit | 3 | 1875 | 5625 |  | unit | 3 | 2000 | 6000
| portable jack hammer |  |  | unit | 2 | 2000 | 4000 |  | unit | 2 | 2500 | 5000 |  | unit | 2 | 2000 | 4000
| Extension wire |  |  | unit | 5 | 1500 | 7500 |  | rolls | 5 | 1500 | 7500 |  | unit | 5 | 1500 | 7500
| Hand Tools (Complete set of combination wrenches) metric and english standard with torque wrench (4 sets in two groups) |  |  | lot | 1 | 2000 | 2000 |  | lot | 1 | 1900 | 1900 |  | lot | 1 | 1500 | 1500
| Welding Panel (both for 440 and 220 volts supply ) w/ meter |  |  | unit | 1 | 2000 | 2000 |  | unit | 1 | 6200 | 6200 |  | unit | 1 | 2000 | 2000
| Chain Block, shackles, Lifting belt, lifting lugs, rope & etc. with certificate |  |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 4050 | 4050 |  | lot | 1 | 20000 | 20000
| Structural analysis for lifting lugs & erected scaffoldings |  |  | lot | 1 | 50000 | 50000 |  | lot | 1 | 150000 | 150000 |  | lot | 1 | 20000 | 20000
| Scaffolding with blind caps |  |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 195000 | 195000 |  | lot | 1 | 55000 | 55000
| Enclosure (scaffolding and tarp) |  |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 45000 | 45000 |  | lot | 1 | 75000 | 75000
| Lighting |  |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 2160 | 2160 |  | lot | 1 | 10000 | 10000
| Exhaust fan with duct and filter box |  |  | lot |  | 30000 | 0 |  | units |  | 2500 | 0 |  | lot |  | 90000 | 0
| Concrete works (demolition & repair) |  |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 18000 | 18000 |  | lot | 1 | 30000 | 30000
| Methodology of the project |  |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 15000 | 15000
| As built drawing |  |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 5000 | 5000
| Project Board 4x8 |  |  | pc | 1 | 3000 | 3000 | [6 empty] | pc | 1 | 5000 | 5000
| Sub-Total | [5 empty] | 388300 |  |  |  |  | 1195823 |  |  |  |  | 509520
B. | Design, Supply & Install of Pulse Jet Dust Collector with Specification Below | [7 empty] | lot | 1 | 3500000 | 3500000
Capacity: 10,000 CFM (Base on the openingof the enclosure w/out plastic curtain)
Filtering Area: 1,648 ft2
Air to Cloth Area: 6 ft/min
No. of filter bags: 100 pcs
Type of Cleaning System : Pulse on Demand (POD)
| Size & Type of Filter Bags: 160mm dia x 3000mm L with Snap band, anti static polyester | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
| Explosion Vent type: Membrane Type - ATEX Certified or Brixxon Safety Latches | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
Dust discharger: Rotar valve drivenby a 1 hp Generator
| No. of Collecting Drums: 2 pcs of collecting drums with roller | [10 empty] | 0
| Sub-Total | [5 empty] | 0 |  |  |  |  | 3500000 |  |  |  |  | 0
C. | Design, Supply & Install of Air base Stainless Duct SystemComplete Individual Dumper, Suction Hood & Necessary Support Bracket, Discharge of Clean Air to Outside the Building | [7 empty] | lot | 1 | 1200000 | 1200000
Material of Construction shall be MS for Straight Duct & Elbow Gage 16 for Transition- For Suction Ducts
| Sub-Total | [10 empty] | 1200000
C.1 | Installation of Dust Collector Unit
| Donaldson UMA 253 Dust Collector |  |  | unit | 1 | 1650000 | 1650000 | [6 empty] | unit | 1 | 1716338 | 1716338
| Stranded wire # 14mm |  |  | box |  | 58000 | 0 | [6 empty] | box |  | 65000 | 0
| Electrical tubing |  |  | lot |  | 70000 | 0 | [6 empty] | lot |  | 80000 | 0
| Sub-Total | [5 empty] | 1650000 | [9 empty] | 1716338
D. | Design, Supply & Install of Centrifugal Fan complete with 40HP motor | [7 empty] | lot | 1 | 650000 | 650000
NYB Centrifugal Fan radial wheel (S20), Powder Coat Finish, Size 364 with DH wheel
Statically & dynamically balance, heavy duty scroll housing, arrangement 9. Complete with
Service Handhole, drain plug, common base, inlet & outlet flange, rubber type vibration
| isolators, pillow block bearings, shaft flexible coupling, shaft bearing guard, coupling guard | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
| direct coupled to 40hp motor, 3 phase 220/440 Vac, 60hz, TEFC Electric Motor. | [10 empty] | 0
| Sub-Total | [10 empty] | 650000
D.1 | Installation of Ducting and hood
| MS plate fabricated ducting |  |  | lot | 1 | 100000 | 100000 | [6 empty] | lot | 1 | 132840 | 132840
| Mild steel elbow 12" |  |  | lot | 1 | 20000 | 20000 | [6 empty] | lot | 1 | 18225 | 18225
| MS plate fabricated suction hood |  |  | lot | 1 | 80000 | 80000 | [6 empty] | lot | 1 | 118050 | 118050
| MS plate 6mm for flange |  |  | lot | 1 | 10000 | 170000 | [6 empty] | lot | 1 | 24500 | 24500
| PVC curtain |  |  | lot | 1 | 50000 | 50000 | [6 empty] | lot | 1 | 144000 | 144000
| I beam 6x6 |  |  | length | 3 | 20000 | 60000 | [6 empty] | length | 3 | 23931 | 71793
[7 empty] | 480000 | [9 empty] | 509408
E. | Design, Supply & Install of Electric Motor Controllers | [7 empty] | lot |  | 850000 | 0
Components of Motor Controllers:
Stainless Panel Board, size: 700mm x 600mm x 300mm
MCCB 125A, 3 Phase Schneider, Soft Starte Alti Start 22, Schneider brand
| Motor Circuit Breaker GV3- L50, Schneider brand | [10 empty] | 0
| Motor Circuit Breaker GV2- L07, Schneider Brand | [10 empty] | 0
| Control Transformer, 1 phase, 440/ 220 VAC, Yokohama | [10 empty] | 0
| Omron Relay 8 pin with base MY4N | [10 empty] | 0
Miniature Circuit breakers 3 & 6 A, 2 poles Schneider
Autel EcoSerial S12, Made in Italy for Purging System
Conduit Pipes & Fittings
| Consumables | [10 empty] | 0
| Sub-Total | [5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
F. | CONSUMABLES FOR DOC. NO. 04,05,07,09,12,25 & 27
1 | Cutting Discs, 7"Ø, "Tyrolit" brand, 8,600 rated rpm |  |  | pcs | 20 | 180 | 3600 |  | pcs | 20 | 181 | 3620 |  | pcs | 20 | 450 | 9000
2 | Cutting Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm |  |  | pcs | 25 | 100 | 2500 |  | pcs | 25 | 56 | 1400 |  | pcs | 25 | 300 | 7500
3 | Grinding Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm |  |  | pcs | 20 | 150 | 3000 |  | pcs | 20 | 56 | 1120 |  | pcs | 20 | 150 | 3000
4 | Tungsten Rod |  |  | pcs | 20 | 80 | 1600 |  | pcs | 20 | 125 | 2500 |  | pcs | 30 | 80 | 2400
5 | SS304 Filler Rod |  |  | kgs | 15 | 700 | 10500 |  | kgs | 15 | 1500 | 22500 |  | kgs | 30 | 700 | 21000
6 | Tig cleene |  |  | jar | 20 | 1000 | 20000 |  | jar | 5 | 812 | 4060 |  | jar | 20 | 2920 | 58400
7 | 6011 welding rod |  |  | kgs | 40 | 200 | 8000 |  | kgs | 50 | 162 | 8100 |  | kgs | 40 | 450 | 18000
7 | 7018 welding rod |  |  | kgs | 20 | 230 | 4600 |  | kgs | 30 | 200 | 6000 |  | kgs | 20 | 450 | 9000
8 | Argon Gas |  |  | cyl | 10 | 2100 | 21000 |  | cyl | 12 | 4625 | 55500 |  | cyl | 10 | 2100 | 21000
9 | Sand Paper, # 120 |  |  | pcs | 50 | 50 | 2500 |  | pcs | 50 | 12 | 600 |  | pcs | 50 | 50 | 2500
10 | Flap Wheel, 4"Ø |  |  | pcs | 20 | 300 | 6000 |  | pcs | 10 | 187 | 1870 |  | pcs | 20 | 300 | 6000
11 | drill bit/ carbide |  |  | lot | 1 | 3000 | 3000 |  | lot | 1 | 4500 | 4500 |  | lot | 1 | 10000 | 10000
12 | Miscelleneous |  |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 20000 | 20000
13 | Primer paint | [12 empty] | gal | 3 | 1500 | 4500
14 | Top coat paint | [12 empty] | gal | 3 | 1500 | 4500
15
| Sub-Total | [5 empty] | 106300 |  |  |  |  | 141770 |  |  |  |  | 196800
G. | LABOR COSTING FOR FABRICATION
| Project Engineer |  | 1 | days | 5 | 1600 | 8000 | 1 | days | 10 | 1875 | 18750 | 1 | days | 5 | 3500 | 17500
| Quality Officer |  |  | days | 5 | 1200 | 0 | 1 | days | 10 | 1375 | 13750 |  | days |  | 1500 | 0
| Safety Officer |  | 1 | days | 5 | 1000 | 5000 | 1 | days | 10 | 1375 | 13750 | 1 | days | 5 | 1000 | 5000
| Foreman |  | 1 | days | 5 | 1300 | 6500 | 1 | days | 10 | 1500 | 15000 |  | days |  |  | 0
| Fabricators/Fitter |  | 4 | days | 5 | 1200 | 24000 | 2 | days | 10 | 1250 | 25000 | 2 | days | 5 | 1200 | 12000
| Welders |  | 4 | days | 5 | 1200 | 24000 | 4 | days | 10 | 1187.5 | 47500 | 2 | days | 5 | 1200 | 12000
| Skilled Helpers/cladder |  | 4 | days | 5 | 800 | 16000 | 5 | days | 10 | 1062.5 | 53125 | 4 | days | 5 | 800 | 16000
| Fire watcher |  | 1 | days | 5 | 1000 | 5000 | [5 empty] | 1 | days | 5 | 1000 | 5000
| Sub-Total |  | 16 |  |  |  | 88500 | 15 |  |  |  | 186875 | 11 |  |  |  | 67500
H. | LABOR COSTING FOR INSTALLATION (with overtime)
| Project Engineer |  | 1 | days | 7 | 1600 | 11200 | 1 | days | 18 | 3046.88 | 54843.84 | 1 | days | 7 | 3500 | 24500
| Quality Officer |  |  | days | 7 | 1300 | 0 |  | days | 18 | 2234.38 | 0 |  | days |  | 1300 | 0
| Safety Officer |  | 1 | days | 7 | 1200 | 8400 | 1 | days | 18 | 2234.38 | 40218.84 | 1 | days | 7 | 1000 | 7000
| Foreman |  | 1 | days | 7 | 1500 | 10500 | 1 | days | 18 | 2437.5 | 43875 | 1 | days | 7 | 1500 | 10500
| Fabricators/Fitter |  | 2 | days | 7 | 1300 | 18200 | 2 | days | 18 | 2031.25 | 73125 | 2 | days | 7 | 1200 | 16800
| Welders |  | 2 | days | 7 | 1200 | 16800 | 2 | days | 18 | 1929.69 | 69468.84 | 2 | days | 7 | 1200 | 16800
| Skilled Helpers/cladder |  | 4 | days | 7 | 1000 | 28000 | 5 | days | 18 | 1726.56 | 155390.4 | 4 | days | 7 | 800 | 22400
| Fire watcher |  | 1 | days | 7 | 800 | 5600 | 0 | days | 18 |  | 0 | 1 | days | 7 | 1000 | 7000
| Electrician |  | 1 | days | 7 | 800 | 5600 | 1 | days | 18 | 1828.12 | 32906.16 |  | days |  |  | 0
| Scaffold inspector |  | 1 | days | 7 | 1000 | 7000 | 1 | days | 18 | 1828.12 | 32906.16 | 1 | days | 7 | 1100 | 7700
| Autocadd operator |  | 1 | days | 1 | 5000 | 5000 | 1 | days | 1 | 1828.12 | 1828.12 | 1 | days | 1 | 10000
| Sub-Total |  | 15 |  |  |  | 116300 | 15 |  |  |  | 504562.36 | 14 |  |  |  | 112700
I. | COMMISSIONING TEAM (3days)
| Project Engineer |  |  | days |  |  | 0 |  | days |  |  | 0 |  | days |  |  | 0
| Safety Officer |  | 2 | days | 3 | 1200 | 7200 | 2 | days | 3 | 2234.38 | 13406.28 | 2 | days | 3 | 1000 | 6000
| Fabricators/ Fitter |  |  | days |  |  | 0 |  | days |  |  | 0 |  | days |  |  | 0
| Welders |  | 2 | days | 3 | 1200 | 7200 | 2 | days | 3 | 1929.69 | 11578.14 | 2 | days | 3 | 1200 | 7200
| Skilled Helpers/cladder |  | 2 | days | 3 | 800 | 4800 | 2 | days | 3 | 1726.56 | 10359.36 | 2 | days | 3 | 800 | 4800
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
| Sub-Total |  | 6 |  |  |  | 19200 | 6 |  |  |  | 35343.78 | 6 |  |  |  | 18000
K. | CARI
| 0.3% of Total Project Cost | [5 empty] | 8491.8 |  |  |  |  | 22232.2624 |  |  |  |  | 9336.798
L. | Administrative | [5 empty] | 141530 |  |  |  |  | 370537.707 |  |  |  |  | 155613.3
Summary:
| General Requirements | [5 empty] | 388300 |  |  |  |  | 1195823 |  |  |  |  | 509520
| Material cost | [5 empty] | 2236300 |  |  |  |  | 5488150 |  |  |  |  | 2422546
| Labor cost | [5 empty] | 206000 |  |  |  |  | 726781.14 |  |  |  |  | 180200
| Mark-up / profit | [5 empty] | 424590 |  |  |  |  | 325000.0309 |  |  |  |  | 466839.9
| GRAND TOTAL COST (VAT Exclusive) | [5 empty] | 3405211.8 |  |  |  |  | 8128524.1403 |  |  |  |  | 3744055.998
| COMPLETION |  | 12 working days |  |  |  |  | 28 working days |  |  |  |  | 12 working days
| GRAND TOTAL |  |  |  |  | Php | 3405211.8 |  |  |  | Php | 8128524.1403 |  |  |  | Php | 3744055.998
0.0036866
Prepared by: |  | Noted by: | [9 empty] | 0.061443
0.043855
WELLERT G. EGUIA |  | MARK ANTHONY P. PANA
Project Engineer |  | Project Head

## finals (hidden)
F O R M S
BID BREAKDOWN DATA SHEET
PROJECT TITLE: |  |  |  |  | Date: | 2023-07-24
SUPPLY OF MATERIALS, LABOR, CONSUMABLES, TOOLS TECHNICAL SUPERVISION, AND TESTING FOR THE PROPOSED INSTALLATION OF GREEN COFFEE TRANSPORT LINE
COST CENTER: |  |  |  |  | Reference:
IN - HOUSE
ITEM NO. | DESCRIPTION |  | Man'r | Unit | Qty | UNIT COST | AMOUNT | Man'r | Unit | Qty | UNIT COST | AMOUNT | Man'r | Unit | Qty | UNIT COST | AMOUNT
A. | GENERAL REQUIREMENTS
1 | Mobilization/Temfacil/Housing, Personnel travel, etc. |  |  | lot | 1 | 50000 | 50000 |  | lot |  |  | 305000 |  | lot | 1 | 396400 | 396400
| Demobilization |  |  | lot | 1 | 30000 | 30000 |  | lot |  |  | 189100 |  | lot | 1 | 471646.66 | 471646.66
2 | Safety Provisions
| a. Comfort grip gloves |  |  | pairs | 1245 | 25 | 31125 |  | pairs | 1245 | 61 | 75945 |  | pairs | 1000 | 50 | 50000
| b. Dust Mask N95 |  |  | bxs | 147 | 187.5 | 27562.5 |  | bxs | 147 | 183 | 26901 |  | bxs | 100 | 850 | 85000
| c. Caution Tape |  |  | roll | 2 | 1500 | 3000 |  | roll | 2 | 1464 | 2928 |  | roll | 2 | 2000 | 4000
| d. Safety Signages |  |  | lot | 1 | 4000 | 4000 |  | lot | 1 | 12200 | 12200 |  | lot | 2 | 10000 | 20000
| e. Fire Blanket (Size: 2m x 2m, temperatures up to 500°C Maximum) |  |  | pcs | 8 | 5000 | 40000 |  | pcs | 8 | 1220 | 9760 |  | pcs | 4 | 4500 | 18000
| f. Welding blanket Size: 2m x 2m, Minimum Type Rating = Heavy Duty = 1200 - 1500°C) |  |  | pcs | 8 | 4000 | 32000 |  | pcs | 8 | 1220 | 9760 |  | pcs | 4 | 4500 | 18000
| g. hygiene uniform (2 upper x 1 lower) per personnel |  |  | pairs | 42 | 1500 | 63000 |  | sets | 42 | 1037 | 43554 |  | pairs | 44 | 850 | 37400
| h. Safety vest |  |  | pcs | 21 | 500 | 10500 |  | pcs | 21 | 244 | 5124 |  | pcs | 22 | 210 | 4620
| i. Welding gloves |  |  | pairs | 8 | 600 | 4800 |  | pairs | 8 | 549 | 4392 |  | pairs | 8 | 750 | 6000
| j. Welding mask |  |  | pcs | 8 | 500 | 4000 |  | pcs | 8 | 488 | 3904 |  | pcs | 4 | 450 | 1800
| k. Safety googles |  |  | pcs | 21 | 300 | 6300 |  | pcs | 21 | 219.6 | 4611.6 |  | pcs | 44 | 150 | 6600
| l. Safety harness |  |  | pcs | 12 | 300 | 3600 |  | pcs | 12 | 3050 | 36600 |  | pcs | 12 | 2745 | 32940
| m. Safety shoes |  |  | pairs | 21 | 1500 | 31500 |  | pairs | 21 | 1525 | 32025 |  | pairs | 22 | 995 | 21890
3 | Tools & Equipment Rentals
| GTAW or Tig welding machine |  |  | unit | 4 | 5500 | 22000 |  | unit | 4 | 5490 | 21960 |  | unit | 4 | 2000 | 8000
| Portable Grinders 7"Ø with double insulation standard |  |  | unit | 4 | 5000 | 20000 |  | unit | 4 | 3050 | 12200 |  | unit | 4 | 300 | 1200
| Portable Grinders 4"Ø with double insulation standard |  |  | unit | 4 | 3000 | 12000 |  | unit | 4 | 2440 | 9760 |  | unit | 8 | 225 | 1800
| Portable hand drill with double insulation standard |  |  | unit | 1 | 4000 | 4000 |  | unit | 1 | 1830 | 1830 |  | unit | 1 | 225 | 225
| portable jack hammer |  |  | unit | 1 | 5000 | 5000 |  | unit | 1 | 2440 | 2440 |  | unit | 1 | 325 | 325
| Extension wire |  |  | unit | 8 | 1500 | 12000 |  | rolls | 8 | 1464 | 11712 |  | unit | 8 | 800 | 6400
| Hand Tools (Complete set of combination wrenches) metric and english standard with torque wrench (4 sets in two groups) |  |  | lot | 4 | 5000 | 20000 |  | sets | 4 | 1464 | 5856 |  | sets | 3 | 300 | 900
| Welding Panel (both for 440 and 220 volts supply ) w/ meter |  |  | unit | 2 | 6000 | 12000 |  | unit | 2 | 6100 | 12200 |  | unit | 2 | 1000 | 2000
| Chain Block, shackles, Lifting belt, lifting lugs, rope & etc. with certificate |  |  | lot | 2 | 10000 | 20000 |  | unit | 2 | 3660 | 7320 |  | lot | 2 | 325 | 650
| Structural analysis for lifting lugs & erected scaffoldings |  |  | lot | 1 | 100000 | 100000 |  | lot | 1 | 24400 | 24400 |  | lot | 1 | 6500 | 6500
| Scaffolding with blind caps |  |  | lot | 1 | 30000 | 30000 |  | lot | 1 | 95160 | 95160 |  | lot | 30 | 1300 | 39000
| Enclosure (scaffolding and tarp) |  |  | lot | 1 | 4000 | 4000 |  | lot | 1 | 21960 | 21960 |  | lot | 1 | 12500 | 12500
| Lighting |  |  | lot | 4 | 1500 | 6000 |  | pcs | 4 | 549 | 2196 |  | lot | 4 | 2500 | 10000
| Exhaust fan with duct and filter box |  |  | lot | 2 | 3500 | 7000 |  | units | 2 | 1464 | 2928 |  | lot | 2 | 2100 | 4200
| Concrete works (demolition & repair) |  |  | lot | 1 | 20000 | 20000 |  | lot | 1 | 12200 | 12200 |  | lot | 1 | 35000 | 35000
| Methodology of the project |  |  | lot | 1 | 4000 | 4000 |  | lot | 1 | 6100 | 6100 |  | lot | 1 | 15000 | 15000
| As built drawing |  |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 18300 | 18300 |  | lot | 1 | 15000 | 15000
| crane rental (2 days) |  |  | lot | 1 | 500000 | 500000 |  | lot | 1 | 183000 | 183000 |  | lot | 1 | 450000 | 450000
| Sub-Total | [5 empty] | 1149387.5 |  |  |  |  | 1213326.6 |  |  |  |  | 1782996.66
B. | Installation of Green Coffee Air - Line
1 | air-line piping w/ butterfly valves(NPI yo supply) | [10 empty] | 0
2 | pipe supports (3" x 6mm thk angle bars) for air-line pipes |  |  | Lt | 2 | 4500 | 9000 |  | Lt | 2 | 2623 | 5246 |  | Lt | 10 | 9625 | 96250
3 | chemical bolt (M12 x 160) for concrete walling supports |  |  | pcs | 20 | 300 | 6000 |  | pcs | 20 | 549 | 10980 |  | pcs | 60 | 337.5 | 20250
4 | final painting |  |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 7320 | 7320 |  | lot | 1 | 10000 | 10000
5 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
6 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
7 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
8
| Sub-Total | [5 empty] | 30000 |  |  |  |  | 23546 |  |  |  |  | 126500
C. | Installation of Green Coffee Transport - Line
1 | GC product line & long elbows (NPI to supply)
2 | pipe supports (3" x 6mm thk angle bars) for transport -line pipes |  |  | Lt | 10 | 4500 | 45000 |  | Lt | 10 | 2623 | 26230 |  | Lt | 10 | 9625 | 96250
3 | chemical bolt (M12 x 160) for concrete walling supports |  |  | pcs | 20 | 300 | 6000 |  | pcs | 20 | 549 | 10980 |  | pcs | 300 | 337.5 | 101250
4 | Brackets for diverter @ rebagging area (3" x 6mm thk angle bars) |  |  | Lt | 2 | 4500 | 9000 |  | le | 2 | 2623 | 5246 |  | Lt | 2 | 9625 | 19250
5 | Platform w/ access ladder & roofing for diverter @ roasting (4"x2" C-channel, 1.5" ms pipe railings, 2" flat bar man guard, ms checkered plate 2mm thk ) |  |  | set | 1 | 30000 | 30000 |  | set | 1 | 30500 | 30500 |  | set | 1 | 102560 | 102560
6 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
7 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
8 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
9 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
10 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
| Sub-Total | [5 empty] | 90000 |  |  |  |  | 72956 |  |  |  |  | 319310
D. | Installation of Recieving Chamber
1 | 3units receiving chamber (NPI to supply)
2 | final painting |  |  | lot | 1 | 50000 | 50000 |  | lot | 1 | 73200 | 73200 |  | lot | 1 | 25000 | 25000
3 | crane rental (2 days) |  |  | lot |  |  | 0 |  | lot |  |  | 0 |  |  |  |  | 0
4 | [11 empty] | 0
5 | [11 empty] | 0
6 | [6 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
| Sub-Total | [5 empty] | 50000 |  |  |  |  | 73200 |  |  |  |  | 25000
E. | CONSUMABLES FOR DOC. NO. 04,05,07,09,12,25 & 27
1 | Cutting Discs, 7"Ø, "Tyrolit" brand, 8,600 rated rpm |  |  | pcs | 60 | 280 | 16800 |  | pcs | 60 | 176.9 | 10614 |  | pcs | 70 | 172.5 | 12075
2 | Cutting Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm |  |  | pcs | 200 | 150 | 30000 |  | pcs | 200 | 54.9 | 10980 |  | pcs | 200 | 116.55 | 23310
3 | Grinding Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm |  |  | pcs | 20 | 150 | 3000 |  | pcs | 20 | 54.9 | 1098 |  | pcs | 20 | 122.85 | 2457
4 | Tungsten Rod |  |  | pcs | 20 | 180 | 3600 |  | pcs | 20 | 122 | 2440 |  | pcs | 20 | 117.6 | 2352
5 | BI Filler Rod |  |  | kgs | 15 | 1200 | 18000 |  | kgs | 15 | 122 | 1830 |  | kgs | 20 | 882 | 17640
6 | Tig cleene |  |  | jar | 2 | 750 | 1500 |  | jar | 2 | 793 | 1586 |  | jar | 4 | 2400 | 9600
7 | 6011 welding rod |  |  | kgs | 40 | 150 | 6000 |  | kgs | 40 | 158.6 | 6344 |  | kgs | 80 | 165 | 13200
7 | 7018 welding rod |  |  | kgs | 40 | 150 | 6000 |  | kgs | 40 | 195.2 | 7808 |  | kgs | 40 | 165 | 6600
8 | Argon Gas |  |  | cyl | 25 | 3500 | 87500 |  | cyl | 25 | 4514 | 112850 |  | cyl | 20 | 2800 | 56000
9 | Sand Paper, # 120 |  |  | pcs | 50 | 16 | 800 |  | pcs | 50 | 12.2 | 610 |  | pcs | 50 | 16 | 800
10 | Flap Wheel, 4"Ø |  |  | pcs | 20 | 455 | 9100 |  | pcs | 20 | 183 | 3660 |  | pcs | 20 | 80 | 1600
11 | Drill bit/ carbide |  |  | lot | 1 | 2500 | 2500 |  | pcs | 6 | 427 | 2562 |  | lot | 6 | 500 | 3000
12 | Miscelleneous |  |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 36600 | 36600 |  | lot | 1 | 17836.08 | 17836.08
13
14
15
16
| Sub-Total | [5 empty] | 194800 |  |  |  |  | 198982 |  |  |  |  | 166470.08
F. | LABOR COSTING FOR FABRICATION
| Project Engineer |  | 1 | days | 15 | 1000 | 15000 | 1 | days | 15 | 1830 | 27450 | 1 | days | 15 | 2100 | 31500
| Quality Officer |  | 1 | days | 15 | 900 | 13500 | 1 | days | 15 | 1464 | 21960 | 1 | days | 15 | 1600 | 24000
| Safety Officer |  | 1 | days | 15 | 900 | 13500 | 1 | days | 15 | 1464 | 21960 | 1 | days | 15 | 1600 | 24000
| Fabricators/Fitter |  | 4 | days | 15 | 750 | 45000 | 2 | days | 15 | 1220 | 36600 | 2 | days | 15 | 1689.68 | 50690.4
| Welders |  | 6 | days | 15 | 700 | 63000 | 4 | days | 15 | 1159 | 69540 | 2 | days | 15 | 1677.25 | 50317.5
| Skilled Helpers/cladder |  | 10 | days | 15 | 1150 | 172500 | 4 | days | 15 | 1037 | 62220 | 4 | days | 15 | 1485 | 89100
| Fire watcher |  | 3 | days | 15 | 750 | 33750 | 1 | days | 15 | 976 | 14640 | 1 | days | 15 | 1391.44 | 20871.6
| Sub-Total |  | 26 |  |  |  | 356250 | 14 |  |  |  | 254370 | 12 |  |  |  | 290479.42
G. | LABOR COSTING FOR INSTALLATION (with overtime)
| Project Engineer |  | 1 | days | 25 | 1750 | 43750 | 1 | days | 30 | 2973.75 | 89212.5 | 1 | days | 25 | 3525.03 | 88125.75
| Quality Officer |  | 1 | days | 25 | 1575 | 39375 | 1 | days | 30 | 2379 | 71370 | 1 | days | 25 | 2592.21 | 64805.25
| Safety Officer |  | 2 | days | 25 | 1575 | 78750 | 1 | days | 30 | 2379 | 71370 | 1 | days | 25 | 2592.21 | 64805.25
| Foreman |  | 3 | days | 25 | 1490 | 111750 | 1 | days | 30 | 1982.5 | 59475 | 1 | days | 25 | 3025.51 | 75637.75
| Fabricators/Fitter |  | 4 | days | 25 | 1350 | 135000 | 3 | days | 30 | 1982.5 | 178425 | 4 | days | 25 | 2820.45 | 282045
| Welders |  | 6 | days | 25 | 1350 | 202500 | 6 | days | 30 | 1883.38 | 339008.4 | 4 | days | 25 | 2797.54 | 279754
| Skilled Helpers/cladder |  | 10 | days | 25 | 1150 | 287500 | 10 | days | 30 | 1220 | 366000 | 7 | days | 25 | 2457.81 | 430116.75
| Fire watcher |  | 3 | days | 25 | 1000 | 75000 | 1 | days | 30 | 1586 | 47580 | 1 | days | 25 | 2297.87 | 57446.75
| Scaffold inspector |  | 1 | days | 25 | 1000 | 25000 | 5 | days | 30 | 1784.25 | 267637.5 | 1 | days | 25 | 2600 | 65000
| Autocadd operator |  | 1 | days | 5 | 1575 | 7875 | 1 | days | 7 | 1586 | 11102 | 1 | days | 25 | 2600 | 65000
| Sub-Total |  | 32 |  |  |  | 1006500 | 30 |  |  |  | 1501179.5 | 22 |  |  |  | 1472735.75
H. | COMMISSIONING PHASE 1A
| Project Engineer |  | 1 | days | 3 | 1750 | 5250 | 1 | days | 3 | 1830 | 5490 | 1 | days | 3 | 2100 | 6300
| Safety Officer |  | 2 | days | 3 | 1575 | 9450 | 1 | days | 3 | 1464 | 4392 | 1 | days | 3 | 1600 | 4800
| Welders |  | 2 | days | 3 | 1350 | 8100 | 1 | days | 3 | 1159 | 3477 | 2 | days | 3 | 1677.25 | 10063.5
| Skilled Helpers/cladder |  | 2 | days | 3 | 1150 | 6900 | 3 | days | 3 | 1037 | 9333 | 4 | days | 3 | 1485 | 17820
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
| Sub-Total |  | 7 |  |  |  | 29700 | 6 |  |  |  | 22692 | 8 |  |  |  | 38983.5
I. | COMMISSIONING PHASE 1B
| Project Engineer |  | 1 | days | 2 | 1750 | 3500 | 1 | days | 3 | 1830 | 5490 | 1 | days | 2 | 2100 | 4200
| Safety Officer |  | 2 | days | 2 | 1575 | 6300 | 1 | days | 3 | 1464 | 4392 | 1 | days | 2 | 1700 | 3400
| Welders |  | 2 | days | 2 | 1350 | 5400 | 1 | days | 3 | 1159 | 3477 | 2 | days | 2 | 1677.25 | 6709
| Skilled Helpers/cladder |  | 2 | days | 2 | 1150 | 4600 | 3 | days | 3 | 1037 | 9333 | 4 | days | 2 | 1619.58 | 12956.64
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0
| Sub-Total |  | 7 |  |  |  | 19800 | 6 |  |  |  | 22692 | 8 |  |  |  | 27265.64
J. | CARI
| 0.3% of Total Project Cost | [5 empty] | 8779.3125 |  |  |  |  | 10148.8323 |  |  |  |  | 12266.9757
K. | Administrative | [5 empty] | 146321.875 |  |  |  |  | 169147.205 |  |  |  |  | 204449.5945
Summary:
| General Requirements | [5 empty] | 1149387.5 |  |  |  |  | 1213326.6 |  |  |  |  | 1782996.66
| Material cost | [5 empty] | 364800 |  |  |  |  | 368684 |  |  |  |  | 542780.08
| Labor cost | [5 empty] | 1412250 |  |  |  |  | 1800933.5 |  |  |  |  | 1763215.15
| Mark-up / profit | [5 empty] | 438965.625 |  |  |  |  | 338294.41 |  |  |  |  | 613348.7835
| GRAND TOTAL COST (VAT Exclusive) | [5 empty] | 3520504.3125 |  |  |  |  | 3900534.5473 |  |  |  |  | 4919057.2437
| COMPLETION |  | 45 working days |  |  |  |  | 51 working days |  |  |  |  | 45 working days
| GRAND TOTAL |  |  |  |  | Php | 3520504.3125 |  |  |  | Php | 3900534.5473 |  |  |  | Php | 4919057.2437
Prepared by:
WELLERT G. EGUIA | [10 empty] | 7.5173
Project Engineer
Noted by:
MARK ANTHONY P. PANA
Project Head

## Reconciled Qty with Contr's amt (hidden)
PROJECT |  | : | Installation of AHU Dehumidifier and Fabrication and Installation of Pipe Lines for Steam and Condensate and Chilled Water Supply and Return and Relocation of Coffee Transport Pipe
SUBJECT |  | : | Reconciled Contractor's Bid
DATE |  | : | October 13, 2015
PR Number |  | : | 735238129
Doc. Control |  | : |  | USING AGREED QUANTITY BUT VENDOR'S UNIT COST
ITEM NO. | DESCRIPTION |  |  | Man'r | Unit | Qty | UNIT COST | AMOUNT
Prepared by:
Oscar M. Sta. Maria, Jr.
|  | TBMC |  |  | - Reconciled quantity
Noted by:
Arnel C. Lopez |  |  | Merachell Escobido
Project Engineer / NPI |  |  | Strategic Buyer / NPI
Confirmed by: ________________________
O & J