## Original Bid
abcdef Good Food, Good Life |  |  |  |  | F O R M S |  |  |  | FORM CODE
BID BREAKDOWN DATA SHEET
PROJECT TITLE: |  |  |  | Proposed FFE RARE ROTARY FILTER |  |  |  |  | Date: | 2023-07-25 16:32
SUBJECT:
COST CENTER: | [8 empty] | Reference: | [8 empty] | Original In-House + Original Contractor’s Bids (All)
[7 empty] | IN HOUSE |  |  |  |  | ACE PACKAGING CO. |  |  |  |  | OMNI CREST ENG'G |  |  |  |  | RHAJTIK
No. |  | SCOPE OF WORKS |  |  |  |  | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT
A. |  | GENERAL REQUIREMENTS
1 |  | Mobilization(Temfacil) | [5 empty] | lot | 1 | 25000 | 25000 |  | lot | 1 | 246000 | 246000 |  | lot | 1 | 525000 | 525000 |  | lot | 1 | 339250 | 339250
2 |  | Demobilization/Housekeeping | [5 empty] | lot | 1 | 35000 | 35000 |  | lot | 1 | 164000 | 164000 |  | lot | 1 | 525000 | 525000 |  | lot | 1 | 172500 | 172500
3 |  | Safety Provisions
4 |  | a. Cotton Gloves | [5 empty] | pairs | 710 | 27 | 19170 |  | pairs | 710 | 50 | 35500 |  | pairs | 200 | 224 | 44800 |  | pairs | 600 | 17.25 | 10350
5 |  | b. Welding Mask | [5 empty] | pcs | 7 | 550 | 3850 |  | pcs | 7 | 450 | 3150 |  | pcs | 6 | 560 | 3360 |  | pcs | 7 | 571.5 | 4000.5
6 |  | c. Welding Gloves | [5 empty] | pairs | 7 | 250 | 1750 |  | pairs | 7 | 750 | 5250 |  | pcs | 6 | 504 | 3024 |  | pairs | 7 | 402.5 | 2817.5
7 |  | d. Welding Apron | [5 empty] | pcs | 7 | 350 | 2450 |  | pcs | 7 | 500 | 3500 |  | pcs | 6 | 504 | 3024 |  | pcs | 7 | 862.5 | 6037.5
8 |  | e. Googles | [5 empty] | pcs | 30 | 250 | 7500 |  | pcs | 30 | 120 | 3600 |  | pcs | 27 | 280 | 7560 |  | pcs | 30 | 207 | 6210
9 |  | f. Dust Mask - N95 | [5 empty] | bxs | 650 | 350 | 227500 |  | bxs | 650 | 65 | 42250 |  | bxs | 3 | 168 | 504 |  | bxs | 650 | 172.5 | 112125
10 |  | g. Caution Tape | [5 empty] | roll | 2 | 1384 | 2768 |  | roll | 2 | 2000 | 4000 |  | roll | 2 | 896 | 1792 |  | roll | 2 | 1380 | 2760
11 |  | h. Rags | [5 empty] | kgs | 10 | 92 | 920 |  | kgs | 10 | 100 | 1000 |  | kgs | 10 | 224 | 2240 |  | kgs | 10 | 97.75 | 977.5
12 |  | i. Safety Signages | [5 empty] | lot | 1 | 5000 | 5000 |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 4480 | 4480 |  | lot | 1 | 10925 | 10925
13 |  | j. Welding blankets | [5 empty] | roll | 6 | 2000 | 12000 |  | roll | 6 | 4500 | 27000 |  | pcs | 6 | 1680 | 10080 |  | roll | 6 | 1265 | 7590
14 |  | k. Fire Blanket | [5 empty] | roll | 6 | 1200 | 7200 |  | roll | 6 | 4500 | 27000 |  | pcs | 6 | 1680 | 10080 |  | roll | 6 | 1265 | 7590
Tools & Equipment Rentals
15 |  | Tig welding machines | [5 empty] | unit | 6 | 7000 | 42000 |  | unit | 6 | 8000 | 48000 |  | unit | 6 | 15800 | 94800 |  | unit | 6 | 5175 | 31050
16 |  | Portable Grinders 4" and 7"dia. | [5 empty] | unit | 8 | 3500 | 28000 |  | unit | 8 | 4500 | 36000 |  | unit | 8 | 26500 | 212000 |  | unit | 8 | 2875 | 23000
17 |  | Portable Drills | [5 empty] | unit | 4 | 2500 | 10000 |  | unit | 4 | 4500 | 18000 |  | unit | 4 | 7200 | 28800 |  | unit | 4 | 1725 | 6900
18 |  | A-Ladder | [5 empty] | lot | 2 | 3000 | 6000 |  | lot | 2 | 16850 | 33700 |  | lot | 2 | 5000 | 10000 |  | lot | 2 | 1725 | 3450
19 |  | As built drawings | [5 empty] | lot | 1 | 10000 | 10000 |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 15000 | 15000 |  | lot | 1 |  | 13800
20 |  | Hand tools | [5 empty] | lot | 2 | 1000 | 2000 |  | lot | 2 | 3000 | 6000 |  | lot | 2 | 5000 | 10000 |  | lot | 2 |  | 5060
21 |  |  | Chain Block with certificate |  |  |  |  | lot | 2 | 5000 | 10000 |  | lot | 2 | 6500 | 13000 |  | lot | 2 | 20160 | 40320 |  | lot | 2 |  | 6900
22 |  | Construction Board 440V to 220V, 3phase | [5 empty] | set | 2 | 40000 | 80000 |  | set | 2 | 20000 | 40000 |  | set | 2 | 240000 | 480000 |  | set | 2 | 5750 | 11500
23 |  | Scaffolding | [20 empty] | Lot | 1 |  | 13800
|  | SUB-TOTAl | [8 empty] | 538108 |  |  |  |  | 781950 |  |  |  |  | 2031864 |  |  |  |  | 798593
B. |  | Improvement FFE RARE E-54
Product Line Supply and Return Coffee Liquor
1 |  | SS Pipe, 3"Ø, sch40, seamless x 6meters (suction/discharge) | [5 empty] | length | 10 | 24500 | 245000 |  | length | 10 | 21924 | 219240 |  | length | 10 | 63250 | 632500 |  | length | 10 | 24909 | 249090
2 |  | SS Pneumatic Valve , DN80, PN40 flanged type,raised face(suction /discharge) |  |  |  |  | NPI | unit | 4 | NPI |  |  | unit | 4 |  |  | NPI | unit | 4 | 4950 | 19800 | NPI | unit | 4
3 |  | SS Ball valve, 3 piece assembly, DN80,PN40, weld end |  |  |  |  | NPI | unit | 4 | NPI |  |  | unit | 4 |  |  | NPI | unit | 4 | 3960 | 15840 | NPI | unit | 4
4 |  | SS check valve, DN80,PN40 flanged type (product outlet) |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 3960 | 3960 | NPI | unit | 1
5 |  | SS Flanges, Slip on type DN80, PN40 with bolts and washers and nuts | [5 empty] | sets | 13 | 3644 | 47372 |  | sets | 13 | 16968 | 220584 |  | sets | 13 | 15400 | 200200 |  | sets | 13 | 9062 | 117806
6 |  | SS Elbow, 3"Ø, sch40, seamless x 90°, weld and(product) | [5 empty] | pcs | 8 | 780 | 6240 |  | pcs | 8 | 2520 | 20160 |  | pcs | 8 | 16656.2 | 133249.6 |  | pcs | 8 | 1610 | 12880
7 |  | SS Elbow, 2"Ø, sch40, seamless x 90°, weld and(product) | [5 empty] | pcs | 10 | 485 | 4850 |  | pcs | 10 | 1596 | 15960 |  | pcs | 10 | 1886.5 | 18865 |  | pcs | 10 | 598 | 5980
8 |  | SS Elbow, 2"Ø, sch40, seamless x 45°, weld end (product) | [5 empty] | pcs | 6 | 485 | 2910 |  | pcs | 6 | 1596 | 9576 |  | pcs | 6 | 1886.5 | 11319 |  | pcs | 6 | 598 | 3588
9 |  | SS Concentric Reducer, 3"Ø x 1 1/2"Ø, sch40, weld end, seamless | [5 empty] | pcs | 2 | 805 | 1610 |  | pcs | 2 | 3528 | 7056 |  | pcs | 2 | 1430 | 2860 |  | pcs | 2 | 1092.5 | 2185
10 |  | SS Concentric Reducer, 2 "Ø x 1 1/2"Ø, sch40, weld end type | [5 empty] | pcs | 2 | 706 | 1412 |  | pcs | 2 | 1911 | 3822 |  | pcs | 2 | 4202 | 8404 |  | pcs | 2 | 1006.25 | 2012.5
11 |  | SS Tee, 3"Ø, sch40, seamless, weld end | [5 empty] | pcs | 6 | 1350 | 8100 |  | pcs | 6 | 3449.25 | 20695.5 |  | pcs | 6 | 4697 | 28182 |  | pcs | 6 | 2535.75 | 15214.5
12 |  | SS Tee, 2"Ø, sch40, seamless, weld end | [5 empty] | pcs | 3 | 1200 | 3600 |  | pcs | 3 | 2194.5 | 6583.5 |  | pcs | 3 | 1848 | 5544 |  | pcs | 3 | 1253.5 | 3760.5
13 |  | SS RED Tee, 3" X 1 1/2"Ø, sch40, seamless, weld end | [5 empty] | pcs | 2 | 1000 | 2000 |  | pcs | 2 | 7612.5 | 15225 |  | pcs | 2 | 5720 | 11440 |  | pcs | 2 | 1437.5 | 2875
BURSTING DISC
14 |  | SS Pipe, 1 1/2"Ø, sch40, seamless x 20 ft (Pressure relief Pipe) | [5 empty] | pcs | 14 | 13650 | 191100 |  | pcs | 14 | 7875 | 110250 |  | pcs | 14 | 21450 | 300300 |  | pcs | 14 | 8682.5 | 121555
15 |  | Bursting disc DN80 PN40 |  |  |  |  | NPI | pcs | 1 |  |  |  | pcs | 1 |  |  | NPI | pcs | 1 | 3960 | 3960
Pressure Relief
16 |  | SS Pipe, 1 1/2"Ø, sch40, seamless x 20 ft (Pressure relief Pipe) | [5 empty] | lght | 14 | 13650 | 191100 |  | lght | 14 | 7875 | 110250 |  | lght | 14 | 21450 | 300300 |  | lght | 14 | 8682.5 | 121555
17 |  | Pressure Relief Valve DN40,15 bars |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 4950 | 4950 | NPI | unit | 1
18 |  | SS Flanges, DN40, 1 1/2" PN40 with bolts and washers and nuts | [5 empty] | sets | 12 | 815 | 9780 |  | sets | 12 | 9030 | 108360 |  | sets | 12 | 11000 | 132000 |  | sets | 12 | 5681 | 68172
19 |  | SS Elbow, 1 1/2"Ø, sch40, seamless x 90°, weld end type (product) | [5 empty] | pcs | 8 | 245 | 1960 |  | pcs | 8 | 1421.7 | 11373.6 |  | pcs | 8 | 1707.2 | 13657.6 |  | pcs | 8 | 414 | 3312
20 |  | SS Elbow, 1 1/2"Ø, sch40, seamless x 45°, welded end type (product) | [5 empty] | pcs | 12 | 245 | 2940 |  | pcs | 12 | 1421.7 | 17060.4 |  | pcs | 12 | 1707.2 | 20486.4 |  | pcs | 12 | 414 | 4968
21 |  | SS Tee, 1 1/2"Ø, sch40, seamless, welded type | [5 empty] | pcs | 2 | 335 | 670 |  | pcs | 2 | 2982 | 5964 |  | pcs | 2 | 1617 | 3234 |  | pcs | 2 | 966 | 1932
22 |  | SS Concentric Reducer, 3 "Ø x 1 1/2"Ø, sch40, weld end type, seamless | [5 empty] | pcs | 1 | 706 | 706 |  | pcs | 1 | 3465 | 3465 |  | pcs | 1 | 1683 | 1683 |  | pcs | 1 | 1092.5 | 1092.5
Drain Line - Coffee sludge
23 |  | SS Pipe, 2"Ø, sch40, seamless x 20 ft (Drain line) | [5 empty] | lght | 2 | 14888 | 29776 |  | lght | 2 | 9975 | 19950 |  | lght | 2 | 10340 | 20680 |  | lght | 2 | 12029 | 24058
24 |  | SS Pneumatic Valve , DN50, PN40 flanged type,raised face |  |  |  |  | NPI | unit | 2 | NPI |  |  | unit | 2 |  |  | NPI | unit | 2 | 4950 | 9900 | NPI | unit | 2
25 |  | Handle valve DN50 PN40 Locking plate |  |  |  |  | NPI | Sets | 1 |  |  |  | Sets | 1 |  |  | NPI | Sets | 1 | 3960 | 3960 | NPI | Sets | 1
26 |  | SS Flanges, DN50, PN40 with bolts and washers and nuts | [5 empty] | sets | 6 | 1100 | 6600 |  | sets | 6 | 10500 | 63000 |  | sets | 6 | 8800 | 52800 |  | sets | 6 | 7406 | 44436
27 |  | Sight Glass, DN50,PN10 |  |  |  |  | NPI | sets | 1 | NPI |  |  | sets | 1 |  |  | NPI | sets | 1 | 3960 | 3960 | NPI | sets | 1
28 |  | SS Elbow, 2"Ø, sch40, seamless x 90°, weld end | [5 empty] | pcs | 4 | 485 | 1940 |  | pcs | 4 | 1596 | 6384 |  | pcs | 4 | 572 | 2288 |  | pcs | 4 | 598 | 2392
29 |  | SS Elbow, 2"Ø, sch40, seamless x 45°, weld end | [5 empty] | lot | 1 | 485 | 485 |  | lot | 1 | 1596 | 1596 |  | lot | 1 | 572 | 572 |  | lot | 1 | 598 | 598
Hot Water Line
30 |  | SS Pipe, 1 1/2"Ø, sch40, seamless x 20 ft (hot water) - Steam Line | [5 empty] | lght | 14 | 13650 | 191100 |  | lght | 14 | 7875 | 110250 |  | lght | 14 | 7700 | 107800 |  | lght | 14 | 8682.5 | 121555
31 |  | SS Pneumatic Valve , DN40, PN40 flanged type,raised face |  |  |  |  | NPI | unit | 2 | NPI |  |  | unit | 2 |  |  | NPI | unit | 2 | 3960 | 7920 | NPI | unit | 2
32 |  | SS Ball valve, 3 piece assembly, 1 1/2"Ø, Weld End (hot water) |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 3960 | 3960 | NPI | unit | 1
33 |  | SS check valve, DN40,PN40 flanged type |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 3960 | 3960 | NPI | unit | 1
34 |  | SS Flanges, DN40, PN40 with bolts and washers and nuts | [5 empty] | sets | 6 | 815 | 4890 |  | sets | 6 | 9030 | 54180 |  | sets | 6 | 11000 | 66000 |  | sets | 6 | 6256 | 37536
35 |  | SS Tee, 3"Ø, sch40, seamless, weld end | [5 empty] | pcs | 1 | 1450 | 1450 |  | pcs | 1 | 3449.25 | 3449.25 |  | pcs | 1 | 4697 | 4697 |  | pcs | 1 | 2535.75 | 2535.75
36 |  | SS Concentric Reducer, 3"Ø x 1 1/2"Ø, sch40, weld end | [5 empty] | pcs | 1 | 1050 | 1050 |  | pcs | 1 | 3465 | 3465 |  | pcs | 1 | 2513.5 | 2513.5 |  | pcs | 1 | 1092.5 | 1092.5
37 |  | SS Elbow, 1 1/2"Ø, sch40, seamless x 90°, weld end (hot water) | [5 empty] | pcs | 10 | 245 | 2450 |  | pcs | 10 | 1423.8 | 14238 |  | pcs | 10 | 389.4 | 3894 |  | pcs | 10 | 414 | 4140
38 |  | SS Elbow, 1 1/2"Ø, sch40, seamless x 45°, weld end (hot water) | [5 empty] | pcs | 6 | 245 | 1470 |  | pcs | 6 | 1423.8 | 8542.8 |  | pcs | 6 | 389.4 | 2336.4 |  | pcs | 6 | 414 | 2484
39 |  | SS Tee, 1 1/2"Ø, sch40, seamless, weld end | [5 empty] | pcs | 1 | 650 | 650 |  | pcs | 1 | 2982 | 2982 |  | pcs | 1 | 924 | 924 |  | pcs | 1 | 966 | 966
40 |  | 1 1/2" x 2" thick insulation-calcium silicate ( 2ft pre moulded) | [5 empty] | pcs | 40 | 750 | 30000 |  | pcs | 40 | 408.45 | 16338 |  | pcs | 40 | 2400 | 96000 |  | pcs | 40 | 460 | 18400
41 |  | SS Cladding, 0.6mm thk, 4 ft x 8 ft | [5 empty] | sheet | 10 | 4500 | 45000 |  | sheet | 10 | 2483.25 | 24832.5 |  | sheet | 10 | 3840 | 38400 |  | sheet | 10 | 3220 | 32200
Instrument Air Line
42 |  | SS Pipe, 1/2"Ø, sch40, seamless x 20 ft (compressed air) | [5 empty] | lght | 5 | 1980 | 9900 |  | lght | 5 | 7875 | 39375 |  | lght | 5 | 3234 | 16170 |  | lght | 5 | 3266 | 16330
43 |  | SS Ball valve, 3 pc assembly, 1/2 "Ø, weld end (comp. air) |  |  |  |  | NPI | pcs | 2 | NPI |  |  | pcs | 2 |  |  | NPI | pcs | 2 | 2640 | 5280 | NPI | pcs | 2
44 |  | SS Elbow, 1/2"Ø, sch40, seamless x 90°, weld end (compressed air) | [5 empty] | pcs | 8 | 75 | 600 |  | pcs | 8 | 1421.7 | 11373.6 |  | pcs | 10 | 440 | 4400 |  | pcs | 8 | 161 | 1288
45 |  | Air Service unit air filter |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 2640 | 2640 | NPI | unit | 1
46 |  | SS Tee Reducer 1 " x 1/2" weld end , seamless | [5 empty] | pcs | 1 | 350 | 350 |  | pcs | 1 | 1352.4 | 1352.4 |  | pcs | 1 | 1012 | 1012 |  | pcs | 1 | 632.5 | 632.5
47 |  | Pneumatic Header, SS Pipe sch 20, with Fittings, Fabricated as per drawing | [5 empty] | lot | 1 | 2500 | 2500 |  | lot | 1 | 45000 | 45000 |  | lot | 1 | 49500 | 49500 |  | lot | 1 | 86250 | 86250
Support and Hanger
48 |  | SS Angle bar, 2" x 2" x 1/4" thk x 20 ft | [5 empty] | lght | 2 | 5500 | 11000 |  | lght | 2 | 6510 | 13020 |  | lght | 2 | 5940 | 11880 |  | lght | 2 | 6900 | 13800
49 |  | SS Channel bar, 4" x 5.4 lbs/ft x 10 ft (Self Cleaning Filter Support) | [5 empty] | lght | 3 | 34000 | 102000 |  | lght | 3 | 28350 | 85050 |  | lght | 3 | 42075 | 126225 |  | lght | 3 | 59800 | 179400
50 |  | SS U-bolts, M12 | [5 empty] | set | 20 | 85 | 1700 |  | set | 20 | 331.8 | 6636 |  | set | 20 | 433.4 | 8668 |  | set | 20 | 230 | 4600
51 |  | SS U-bolts, M10 | [5 empty] | set | 40 | 65 | 2600 |  | set | 40 | 161.7 | 6468 |  | set | 40 | 183.7 | 7348 |  | set | 40 | 189.75 | 7590
52 |  | SS U-bolts, M8 | [5 empty] | set | 36 | 42 | 1512 |  | set | 36 | 124.95 | 4498.2 |  | set | 36 | 59.4 | 2138.4 |  | set | 36 | 138 | 4968
53 |  | SS Square Tube 2"x2"x4mm thick 6meter length | [5 empty] | lght | 10 | 6703.4 | 67034 |  | lght | 10 | 12600 | 126000 |  | lght | 10 | 13227.5 | 132275 |  | lght | 10 | 8970 | 89700
54 |  | 4mm thick SS304 Flat bar 2ft. | [5 empty] | lght | 10 | 2500 | 25000 |  | lght | 10 | 2100 | 21000 |  | lght | 10 | 2750 | 27500 |  | lght | 10 | 2760 | 27600
55 |  | M8X40mm Hexabolt dome type hex head | [5 empty] | pcs | 100 | 30 | 3000 |  | pcs | 100 | 16.8 | 1680 |  | pcs | 100 | 220 | 22000 |  | pcs | 100 | 51.75 | 5175
56 |  | DN20 SCH. 40 SS304 | [5 empty] | lght | 4 | 1500 | 6000 |  | lght | 4 | 2992.5 | 11970 |  | lght | 4 | 2866.6 | 11466.4 |  | lght | 4 | 4025 | 16100
57 |  | SS Flat bar 4ft. | [5 empty] | lght | 4 | 1161.6 | 4646.4 |  | lght | 4 | 4500 | 18000 |  | lght | 4 | 9350 | 37400 |  | lght | 4 | 2760 | 11040
Fabricated Trolley
58 |  | Fabrication of SS Trolley,Fabricate as per drawing - 300 kgs capacity | [5 empty] | lot | 2 | 45000 | 90000 |  | lot | 2 | 18000 | 36000 |  | lot | 2 | 83185.3 | 166370.6 |  | lot | 2 | 86250 | 172500
|  | SUB-TOTAl | [8 empty] | 1366053.4 |  |  |  |  | 1662255.75 |  |  |  |  | 2937572.9 |  |  |  |  | 1667344.75
E. |  | CONSUMABLES
1 |  | Cutting Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm | [5 empty] | pcs | 65 | 100 | 6500 |  | pcs | 65 | 172.2 | 11193 |  | pcs | 200 | 71.5 | 14300 |  | pcs | 65 | 51.75 | 3363.75
2 |  | Cutting Discs, 7"Ø, "Tyrolit" brand, 8,600 rated rpm | [5 empty] | pcs | 65 | 150 | 9750 |  | pcs | 65 | 116.55 | 7575.75 |  | pcs | 70 | 137.5 | 9625 |  | pcs | 65 | 149.5 | 9717.5
3 |  | Grinding Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm | [5 empty] | pcs | 65 | 125 | 8125 |  | pcs | 65 | 122.85 | 7985.25 |  | pcs | 60 | 38.5 | 2310 |  | pcs | 65 | 51.75 | 3363.75
4 |  | Grinding Discs, 7"Ø, "Tyrolit" brand, 8,600 rated rpm | [5 empty] | pcs | 65 | 175 | 11375 |  | pcs | 65 | 219.45 | 14264.25 |  | pcs | 20 | 165 | 3300 |  | pcs | 65 | 149.5 | 9717.5
6 |  | Tungsten | [5 empty] | pcs | 18 | 100 | 1800 |  | pcs | 18 | 117.6 | 2116.8 |  | pcs | 10 | 220 | 2200 |  | pcs | 18 | 115 | 2070
7 |  | SS Filler Rod, 304 | [5 empty] | kgs | 18 | 950 | 17100 |  | kgs | 18 | 882 | 15876 |  | kgs | 70 | 990 | 69300 |  | kgs | 18 | 2472.5 | 44505
8 |  | Blind Revits | [15 empty] | box | 3 | 1320 | 3960
9 |  | Argon Gas | [5 empty] | cyl | 20 | 4135 | 82700 |  | cyl | 20 | 2940 | 58800 |  | cyl | 70 | 4950 | 346500 |  | cyl | 20 | 4255 | 85100
10 |  | Tig Cleene | [5 empty] | kgs | 2 | 1650 | 3300 |  | kgs | 2 | 2257.5 | 4515 |  | kgs | 2 | 440 | 880 |  | kgs | 2 | 747.5 | 1495
11 |  | Finishing Wheel/Grey | [5 empty] | pcs | 20 | 336 | 6720 |  | pcs | 20 | 892.5 | 17850 |  | pcs | 20 | 55 | 1100 |  | pcs | 20 | 2875 | 57500
12 |  | Oxygen | [5 empty] | cyl | 15 | 375 | 5625 |  | cyl | 15 | 682.5 | 10237.5 |  | cyl | 2 | 990 | 1980 |  | cyl | 15 | 517.5 | 7762.5
13 |  | Acetylene | [5 empty] | cyl | 10 | 1050 | 10500 |  | cyl | 10 | 1890 | 18900 |  | cyl | 1 | 1320 | 1320 |  | cyl | 10 | 1437.5 | 14375
14 |  | Painting Works | [5 empty] | Gal | 2 | 1050 | 2100 |  | Gal | 2 | 1800 | 3600 |  | Gal | 1 | 1650 | 1650 |  | Gal | 2 | 1380 | 2760
15 |  | Miscelleneous(painting/Tagging/Labeling and others) | [5 empty] | lot | 1 | 10000 | 10000 |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 72581.46 | 72581.46 |  | lot | 1 | 46000 | 46000
|  | SUB-TOTAl | [8 empty] | 175595 |  |  |  |  | 177913.55 |  |  |  |  | 531006.46 |  |  |  |  | 287730
F. |  | LABOR COSTING
[7 empty] | No. of Manpower | Days | No. of Days | Manpower Rate | Total Cost | No. of Manpower | Days | No. of Days | Manpower Rate | Total Cost | No. of Manpower | Days | No. of Days | Manpower Rate | Total Cost | No. of Manpower | Days | No. of Days | Manpower Rate | Total Cost
FABRICATION
1 |  | Foreman/Leadman |  |  |  |  | 1 | days | 15 | 850 | 12750 | 1 | days | 15 | 1562.7 | 23440.5 | 1 | days | 30 | 2220 | 66600 | 1 | days | 15 | 1509.38 | 22640.7
2 |  | Pipe Fitter |  |  |  |  | 3 | days | 15 | 650 | 29250 | 3 | days | 15 | 1455.78 | 65510.1 | 1 | days | 5 | 1980 | 9900 | 3 | days | 15 | 1509.38 | 67922.1
3 |  | Welders - Subject for actual testing |  |  |  |  | 2 | days | 15 | 800 | 24000 | 2 | days | 15 | 1443.72 | 43311.6 | 2 | days | 30 | 1980 | 118800 | 2 | days | 15 | 1433.91 | 43017.3
4 |  | Skilled Helpers |  |  |  |  | 4 | days | 15 | 650 | 39000 | 4 | days | 15 | 1247.37 | 74842.2 | [5 empty] | 4 | days | 15 | 1282.97 | 76978.2
|  | SUB-TOTAl |  |  |  |  | 10 |  |  |  | 105000 | 10 |  |  |  | 207104.4 |  |  |  |  | 195300 |  |  |  |  | 210558.3
INSTALLATION
1 |  | Project Engineer |  |  |  |  | 1 | days | 25 | 1000 | 25000 | 1 | days | 25 | 2586.26 | 64656.5 | [5 empty] | 1 | days | 25 | 2803.13 | 70078.25
2 |  | Quality Officer |  |  |  |  | 1 | days | 25 | 750 | 18750 | 1 | days | 25 | 2856.26 | 71406.5 | [5 empty] | 1 | days | 25 | 2242.5 | 56062.5
3 |  | Safety Officer |  |  |  |  | 1 | days | 25 | 750 | 18750 | 1 | days | 25 | 2023.47 | 50586.75 | [5 empty] | 1 | days | 25 | 2055.63 | 51390.75
4 |  | Foreman/leadman |  |  |  |  | 1 | days | 25 | 850 | 21250 | 1 | days | 25 | 2419.07 | 60476.75 | [5 empty] | 1 | days | 25 | 1868.75 | 46718.75
5 |  | Pipe Fitter |  |  |  |  | 4 | days | 25 | 650 | 65000 | 4 | days | 25 | 2237.63 | 223763 | [5 empty] | 4 | days | 25 | 1868.75 | 186875
6 |  | Welders-Qualified on NPI |  |  |  |  | 3 | days | 25 | 800 | 60000 | 3 | days | 25 | 2215.66 | 166174.5 | 2 | days | 30 | 2100 | 126000 | 3 | days | 25 | 1775.31 | 133148.25
7 |  | Skilled Helpers |  |  |  |  | 4 | days | 25 | 650 | 65000 | 4 | days | 25 | 1247.37 | 124737 | 4 | days | 30 | 1980 | 237600 | 4 | days | 25 | 1588.44 | 158844
8 |  | Tool keeper |  |  |  |  | 1 | days | 25 | 650 | 16250 | 1 | days | 25 | 1247.37 | 31184.25 | 6 | days | 30 | 1980 | 356400 | 1 | days | 25 | 1588.44 | 39711
9 |  | Scaffoldder |  |  |  |  | 2 | days | 25 | 800 | 40000 | 2 | days | 25 | 1984.22 | 99211 | 8 | days | 30 | 1920 | 460800 | 2 | days | 25 | 1588.44 | 79422
10 |  | Fire watcher |  |  |  |  | 1 | days | 25 | 650 | 16250 | 1 | days | 25 | 1984.22 | 49605.5 | 2 | days | 30 | 1920 | 115200 | 1 | days | 25 | 1588.44 | 39711
11 |  | Electrician |  |  |  |  | 1 | days | 25 | 800 | 20000 | 1 | days | 25 | 1797.52 | 44938 | 2 | days | 30 | 1920 | 115200 | 1 | days | 25 | 1681.88 | 42047
|  | Sub-Total |  |  |  |  | 20 |  | 25 |  | 366250 | 20 |  |  |  | 986739.75 |  |  |  |  | 1411200 |  |  |  |  | 904008.5
LABOR COSTING FOR COMMISSIONING (With overtime)
1 |  | Fitter |  |  |  |  | 2 | days | 4 | 650 | 5200 | 2 | days | 4 | 2237.63 | 17901.04 | [5 empty] | 2 | days | 4 | 1868.75 | 14950
2 |  | Welders |  |  |  |  | 2 | days | 4 | 800 | 6400 | 2 | days | 4 | 2215.66 | 17725.28 | [5 empty] | 2 | days | 4 | 1775.31 | 14202.48
3 |  | Safety Officer |  |  |  |  | 1 | days | 4 | 750 | 3000 | 1 | days | 4 | 2023.47 | 8093.88 | [5 empty] | 1 | days | 4 | 2055.63 | 8222.52
|  | Sub-Total |  |  |  |  | 5 |  | 12 |  | 14600 |  |  |  |  | 43720.2 | [5 empty] | 5 |  | 12 |  | 37375
G. |  | CARI
|  | 3% of Total Project Cost | [8 empty] | 76968.192 |  |  |  |  | 115790.5095 |  |  |  |  | 42641.6602 |  |  |  |  | 11716.8286
|  | Administrative cost | [8 empty] | 128280.32 |  |  |  |  | 148520.6269 |  |  |  |  | 355347.168 |  |  |  |  | 195280.4775
`
Summary:
|  | General Requirements | [8 empty] | 538108 |  |  |  |  | 781950 |  |  |  |  | 2031864 |  |  |  |  | 798593
|  | Material cost and Consumables | [8 empty] | 1541648.4 |  |  |  |  | 1840169.3 |  |  |  |  | 3468579.36 |  |  |  |  | 1955074.75
|  | Labor cost | [8 empty] | 485850 |  |  |  |  | 1237564.35 |  |  |  |  | 1606500 |  |  |  |  | 1151941.8
|  | Mark-up / profit | [8 empty] | 384840.96 |  |  |  |  | 618321.3207 |  |  |  |  | 426416.6016 |  |  |  |  | 468673.146
|  | GRAND TOTAL COST (VAT Exclusive) | [8 empty] | 3155695.872 |  |  |  |  | 4742316.1071 |  |  |  |  | 7931348.7898 |  |  |  |  | 4581280.0022
|  | GRAND TOTAL COST (VAT Inclusive) | [8 empty] | 3534379.3766 | [14 empty] | 5131033.6024
|  | COMPLETION |  |  |  |  | 25 WORKING DAYS
|  | GRAND TOTAL | [7 empty] | Php | 3155695.872 |  |  |  |  | 4742316.1071 |  |  |  |  | 7931348.7898 |  |  |  |  | 4581280.0022
[12 empty] | 1 |  |  |  |  | 2 |  |  |  |  | 3
Visa |  | Submitted by: | [5 empty] | Noted by:
[12 empty] | NO NEED TO RECONCILE THE QTY. IT SEEMS THE SAME FROM THE IN HOUSE |  |  |  |  | OMNI CREST IS REQUIRED TO REVIEW AND RESUBMIT NEW QUOTATION BECAUSE THE NPI MATERIAL IS ALSO FILLED WITH HIS BUDGET, FOR QTY. I THINK NO NEED TO RECONCILE IT SEEMS NOT FAR FROM IN HOUSE |  |  |  |  | RHAJTIK I THINK THAT’S OKAY BUT THE GENERAL REQUIREMENTS THERE IS SOMETHING ERROR ON THE PERCENTAGE CALCULATION INSTEAD OF 3% THEY PUT MORE LOWER PERCENTAGE
Date
The Grand total indicated above constitute the Fixed Lump Sum Price of our bid which includes the cost of materials, labor, equipments, overhead profits and all other construction related costs to satisfactorily complete the work in accordance with the drawings, Scope of Work, Specifications and other related bid documents.
It is understood that the quantities and unit prices indicated above are complete and any item not shown but otherwise required to satisfactorily complete the work are considered built-in and included in our Fixed Lump Sum Price. It is also understood that this Bid Breakdown is part of our proposal and the Owner can use this as one of the basis for evaluation.
| Construction Duration : |  |  |  | 25 WORKING DAYS
Submitted by:
|  |  |  | (Company Name) |  | (Signature Over Printed Name)
---------------- C L O S E ----------------
---------------- C L O S E ----------------
---------------- C L O S E ----------------
---------------- C L O S E ----------------

## Reconciliation
abcdef Good Food, Good Life |  |  |  |  | F O R M S |  |  |  | FORM CODE
BID BREAKDOWN DATA SHEET
PROJECT TITLE: |  |  |  | Proposed FFE RARE ROTARY FILTER |  |  |  |  | Date: | 2023-07-25 16:32
SUBJECT:
COST CENTER: | [8 empty] | Reference: | [8 empty] | Original In-House + Original Contractor’s Bids (All)
[7 empty] | IN HOUSE |  |  |  |  | ACE PACKAGING CO. |  |  |  |  | OMNI CREST ENG'G |  |  |  |  | RHAJTIK
No. |  | SCOPE OF WORKS |  |  |  |  | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT | Man'r | UNIT | QTY | U/RATE | AMOUNT
A. |  | GENERAL REQUIREMENTS
1 |  | Mobilization(Temfacil) | [5 empty] | lot | 1 | 25000 | 25000 |  | lot | 1 | 246000 | 246000 |  | lot | 1 | 525000 | 525000 |  | lot | 1 | 339250 | 339250
2 |  | Demobilization/Housekeeping | [5 empty] | lot | 1 | 35000 | 35000 |  | lot | 1 | 164000 | 164000 |  | lot | 1 | 525000 | 525000 |  | lot | 1 | 172500 | 172500
3 |  | Safety Provisions
4 |  | a. Cotton Gloves | [5 empty] | pairs | 710 | 27 | 19170 |  | pairs | 600 | 50 | 30000 |  | pairs | 200 | 224 | 44800 |  | pairs | 600 | 17.1 | 10260
5 |  | b. Welding Mask | [5 empty] | pcs | 7 | 550 | 3850 |  | pcs | 7 | 450 | 3150 |  | pcs | 6 | 560 | 3360 |  | pcs | 7 | 571.5 | 4000.5
6 |  | c. Welding Gloves | [5 empty] | pairs | 7 | 250 | 1750 |  | pairs | 7 | 750 | 5250 |  | pcs | 6 | 504 | 3024 |  | pairs | 7 | 401.5 | 2810.5
7 |  | d. Welding Apron | [5 empty] | pcs | 7 | 350 | 2450 |  | pcs | 7 | 500 | 3500 |  | pcs | 6 | 504 | 3024 |  | pcs | 7 | 855.5 | 5988.5
8 |  | e. Googles | [5 empty] | pcs | 30 | 250 | 7500 |  | pcs | 24 | 120 | 2880 |  | pcs | 27 | 280 | 7560 |  | pcs | 24 | 205 | 4920
9 |  | f. Dust Mask - N95 | [5 empty] | bxs | 650 | 350 | 227500 |  | bxs | 5 | 650 | 3250 |  | bxs | 3 | 168 | 504 |  | bxs | 650 | 172.5 | 112125
10 |  | g. Caution Tape | [5 empty] | roll | 2 | 1384 | 2768 |  | roll | 2 | 2000 | 4000 |  | roll | 2 | 896 | 1792 |  | roll | 2 | 1365 | 2730
11 |  | h. Rags | [5 empty] | kgs | 10 | 92 | 920 |  | kgs | 10 | 100 | 1000 |  | kgs | 10 | 224 | 2240 |  | kgs | 10 | 97.75 | 977.5
12 |  | i. Safety Signages | [5 empty] | lot | 1 | 5000 | 5000 |  | lot | 1 | 10000 | 10000 |  | lot | 1 | 4480 | 4480 |  | lot | 1 | 10925 | 10925
13 |  | j. Welding blankets | [5 empty] | roll | 6 | 2000 | 12000 |  | roll | 6 | 4500 | 27000 |  | pcs | 6 | 1680 | 10080 |  | roll | 6 | 1265 | 7590
14 |  | k. Fire Blanket | [5 empty] | roll | 6 | 1200 | 7200 |  | roll | 6 | 4500 | 27000 |  | pcs | 6 | 1680 | 10080 |  | roll | 6 | 1255 | 7530
Tools & Equipment Rentals
15 |  | Tig welding machines | [5 empty] | unit | 6 | 7000 | 42000 |  | unit | 6 | 8000 | 48000 |  | unit | 6 | 15800 | 94800 |  | unit | 6 | 5160 | 30960
16 |  | Portable Grinders 4" and 7"dia. | [5 empty] | unit | 8 | 3500 | 28000 |  | unit | 8 | 4500 | 36000 |  | unit | 8 | 26500 | 212000 |  | unit | 8 | 2875 | 23000
17 |  | Portable Drills | [5 empty] | unit | 4 | 2500 | 10000 |  | unit | 4 | 4500 | 18000 |  | unit | 4 | 7200 | 28800 |  | unit | 4 | 1725 | 6900
18 |  | A-Ladder | [5 empty] | lot | 2 | 3000 | 6000 |  | lot | 2 | 16850 | 33700 |  | lot | 2 | 5000 | 10000 |  | lot | 2 | 1725 | 3450
19 |  | As built drawings | [5 empty] | lot | 1 | 10000 | 10000 |  | lot | 1 | 15000 | 15000 |  | lot | 1 | 15000 | 15000 |  | lot | 1 |  | 13800
20 |  | Hand tools | [5 empty] | lot | 2 | 1000 | 2000 |  | lot | 2 | 3000 | 6000 |  | lot | 2 | 5000 | 10000 |  | lot | 2 |  | 5055
21 |  |  | Chain Block with certificate |  |  |  |  | lot | 2 | 5000 | 10000 |  | lot | 4 | 6500 | 26000 |  | lot | 2 | 20160 | 40320 |  | lot | 2 |  | 6900
22 |  | Construction Board 440V to 220V, 3phase | [5 empty] | set | 2 | 40000 | 80000 |  | set | 2 | 20000 | 40000 |  | set | 2 | 240000 | 480000 |  | set | 2 | 5750 | 11500
23 |  | Scaffolding | [5 empty] | lot | 1 | 15000 | 15000 |  | LOT | 1 | 50000 | 50000 | [6 empty] | Lot | 1 |  | 13800
|  | SUB-TOTAl | [8 empty] | 553108 |  |  |  |  | 799730 |  |  |  |  | 2031864 |  |  |  |  | 796972
B. |  | Improvement FFE RARE E-54
Product Line Supply and Return Coffee Liquor
1 |  | SS Pipe, 3"Ø, sch40, seamless x 6meters (suction/discharge) | [5 empty] | length | 10 | 24500 | 245000 |  | length | 10 | 21924 | 219240 |  | length | 10 | 63250 | 632500 |  | length | 10 | 24909 | 249090
2 |  | SS Pneumatic Valve , DN80, PN40 flanged type,raised face(suction /discharge) |  |  |  |  | NPI | unit | 4 | NPI |  |  | unit | 4 |  |  | NPI | unit | 4 | 4950 | 19800 | NPI | unit | 4
3 |  | SS Ball valve, 3 piece assembly, DN80,PN40, weld end |  |  |  |  | NPI | unit | 4 | NPI |  |  | unit | 4 |  |  | NPI | unit | 4 | 3960 | 15840 | NPI | unit | 4
4 |  | SS check valve, DN80,PN40 flanged type (product outlet) |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 3960 | 3960 | NPI | unit | 1
5 |  | SS Flanges, Weld neck type DN80, PN40 with bolts and washers and nuts | [5 empty] | sets | 13 | 3644 | 47372 |  | sets | 13 | 15300 | 198900 |  | sets | 13 | 15400 | 200200 |  | sets | 13 | 9062 | 117806
6 |  | SS Elbow, 3"Ø, sch40, seamless x 90°, weld and(product) | [5 empty] | pcs | 8 | 780 | 6240 |  | pcs | 8 | 2520 | 20160 |  | pcs | 8 | 16656.2 | 133249.6 |  | pcs | 8 | 1610 | 12880
7 |  | SS Elbow, 2"Ø, sch40, seamless x 90°, weld and(product) | [5 empty] | pcs | 10 | 485 | 4850 |  | pcs | 10 | 1596 | 15960 |  | pcs | 10 | 1886.5 | 18865 |  | pcs | 10 | 598 | 5980
8 |  | SS Elbow, 2"Ø, sch40, seamless x 45°, weld end (product) | [5 empty] | pcs | 6 | 485 | 2910 |  | pcs | 6 | 1596 | 9576 |  | pcs | 6 | 1886.5 | 11319 |  | pcs | 6 | 598 | 3588
9 |  | SS Concentric Reducer, 3"Ø x 1 1/2"Ø, sch40, weld end, seamless | [5 empty] | pcs | 2 | 805 | 1610 |  | pcs | 2 | 3528 | 7056 |  | pcs | 2 | 1430 | 2860 |  | pcs | 2 | 1092.5 | 2185
10 |  | SS Concentric Reducer, 2 "Ø x 1 1/2"Ø, sch40, weld end type | [5 empty] | pcs | 2 | 706 | 1412 |  | pcs | 2 | 1911 | 3822 |  | pcs | 2 | 4202 | 8404 |  | pcs | 2 | 1006.25 | 2012.5
11 |  | SS Tee, 3"Ø, sch40, seamless, weld end | [5 empty] | pcs | 6 | 1350 | 8100 |  | pcs | 6 | 3449.25 | 20695.5 |  | pcs | 6 | 4697 | 28182 |  | pcs | 6 | 2535.75 | 15214.5
12 |  | SS Tee, 2"Ø, sch40, seamless, weld end | [5 empty] | pcs | 3 | 1200 | 3600 |  | pcs | 3 | 2194.5 | 6583.5 |  | pcs | 3 | 1848 | 5544 |  | pcs | 3 | 1253.5 | 3760.5
13 |  | SS RED Tee, 3" X 1 1/2"Ø, sch40, seamless, weld end | [5 empty] | pcs | 2 | 1000 | 2000 |  | pcs | 2 | 7612.5 | 15225 |  | pcs | 2 | 5720 | 11440 |  | pcs | 2 | 1437.5 | 2875
BURSTING DISC
14 |  | SS Pipe, 1 1/2"Ø, sch40, seamless x 20 ft (Pressure relief Pipe) | [5 empty] | pcs | 14 | 13650 | 191100 |  | pcs | 14 | 7875 | 110250 |  | pcs | 14 | 21450 | 300300 |  | pcs | 14 | 8682.5 | 121555
15 |  | Bursting disc DN80 PN40 |  |  |  |  | NPI | pcs | 1 |  |  |  | pcs | 1 |  |  | NPI | pcs | 1 | 3960 | 3960
Pressure Relief
16 |  | SS Pipe, 1 1/2"Ø, sch40, seamless x 20 ft (Pressure relief Pipe) | [5 empty] | lght | 14 | 13650 | 191100 |  | lght | 14 | 7875 | 110250 |  | lght | 14 | 21450 | 300300 |  | lght | 14 | 8682.5 | 121555
17 |  | Pressure Relief Valve DN40,15 bars |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 4950 | 4950 | NPI | unit | 1
18 |  | SS Flanges, DN40, 1 1/2" PN40 with bolts and washers and nuts | [5 empty] | sets | 12 | 815 | 9780 |  | sets | 12 | 6600 | 79200 |  | sets | 12 | 11000 | 132000 |  | sets | 12 | 5681 | 68172
19 |  | SS Elbow, 1 1/2"Ø, sch40, seamless x 90°, weld end type (product) | [5 empty] | pcs | 8 | 245 | 1960 |  | pcs | 8 | 1421.7 | 11373.6 |  | pcs | 8 | 1707.2 | 13657.6 |  | pcs | 8 | 414 | 3312
20 |  | SS Elbow, 1 1/2"Ø, sch40, seamless x 45°, welded end type (product) | [5 empty] | pcs | 12 | 245 | 2940 |  | pcs | 12 | 1421.7 | 17060.4 |  | pcs | 12 | 1707.2 | 20486.4 |  | pcs | 12 | 414 | 4968
21 |  | SS Tee, 1 1/2"Ø, sch40, seamless, welded type | [5 empty] | pcs | 2 | 335 | 670 |  | pcs | 2 | 2982 | 5964 |  | pcs | 2 | 1617 | 3234 |  | pcs | 2 | 966 | 1932
22 |  | SS Concentric Reducer, 3 "Ø x 1 1/2"Ø, sch40, weld end type, seamless | [5 empty] | pcs | 1 | 706 | 706 |  | pcs | 1 | 3465 | 3465 |  | pcs | 1 | 1683 | 1683 |  | pcs | 1 | 1092.5 | 1092.5
Drain Line - Coffee sludge
23 |  | SS Pipe, 2"Ø, sch40, seamless x 20 ft (Drain line) | [5 empty] | lght | 2 | 14888 | 29776 |  | lght | 2 | 9975 | 19950 |  | lght | 2 | 10340 | 20680 |  | lght | 2 | 12029 | 24058
24 |  | SS Pneumatic Valve , DN50, PN40 flanged type,raised face |  |  |  |  | NPI | unit | 2 | NPI |  |  | unit | 2 |  |  | NPI | unit | 2 | 4950 | 9900 | NPI | unit | 2
25 |  | Handle valve DN50 PN40 Locking plate |  |  |  |  | NPI | Sets | 1 |  |  |  | Sets | 1 |  |  | NPI | Sets | 1 | 3960 | 3960 | NPI | Sets | 1
26 |  | SS Flanges, DN50, PN40 with bolts and washers and nuts | [5 empty] | sets | 6 | 1100 | 6600 |  | sets | 6 | 10500 | 63000 |  | sets | 6 | 8800 | 52800 |  | sets | 6 | 7406 | 44436
27 |  | Sight Glass, DN50,PN10 |  |  |  |  | NPI | sets | 1 | NPI |  |  | sets | 1 |  |  | NPI | sets | 1 | 3960 | 3960 | NPI | sets | 1
28 |  | SS Elbow, 2"Ø, sch40, seamless x 90°, weld end | [5 empty] | pcs | 4 | 485 | 1940 |  | pcs | 4 | 1596 | 6384 |  | pcs | 4 | 572 | 2288 |  | pcs | 4 | 598 | 2392
29 |  | SS Elbow, 2"Ø, sch40, seamless x 45°, weld end | [5 empty] | lot | 1 | 485 | 485 |  | lot | 1 | 1596 | 1596 |  | lot | 1 | 572 | 572 |  | lot | 1 | 598 | 598
Hot Water Line
30 |  | SS Pipe, 1 1/2"Ø, sch40, seamless x 20 ft (hot water) - Steam Line | [5 empty] | lght | 14 | 13650 | 191100 |  | lght | 14 | 7875 | 110250 |  | lght | 14 | 7700 | 107800 |  | lght | 14 | 8682.5 | 121555
31 |  | SS Pneumatic Valve , DN40, PN40 flanged type,raised face |  |  |  |  | NPI | unit | 2 | NPI |  |  | unit | 2 |  |  | NPI | unit | 2 | 3960 | 7920 | NPI | unit | 2
32 |  | SS Ball valve, 3 piece assembly, 1 1/2"Ø, Weld End (hot water) |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 3960 | 3960 | NPI | unit | 1
33 |  | SS check valve, DN40,PN40 flanged type |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 3960 | 3960 | NPI | unit | 1
34 |  | SS Flanges, DN40, PN40 with bolts and washers and nuts | [5 empty] | sets | 6 | 815 | 4890 |  | sets | 6 | 9030 | 54180 |  | sets | 6 | 11000 | 66000 |  | sets | 6 | 6256 | 37536
35 |  | SS Tee, 3"Ø, sch40, seamless, weld end | [5 empty] | pcs | 1 | 1450 | 1450 |  | pcs | 1 | 3449.25 | 3449.25 |  | pcs | 1 | 4697 | 4697 |  | pcs | 1 | 2535.75 | 2535.75
36 |  | SS Concentric Reducer, 3"Ø x 1 1/2"Ø, sch40, weld end | [5 empty] | pcs | 1 | 1050 | 1050 |  | pcs | 1 | 3465 | 3465 |  | pcs | 1 | 2513.5 | 2513.5 |  | pcs | 1 | 1092.5 | 1092.5
37 |  | SS Elbow, 1 1/2"Ø, sch40, seamless x 90°, weld end (hot water) | [5 empty] | pcs | 10 | 245 | 2450 |  | pcs | 10 | 1423.8 | 14238 |  | pcs | 10 | 389.4 | 3894 |  | pcs | 10 | 414 | 4140
38 |  | SS Elbow, 1 1/2"Ø, sch40, seamless x 45°, weld end (hot water) | [5 empty] | pcs | 6 | 245 | 1470 |  | pcs | 6 | 1423.8 | 8542.8 |  | pcs | 6 | 389.4 | 2336.4 |  | pcs | 6 | 414 | 2484
39 |  | SS Tee, 1 1/2"Ø, sch40, seamless, weld end | [5 empty] | pcs | 1 | 650 | 650 |  | pcs | 1 | 2982 | 2982 |  | pcs | 1 | 924 | 924 |  | pcs | 1 | 966 | 966
40 |  | 1 1/2" x 2" thick insulation-calcium silicate ( 2ft pre moulded) | [5 empty] | pcs | 40 | 750 | 30000 |  | pcs | 40 | 408.45 | 16338 |  | pcs | 40 | 2400 | 96000 |  | pcs | 40 | 460 | 18400
41 |  | SS Cladding, 0.6mm thk, 4 ft x 8 ft | [5 empty] | sheet | 10 | 4500 | 45000 |  | sheet | 10 | 2483.25 | 24832.5 |  | sheet | 10 | 3840 | 38400 |  | sheet | 10 | 3220 | 32200
Instrument Air Line
42 |  | SS Pipe, 1/2"Ø, sch40, seamless x 20 ft (compressed air) | [5 empty] | lght | 5 | 1980 | 9900 |  | lght | 5 | 7875 | 39375 |  | lght | 5 | 3234 | 16170 |  | lght | 5 | 3266 | 16330
43 |  | SS Ball valve, 3 pc assembly, 1/2 "Ø, weld end (comp. air) |  |  |  |  | NPI | pcs | 2 | NPI |  |  | pcs | 2 |  |  | NPI | pcs | 2 | 2640 | 5280 | NPI | pcs | 2
44 |  | SS Elbow, 1/2"Ø, sch40, seamless x 90°, weld end (compressed air) | [5 empty] | pcs | 8 | 75 | 600 |  | pcs | 8 | 1421.7 | 11373.6 |  | pcs | 10 | 440 | 4400 |  | pcs | 8 | 161 | 1288
45 |  | Air Service unit air filter |  |  |  |  | NPI | unit | 1 | NPI |  |  | unit | 1 |  |  | NPI | unit | 1 | 2640 | 2640 | NPI | unit | 1
46 |  | SS Tee Reducer 1 " x 1/2" weld end , seamless | [5 empty] | pcs | 1 | 350 | 350 |  | pcs | 1 | 1352.4 | 1352.4 |  | pcs | 1 | 1012 | 1012 |  | pcs | 1 | 632.5 | 632.5
47 |  | Pneumatic Header, SS Pipe sch 20, with Fittings, Fabricated as per drawing | [5 empty] | lot | 1 | 2500 | 2500 |  | lot | 1 | 45000 | 45000 |  | lot | 1 | 49500 | 49500 |  | lot | 1 | 86250 | 86250
Support and Hanger
48 |  | SS Angle bar, 2" x 2" x 1/4" thk x 20 ft | [5 empty] | lght | 2 | 5500 | 11000 |  | lght | 2 | 6510 | 13020 |  | lght | 2 | 5940 | 11880 |  | lght | 2 | 6900 | 13800
49 |  | SS Channel bar, 4" x 5.4 lbs/ft x 10 ft (Self Cleaning Filter Support) | [5 empty] | lght | 3 | 34000 | 102000 |  | lght | 3 | 28350 | 85050 |  | lght | 3 | 42075 | 126225 |  | lght | 3 | 59800 | 179400
50 |  | SS U-bolts, M12 | [5 empty] | set | 20 | 85 | 1700 |  | set | 20 | 331.8 | 6636 |  | set | 20 | 433.4 | 8668 |  | set | 20 | 230 | 4600
51 |  | SS U-bolts, M10 | [5 empty] | set | 40 | 65 | 2600 |  | set | 40 | 161.7 | 6468 |  | set | 40 | 183.7 | 7348 |  | set | 40 | 189.75 | 7590
52 |  | SS U-bolts, M8 | [5 empty] | set | 36 | 42 | 1512 |  | set | 36 | 124.95 | 4498.2 |  | set | 36 | 59.4 | 2138.4 |  | set | 36 | 138 | 4968
53 |  | SS Square Tube 2"x2"x4mm thick 6meter length | [5 empty] | lght | 10 | 6703.4 | 67034 |  | lght | 10 | 12600 | 126000 |  | lght | 10 | 13227.5 | 132275 |  | lght | 10 | 8970 | 89700
54 |  | 4mm thick SS304 Flat bar 2ft. | [5 empty] | lght | 10 | 2500 | 25000 |  | lght | 10 | 2100 | 21000 |  | lght | 10 | 2750 | 27500 |  | lght | 10 | 2760 | 27600
55 |  | M8X40mm Hexabolt dome type hex head | [5 empty] | pcs | 100 | 30 | 3000 |  | pcs | 100 | 16.8 | 1680 |  | pcs | 100 | 220 | 22000 |  | pcs | 100 | 51.75 | 5175
56 |  | DN20 SCH. 40 SS304 | [5 empty] | lght | 4 | 1500 | 6000 |  | lght | 4 | 2992.5 | 11970 |  | lght | 4 | 2866.6 | 11466.4 |  | lght | 4 | 4025 | 16100
57 |  | SS Flat bar 4ft. | [5 empty] | lght | 4 | 1161.6 | 4646.4 |  | lght | 4 | 4500 | 18000 |  | lght | 4 | 9350 | 37400 |  | lght | 4 | 2760 | 11040
Fabricated Trolley
58 |  | Fabrication of SS Trolley,Fabricate as per drawing - 300 kgs capacity | [5 empty] | lot | 2 | 45000 | 90000 |  | lot | 2 | 18000 | 36000 |  | lot | 2 | 83185.3 | 166370.6 |  | lot | 2 | 86250 | 172500
|  | SUB-TOTAl | [8 empty] | 1366053.4 |  |  |  |  | 1611411.75 |  |  |  |  | 2937572.9 |  |  |  |  | 1667344.75
E. |  | CONSUMABLES
1 |  | Cutting Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm | [5 empty] | pcs | 65 | 100 | 6500 |  | pcs | 65 | 172.2 | 11193 |  | pcs | 200 | 71.5 | 14300 |  | pcs | 65 | 51.75 | 3363.75
2 |  | Cutting Discs, 7"Ø, "Tyrolit" brand, 8,600 rated rpm | [5 empty] | pcs | 65 | 150 | 9750 |  | pcs | 65 | 116.55 | 7575.75 |  | pcs | 70 | 137.5 | 9625 |  | pcs | 65 | 149.5 | 9717.5
3 |  | Grinding Discs, 4"Ø, "Tyrolit" brand, 15,300 rated rpm | [5 empty] | pcs | 65 | 125 | 8125 |  | pcs | 65 | 122.85 | 7985.25 |  | pcs | 60 | 38.5 | 2310 |  | pcs | 65 | 51.75 | 3363.75
4 |  | Grinding Discs, 7"Ø, "Tyrolit" brand, 8,600 rated rpm | [5 empty] | pcs | 65 | 175 | 11375 |  | pcs | 65 | 219.45 | 14264.25 |  | pcs | 20 | 165 | 3300 |  | pcs | 65 | 149.5 | 9717.5
6 |  | Tungsten | [5 empty] | pcs | 18 | 100 | 1800 |  | pcs | 18 | 117.6 | 2116.8 |  | pcs | 10 | 220 | 2200 |  | pcs | 18 | 115 | 2070
7 |  | SS Filler Rod, 304 | [5 empty] | kgs | 18 | 950 | 17100 |  | kgs | 18 | 882 | 15876 |  | kgs | 70 | 990 | 69300 |  | kgs | 18 | 2472.5 | 44505
8 |  | Blind Revits | [15 empty] | box | 3 | 1320 | 3960
9 |  | Argon Gas | [5 empty] | cyl | 20 | 4135 | 82700 |  | cyl | 20 | 2940 | 58800 |  | cyl | 70 | 4950 | 346500 |  | cyl | 20 | 4255 | 85100
10 |  | Tig Cleene | [5 empty] | kgs | 2 | 1650 | 3300 |  | kgs | 2 | 2257.5 | 4515 |  | kgs | 2 | 440 | 880 |  | kgs | 2 | 747.5 | 1495
11 |  | Finishing Wheel/Grey | [5 empty] | pcs | 20 | 336 | 6720 |  | pcs | 20 | 892.5 | 17850 |  | pcs | 20 | 55 | 1100 |  | pcs | 20 | 2875 | 57500
12 |  | Oxygen | [5 empty] | cyl | 15 | 375 | 5625 |  | cyl | 15 | 682.5 | 10237.5 |  | cyl | 2 | 990 | 1980 |  | cyl | 15 | 517.5 | 7762.5
13 |  | Acetylene | [5 empty] | cyl | 10 | 1050 | 10500 |  | cyl | 10 | 1890 | 18900 |  | cyl | 1 | 1320 | 1320 |  | cyl | 10 | 1437.5 | 14375
14 |  | Painting Works | [5 empty] | Gal | 2 | 1050 | 2100 |  | Gal | 2 | 1800 | 3600 |  | Gal | 1 | 1650 | 1650 |  | Gal | 2 | 1380 | 2760
15 |  | Miscelleneous(painting/Tagging/Labeling and others) | [5 empty] | lot | 1 | 10000 | 10000 |  | lot | 1 | 5000 | 5000 |  | lot | 1 | 72581.46 | 72581.46 |  | lot | 1 | 46000 | 46000
|  | SUB-TOTAl | [8 empty] | 175595 |  |  |  |  | 177913.55 |  |  |  |  | 531006.46 |  |  |  |  | 287730
F. |  | LABOR COSTING
[7 empty] | No. of Manpower | Days | No. of Days | Manpower Rate | Total Cost | No. of Manpower | Days | No. of Days | Manpower Rate | Total Cost | No. of Manpower | Days | No. of Days | Manpower Rate | Total Cost | No. of Manpower | Days | No. of Days | Manpower Rate | Total Cost
FABRICATION
1 |  | Foreman/Leadman |  |  |  |  | 1 | days | 15 | 850 | 12750 | 1 | days | 15 | 1562.7 | 23440.5 | 1 | days | 30 | 2220 | 66600 | 1 | days | 15 | 1509.38 | 22640.7
2 |  | Pipe Fitter |  |  |  |  | 3 | days | 15 | 650 | 29250 | 3 | days | 15 | 1455.78 | 65510.1 | 1 | days | 5 | 1980 | 9900 | 3 | days | 15 | 1509.38 | 67922.1
3 |  | Welders - Subject for actual testing |  |  |  |  | 2 | days | 15 | 800 | 24000 | 2 | days | 15 | 1443.72 | 43311.6 | 2 | days | 30 | 1980 | 118800 | 2 | days | 15 | 1433.91 | 43017.3
4 |  | Skilled Helpers |  |  |  |  | 4 | days | 15 | 650 | 39000 |  | days |  |  | 0 | [6 empty] | days |  | 1282.97 | 0
|  | SUB-TOTAl |  |  |  |  | 10 |  |  |  | 105000 | 6 |  |  |  | 132262.2 |  |  |  |  | 195300 |  |  |  |  | 133580.1
INSTALLATION
1 |  | Project Engineer |  |  |  |  | 1 | days | 25 | 1000 | 25000 | 1 | days | 25 | 2586.26 | 64656.5 | [5 empty] | 1 | days | 25 | 2803.13 | 70078.25
2 |  | Quality Officer |  |  |  |  | 1 | days | 25 | 750 | 18750 | 1 | days | 25 | 2856.26 | 71406.5 | [5 empty] | 1 | days | 25 | 2242.5 | 56062.5
3 |  | Safety Officer |  |  |  |  | 1 | days | 25 | 750 | 18750 | 1 | days | 25 | 2023.47 | 50586.75 | [5 empty] | 1 | days | 25 | 2055.63 | 51390.75
4 |  | Foreman/leadman |  |  |  |  | 1 | days | 25 | 850 | 21250 |  |  |  |  | 0 | [6 empty] | days | 25 | 1868.75 | 0
5 |  | Pipe Fitter |  |  |  |  | 4 | days | 25 | 650 | 65000 | 4 | days | 25 | 2237.63 | 223763 | [5 empty] | 4 | days | 25 | 1868.75 | 186875
6 |  | Welders-Qualified on NPI |  |  |  |  | 3 | days | 25 | 800 | 60000 | 3 | days | 25 | 2215.66 | 166174.5 | 2 | days | 30 | 2100 | 126000 | 3 | days | 25 | 1775.31 | 133148.25
7 |  | Skilled Helpers |  |  |  |  | 4 | days | 25 | 650 | 65000 | 4 | days | 25 | 1247.37 | 124737 | 4 | days | 30 | 1980 | 237600 | 4 | days | 25 | 1588.44 | 158844
8 |  | Tool keeper |  |  |  |  | 1 | days | 25 | 650 | 16250 | 1 | days | 25 | 1247.37 | 31184.25 | 6 | days | 30 | 1980 | 356400 | 1 | days | 25 | 1588.44 | 39711
9 |  | Scaffoldder |  |  |  |  | 2 | days | 25 | 800 | 40000 | 1 | days | 25 | 1984.22 | 49605.5 | 8 | days | 30 | 1920 | 460800 | 1 | days | 25 | 1588.44 | 39711
10 |  | Fire watcher |  |  |  |  | 1 | days | 25 | 650 | 16250 | 1 | days | 25 | 1984.22 | 49605.5 | 2 | days | 30 | 1920 | 115200 | 1 | days | 25 | 1588.44 | 39711
11 |  | Electrician |  |  |  |  | 1 | days | 25 | 800 | 20000 | 1 | days | 25 | 1797.52 | 44938 | 2 | days | 30 | 1920 | 115200 | 1 | days | 25 | 1681.88 | 42047
|  | Sub-Total |  |  |  |  | 20 |  | 25 |  | 366250 | 18 |  |  |  | 876657.5 |  |  |  |  | 1411200 |  |  |  |  | 817578.75
LABOR COSTING FOR COMMISSIONING (With overtime)
1 |  | Fitter |  |  |  |  | 2 | days | 4 | 650 | 5200 | 2 | days | 4 | 2237.63 | 17901.04 | [5 empty] | 2 | days | 4 | 1868.75 | 14950
2 |  | Welders |  |  |  |  | 2 | days | 4 | 800 | 6400 | 2 | days | 4 | 2215.66 | 17725.28 | [5 empty] | 2 | days | 4 | 1775.31 | 14202.48
3 |  | Safety Officer |  |  |  |  | 1 | days | 4 | 750 | 3000 | 1 | days | 4 | 2023.47 | 8093.88 | [5 empty] | 1 | days | 4 | 2055.63 | 8222.52
|  | Sub-Total |  |  |  |  | 5 |  | 12 |  | 14600 |  |  |  |  | 43720.2 | [5 empty] | 5 |  | 12 |  | 37375
G. |  | CARI
|  | 3% of Total Project Cost | [8 empty] | 77418.192 |  |  |  |  | 109250.856 |  |  |  |  | 42641.6602 |  |  |  |  | 11221.7418
|  | Administrative cost | [8 empty] | 129030.32 |  |  |  |  | 126316.788 |  |  |  |  | 355347.168 |  |  |  |  | 187029.03
`
Summary:
|  | General Requirements | [8 empty] | 553108 |  |  |  |  | 799730 |  |  |  |  | 2031864 |  |  |  |  | 796972
|  | Material cost and Consumables | [8 empty] | 1541648.4 |  |  |  |  | 1789325.3 |  |  |  |  | 3468579.36 |  |  |  |  | 1955074.75
|  | Labor cost | [8 empty] | 485850 |  |  |  |  | 1052639.9 |  |  |  |  | 1606500 |  |  |  |  | 988533.85
|  | Mark-up / profit | [8 empty] | 387090.96 |  |  |  |  | 581589.4266 |  |  |  |  | 426416.6016 |  |  |  |  | 448869.672
|  | GRAND TOTAL COST (VAT Exclusive) | [8 empty] | 3174145.872 |  |  |  |  | 4458852.2706 |  |  |  |  | 7931348.7898 |  |  |  |  | 4387701.0438
|  | GRAND TOTAL COST (VAT Inclusive) | [8 empty] | 3555043.3766 | [14 empty] | 4914225.1691
|  | COMPLETION |  |  |  |  | 25 WORKING DAYS
|  | GRAND TOTAL | [7 empty] | Php | 3174145.872 |  |  |  |  | 4458852.2706 |  |  |  |  | 7931348.7898 |  |  |  |  | 4387701.0438
[12 empty] | 1 |  |  |  |  | 2 |  |  |  |  | 3
Visa |  | Submitted by: | [5 empty] | Noted by:
[12 empty] | Reconciled and some adjustment for APCI |  |  |  |  | OMNI CREST DID NOT PARTICIPATE FOR Reconciliation |  |  |  |  | Reconciled and some adjustment
Date
The Grand total indicated above constitute the Fixed Lump Sum Price of our bid which includes the cost of materials, labor, equipments, overhead profits and all other construction related costs to satisfactorily complete the work in accordance with the drawings, Scope of Work, Specifications and other related bid documents.
It is understood that the quantities and unit prices indicated above are complete and any item not shown but otherwise required to satisfactorily complete the work are considered built-in and included in our Fixed Lump Sum Price. It is also understood that this Bid Breakdown is part of our proposal and the Owner can use this as one of the basis for evaluation.
| Construction Duration : |  |  |  | 25 WORKING DAYS
Submitted by:
|  |  |  | (Company Name) |  | (Signature Over Printed Name)
---------------- C L O S E ----------------
---------------- C L O S E ----------------
---------------- C L O S E ----------------
---------------- C L O S E ----------------

## SUMMARY
| SCOPE OF WORKS | IN HOUSE | ACE PACKAGING | OMNI CREST | RHAJTIK
A | GENERAL REQUIREMENTS | 553108 | 799730 | 2031864 | 796972
B | MATERIALS COST AND CONSUMABLES | 1541648.4 | 1789325.3 | 3468579.36 | 1955074.75
C | LABOR COST | 485850 | 1052639.9 | 1606500 | 988533.85
D | CARI | 77418.19 | 109250.86 | 42641.66 | 11221.74
E | ADMINISTRATIVE COST | 129030.32 | 126316.79 | 355347.17 | 187029.03
F | OVERHEAD/CONTINGENCY
G | MARK UP PROFIT | 387090.96 | 581589.43 | 426416.6 | 448869.67
| GRAND TOTAL | 3174145.87 | 4458852.28 | 7931348.79 | 4387701.04 | 0
|  | 100% | 140.5% | 249.9% | 138.2% | 0%