## STATUS RAW
PROJECT | DOC | STATUS
AUTOCOMPACTOR | AMM | Done discussion
| MPLAN | Done discussion
HYDRAULIC PROJECT | AMM | Done discussion
| MPLAN | Done discussion
GCU+ | AMM | Done discussion
| MPLAN | Done discussion
WATER HEATER | AMM | Done discussion
| MPLAN | Done discussion
GCCD Transport Phase 1 | AMM | Schedule: Sept 20
| MPLAN | Schedule: Sept 20
SIR | AMM | Schedule: Sept 19
| MPLAN | Schedule: Sept 19
IPTA VACUUM PUMP | AMM | Done discussion
| MPLAN | Done discussion
ICIP | AMM | Schedule: Sept 19
| MPLAN | Schedule: Sept 19
GC Van Unloading Facility | AMM | Done discussion
| MPLAN | Done discussion
PEC 2020: PE Panel Cooling | AMM | Schedule: Sept 19
| MPLAN | Schedule: Sept 19
PEC 2020: Process adaptation | AMM | Schedule: Sept 19
| MPLAN | Schedule: Sept 20
FFE-RARE | AMM | Schedule: Sept 20
| MPLAN | Schedule: Sept 20
PEC 2020: Spot Cooling | AMM | Schedule: Sept 20
| MPLAN | Schedule: Sept 20
PACKING VENTILATION | AMM | Done discussion
| MPLAN | Done discussion
Wet Process Upgrade | AMM | Schedule: Sept 20
| MPLAN | Schedule: Sept 20
AFBB Smokestack Upgrade | AMM | Schedule: Sept 21
| MPLAN | Schedule: Sept 21
Secondary Packaging Area Ventilation (DHNS) | AMM | Schedule: Sept 21
| MPLAN | Schedule: Sept 21
ETS 2021: AFBB Heat Recovery System | AMM | Schedule: Sept 21
| MPLAN | Schedule: Sept 21
Project Elmer (Phase 1) - DHNS | AMM | Schedule: Sept 21
| MPLAN | Schedule: Sept 21
Homogenizers and HPP Cooling Water Recovery System | AMM | Done discussion
| MPLAN | Done discussion

## RAW
PART / MPLAN NO. | PROJECT | DESCRIPTION | DOC_TYPE | INIT DATE | STATUS | TIMESTAMP | INIT_AGE (DAYS) | AGE (DAYS) | PIC | REMARKS | PROJECT_TYPE | AREA | TYPE | SWITCH | REMARKS FOR WEEKLY REPORT
| AUTOCOMPACTOR | DOOR FLAP PNUEMATIC CYLINDER - REPAIR | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 14W ENERGY CHAIN - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 6M DRIVE GEAR MOTOR - PM INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3Y DRIVE GEAR MOTOR PM CHANGE GEAR OIL | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3W VIBRATOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3W DRIVE GEAR MOTOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3W COMPACTOR HOIST - PM - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3M VIBRATOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3M KNOCKER HAMMER Inspection | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3M DRIVE GEAR MOTOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3M COMPACTOR HOIST - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1Y VIBRATOR MOTOR - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1Y DRIVE GEAR MOTOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1Y COMPACTOR HOIST - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1M VIBRATOR MOTOR - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1M KNOCKER HAMMER Inspection | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1D VIBRATOR MOTOR - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | EXPULSION VALVE CYLINDER SERVICING E54 2.5Y | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC BYPASS VALVE SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC LID CYLINDER SERVICING E54 2Y | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC LID LOCK CYLINDER SERVICING E542Y | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC OVER CENTRE VALVE SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC PRESSURE RELIEF VALVE SERVICING | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC QUICK ACTING VALVE SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC SPEED REGULATOR VALVE SERVICING | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC STOP VALVE (HS-22W-6M) SERVICING | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC VALVE (HS-43W-6) SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC VALVE (HS-43W-6V) SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 202.3424 | 36.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCU+ | <to utilize existing MPLAN> | MPLAN | 2024-03-01 | DONE | 2024-07-29 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | <to utilize existing MPLAN> | MPLAN | 2024-03-01 | DONE | 2024-07-29 | 202.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 2Y (15000H) Diverter Maintenance | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 141.3424 | 47.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 6M (4000H) Diverter Maintenance | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 141.3424 | 47.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 3Y DRIVE GEAR MOTOR PM | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 141.3424 | 47.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 6M DRIVE GEAR MOTOR PM | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 141.3424 | 47.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Rotary Valve GL 300 - 3M (2500OH) Inspection | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 141.3424 | 47.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Rotary Valve GL 300 - 12M (10000OH) Servicing | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 141.3424 | 47.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Sealing or Quenching Liquid Check 2Y | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Sealing or Quenching Liquid Check 1D | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Replacement of Shaft Seal 2Y | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Replacement of Motor 2Y (Existing MPLAN) | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Calibration of Pressure Transmitter 52W | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Replacement of Valve Terminal | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | 3M 2000L Sludge Tank Agitator Gearbox - INSPECTION | MPLAN | 2024-06-01 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 110.3424 | 45.3424 | Jenelyn Allado | Hand over to Maam Allado for review. | OLD | Coffee | TARGET | 1
| SIR | 3Y 2000L Sludge Tank Agitator Gearbox - CHANGE GEAR OIL | MPLAN | 2024-06-01 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 110.3424 | 45.3424 | Jenelyn Allado | Hand over to Maam Allado for review. | OLD | Coffee | TARGET | 1
| SIR | 6M 2000L Sludge Tank Agitator Gearbox - INSPECTION | MPLAN | 2024-06-01 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 110.3424 | 45.3424 | Jenelyn Allado | Hand over to Maam Allado for review. | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | 12W VACUUM PUMP LEMA 251 9Z Inspection | MPLAN | 2024-07-08 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-20 | 73.3424 | 30.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | 12W VACUUM PUMP LEMA 425 AZ Inspection | MPLAN | 2024-07-08 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-09 | 73.3424 | 41.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 0
| ICIP | MPlan1_Butterfly Valves.FS | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | MPlan2_Mixproof Valves.FS | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | MPlan3_Pneumatic Actuator Replacement.FS | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Replacement of Motor - 801 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Replacement of Shaft Seal - 803 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Sealing or Quenching Liquid Check - 802 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Replacement of Motor - 798 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Replacement of Shaft Seal - 800 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Sealing or Quenching Liquid Check - 799 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 262.3424 | 262.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Nozzle Spray 1/4 | AMM | 2024-01-01 | DONE | 2024-09-12 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hoist Control Set DEMAG | AMM | 2024-01-01 | DONE | 2024-09-12 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hoist Electric DEMAG | AMM | 2024-01-01 | DONE | 2024-09-12 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hose pre-wet ESI-NEP 6 | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 262.3424 | 171.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hose water nipple union | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 262.3424 | 171.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hose water pipe union | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 262.3424 | 171.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hose water nipple union ESIC BSP 4mtrs | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 262.3424 | 171.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Motor vibrating flap ESIC VV40B | AMM | 2024-01-01 | DONE | 2024-04-01 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Valve Solenoid Spray | AMM | 2024-01-01 | DONE | 2024-04-01 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Valve Solenoid Spray 1 1/2" DP100 | AMM | 2024-01-01 | DONE | 2024-04-01 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Chain Duplex ESIC | AMM | 2024-01-01 | DONE | 2024-04-01 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Motor Gear SW Helical | AMM | 2024-01-01 | DONE | 2024-04-01 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | MaghSpare Partser Knocker Nippon SIC-1AS | AMM | 2024-01-01 | DONE | 2024-04-01 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | MaghSpare Partser Knocker Nippon SB-1A | AMM | 2024-01-01 | DONE | 2024-04-01 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Actuator Door Flap ESIC MDUH 1003 | AMM | 2024-01-01 | DONE | 2024-04-01 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Switch Proximity | AMM | 2024-01-01 | DONE | 2024-04-01 | 262.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | SKF Bearing FYTB 15 FM | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-27 | 141.3424 | 23.3424 | Jenelyn Allado |  | OLD | Coffee | ADDITIONAL | 1
| AUTOCOMPACTOR | Spring Compression, OD 50-51mm 100mm L | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 141.3424 | 171.3424 | Jenelyn Allado |  | OLD | Coffee | ADDITIONAL | 1
| AUTOCOMPACTOR | Cylinder Pneumatic 160x100 mm 12kN Festo | AMM | 2024-05-01 | DONE | 2024-04-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | 1
| AUTOCOMPACTOR | Hose PTFE Exitflex EF179 1/4" OL=30cm | AMM | 2024-05-01 | DONE | 2024-04-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | 1
| AUTOCOMPACTOR | Vibrator Assembly | AMM | 2024-05-01 | DONE | 2024-04-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | 1
| HYDRAULIC PROJECT | Hydraulic cylinder - Expulsion valve - D130L09E0254028 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Tubing Flexible Compair 1089041000205 1000mm nipples FL6.35/FL6.35, Inox | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1089041050201 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1178012011 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2318N001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2018N002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2102N001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2218N001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - 1118072 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V1502A001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - D150L11C0330019 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1122120700002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1122120800003 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - V2818B001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - V2418B005 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1089040850202 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1089040950202 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1115006144 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - D090L11C0155007 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1122120800002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1122120850002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040570202 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - E050A05F0020012 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Silverpress Flexible Tubing - 1089040550204 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - E125B09E0010124 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - 1089041100202 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1 |  | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1119002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1116014 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1096160003 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1107006 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 10990016002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1107007 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079D130L10014 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079D150L12011 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079D090L12009 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2018002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2118002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079E125A10042 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V0100001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hose Flex Compair 1122120800001 800mm type: 15L-1ST-15K90L, 800 mm long | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-10 | 141.3424 | 9.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic valve - V2318N002 type: HS-4/3W-6 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-10 | 141.3424 | 9.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic valve - V2318N004 type: HS-2/2W-6/M | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-10 | 141.3424 | 9.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Pneum.- throttle-check valve - 1135016001 type: DRV-18 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-10 | 141.3424 | 9.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic solenoid valve 4/2 - 1096000022 type: MS-W 4/2W-10 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-10 | 141.3424 | 9.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Stiffener sleeve INOX - 1115006061 Type: SO 50003-6-4 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-10 | 141.3424 | 9.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Repair kit for pneum. locking-cylinder - 1079E050A06008 V50-20EdK/spez.9 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-10 | 141.3424 | 9.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hose Flexible Compair 1122120950002 950mm | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1178012012 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1115006117 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1089081200001 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040610201 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040630201 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040500205 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - 1089040950203 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - 1115006497 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1096100001 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1144007 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1115006439 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2318002 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2318001 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2118001 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2418004 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079E125A10041 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 141.3424 | 52.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Suction filter - 10990040001 type: S45 - G1"-A | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-10 | 141.3424 | 9.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCU+ | Gasket Klinger C4408 107x52x1.5mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| GCU+ | Gasket Klinger C4408 145x80x1.5mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| GCU+ | Gasket Klinger C4408 107x50x1.5mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| GCU+ | Gasket Steelflon 98x50x2mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | Gasket head Ginox 3813/22A 735x3mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | Gasket head Ginox 3813/22A 585x3mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | Gasket head Ginox 3813/22B 735x3mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | Gasket head Ginox 3813/22B 585x3mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 141.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | 3/4"W Flanges Stud A193 Gr B7 (ZN) SET (+ 3/4"W Stud nuts ASTM A184 Gr 2H DIN-934,3/4"W Stud washer HV140 (ZN) dia21 DIN125) | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 141.3424 | 22.3424 | John Carlo Baltazar | Forwarded to Maam Jen for review last July 4 but no feedback. Decided to proceed with docusign. | OLD | Coffee | ADDITIONAL | 1
| GCCD Transport Phase 1 | Gearmotor SEW EURODRIVE R57 DRN80M4/TF | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-17 | 110.3424 | 2.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Ball-bearing 6314-2RS1 PN:03431534 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-17 | 110.3424 | 2.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Nilos ring 6314 ZJV PN:03433034 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-17 | 110.3424 | 2.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Key 10x8x50 St PN:46016050 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-17 | 110.3424 | 2.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Packingset AL-BL 300/350 TEADIT 2005 FDA EC 1935/2004 PN:20803094 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-17 | 110.3424 | 2.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Chain wheel 3/4''-21t-dia38 St PN:CW0202138 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-17 | 110.3424 | 2.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Chain wheel 3/4''-13t-dia35 St PN:CW0201335 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-17 | 110.3424 | 2.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 12B-1 Roller Chain L=43.52in | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-17 | 110.3424 | 2.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Seal PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-22 | 110.3424 | 28.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Ball Bearing PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-22 | 110.3424 | 28.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Lip Seal PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-22 | 110.3424 | 28.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Plain Bearing PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-22 | 110.3424 | 28.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Slide Bearing PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-22 | 110.3424 | 28.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Retainer Ring PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-22 | 110.3424 | 28.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | O' ring PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-22 | 110.3424 | 28.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
105809745 | SIR | Mechanical Seal Fristam 0817330413 | AMM | 2024-08-02 | DONE | 2024-09-16 | 48.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
105809748 | SIR | O-Ring Fristam 0180350376 | AMM | 2024-08-02 | DONE | 2024-09-16 | 48.3424 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| SIR | O-Ring Fristam 0180350029 | AMM | 2024-08-02 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-14 | 48.3424 | 5.3424 | Rosiell Suello |  | OLD | Coffee | TARGET | 1
| SIR | Mechanical Seal Fristam 816310629 | AMM | 2024-08-02 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-14 | 48.3424 | 5.3424 | Rosiell Suello |  | OLD | Coffee | TARGET | 1
| SIR | O-Ring Fristam 180350364 | AMM | 2024-08-02 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-14 | 48.3424 | 5.3424 | Rosiell Suello |  | OLD | Coffee | TARGET | 1
| SIR | O-Ring Fristam 180350022 | AMM | 2024-08-02 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-14 | 48.3424 | 5.3424 | Rosiell Suello |  | OLD | Coffee | TARGET | 1
| SIR | Seal Mechanical Fristam FPE 752/250 VA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | O-ring Firstam FPE 752/250 VA 376 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | O-ring Firstam FPE 752/250 VA 029 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Pneumatic Control Valve 3730-3 | AMM | 2024-07-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-07-01 | 80.3424 | 80.3424 | Zaira April Flores | For docusign Sir JC | OLD | Coffee | TARGET | 1
| SIR | O-Ring Fristam 180350377 Ø253 37x5 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Seal Mechanical Fristam 816330271 9.467a 2K 10V2 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Transmitter Temperature Rosemount 248 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Transmitter Temperature Rosemount 2051TG3A2B21AS5B4Q4 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Transmitter Temperature Rosemount 2051 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Sensor Magnetic Flow Meter Rosemount 8705 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Valve Terminal Festo HY-MPA-FB-VI-MSB6 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Base-sub VMPA1-FB-AP-4-1 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Seal VMPA1-DP | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Electrical Manifold VMPA1-FB-EV-AB | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Electronics VMPA1-FB-EMG-8 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Valve Solenoid VMPA1-M1H-J-PI | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Input CVX-16DE | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Analogue Input CVX-4AE-1 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Analogue Output CPX-2AA-U-I | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Transmitter Pressure UPT-20 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Load cell Controller Minebea PR 5230/02 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Valve Pneumatic Samson 3730-3 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Valve Control Samson 3241-7 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 80.3424 | 80.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Digital Conductivity | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Control Board Pneumatic V70 Think Top | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Control Board Pneumatic V50 Think Top | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Control Unique RV-P | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Flowmeter Magnetic Rosemount | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Sensor Toroidal Conductivity Rosemount | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Power Supply Board for 1056-01 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | O-Ring Cover Fristman 3552/215 B | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Impeller Nut O-Ring | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Seal Mechanical Fristam 3552/215B | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Motor Theo Halter GmbH Elektromotoren | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Unique Mixproof Welded DN 50/50 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Unique Mixproof Welded DN 40/40 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Pneumatic Macainox 3"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Pneumatic Macainox 2"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Pneumatic Ball SS Macainox 2"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Mixproof Unique Mecainox 3-Body ISO-DN 100/110 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Mixproof Unique Mecainox 3-Body ISO-DN 76/76 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Butterfly w/ Actuator LKB-F ISO WELD-38 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Butterfly w/ Actuator LKB-F ISO WELD-51 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Manual Ball Mecainox 1" | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Manual Ball Mecainox 3/4" | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Manual Ball SS Macainox 1"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Non-Return LKC-2 ISO- SMS -51 EPDM | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Non-Return LKC-2 ISO- SMS -76 EPDM | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve ButterFly Macainox 6"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve ButterFly Macainox 4" DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 80.3424 | 66.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | Guide Disc Assy LEMA 425 AZ PN20017164 | AMM | 2024-07-25 | NOT STARTED | 2024-08-14 | 56.3424 | 36.3424 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 0
| IPTA VACUUM PUMP | Guide Disc LEMA 251 9Z BLU 4B PN20044252 | AMM | 2024-07-25 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-18 | 56.3424 | 1.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | Repair Kit Basic LEMA 251 PN65008395 | AMM | 2024-07-25 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-18 | 56.3424 | 1.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | Level indicator LV-300 L=300 LEMA 251 9Z BLU 4B | AMM | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-02 | 56.3424 | 48.3424 | Francis Carlo Tadena | Not included in the qoutation P124-2034-2 | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | Repair Kit Basic LEMA 425 AZ PN65007942 | AMM | 2024-07-25 | NOT STARTED | 2024-08-14 | 56.3424 | 36.3424 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 0
| <X> VACUUM PUMP | Vane wheel impeller assy LEMA PN20017131 | AMM | 2024-07-25 | NOT STARTED | 2024-08-14 | 56.3424 | 36.3424 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 0
| IPTA VACUUM PUMP | Vane wheel impeller assy LEMA PN20072583 | AMM | 2024-07-25 | FULLY SIGNED - FOR ENROLLMENT | 2024-09-18 | 56.3424 | 1.3424 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | Level Indicator LV-300 L=500 LEMA 9Z BLU 4B | AMM | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-14 | 56.3424 | 36.3424 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 0
| IPTA VACUUM PUMP | Motor Sterling SIHI GmbH 8.0KW 1750RPM | AMM | 2024-08-05 | WAITING FOR QUOTATION | 2024-08-10 | 45.3424 | 40.3424 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | Motor Sterling SIHI GmbH 18KW 1765RPM | AMM | 2024-08-05 | WAITING FOR QUOTATION | 2024-08-14 | 45.3424 | 36.3424 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 0
| IPTA VACUUM PUMP | 52W Heat Exchanger for IPTA Vacuum Pump Inpsection & Servicing | MPLAN | 2024-08-05 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-28 | 45.3424 | 22.3424 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GC Van Unloading Facility | 1M Green Coffee Transport Unimaster Dust Collector Inspection | MPLAN | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 59.3424 | 45.3424 | Jenelyn Allado |  | NEW | Coffee | TARGET | 1
| GC Van Unloading Facility | 1W Green Coffee Transport Unimaster Dust Collector Inspection | MPLAN | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 59.3424 | 45.3424 | Jenelyn Allado |  | NEW | Coffee | TARGET | 1
| GC Van Unloading Facility | 1Y Green Coffee Transport Unimaster Dust Collector Inspection | MPLAN | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 59.3424 | 45.3424 | Jenelyn Allado |  | NEW | Coffee | TARGET | 1
| GC Van Unloading Facility | 6M Green Coffee Transport Unimaster Dust Collector Inspection | MPLAN | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 59.3424 | 45.3424 | Jenelyn Allado |  | NEW | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Grease Rivolta GT-2 | AMM | 2024-08-16 | NOT STARTED | 2024-08-16 | 34.3424 | 34.3424 | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | 1
| IPTA VACUUM PUMP | <Heat Exchanger (AMM) Possible plates> | AMM | 2024-08-05 | NOT STARTED | 2024-08-05 | 45.3424 | 45.3424 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | <Heat Exchanger (AMM)> | AMM | 2024-08-05 | NOT STARTED | 2024-08-14 | 45.3424 | 36.3424 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | <Heat Exchanger (MPLAN)> | MPLAN | 2024-08-05 | NOT STARTED | 2024-08-14 | 45.3424 | 36.3424 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 1
| PEC 2020: PE Panel Cooling | <PEC 2020: PE Panel Cooling> | MPLAN | 2024-07-01 | WAITING FOR OTHER DOCS | 2024-07-22 | 80.3424 | 59.3424 | Rosiell Suello | Material list from SE for equipment data | NEW | Coffee | TARGET | 1
| PEC 2020: PE Panel Cooling | <PEC 2020: PE Panel Cooling> | AMM | 2024-07-01 | WAITING FOR OTHER DOCS | 2024-07-22 | 80.3424 | 59.3424 | Rosiell Suello | Material list from SE for equipment data | NEW | Coffee | TARGET | 1
| PEC 2020: Process adaptation | <PEC 2020: Process adaptation> | MPLAN | 2024-07-01 | NOT STARTED | 2024-08-03 | 80.3424 | 47.3424 | Francis Carlo Tadena |  | NEW | Coffee | TARGET | 0
| PEC 2020: Process adaptation | <PEC 2020: Process adaptation> | AMM | 2024-07-01 | NOT STARTED | 2024-08-03 | 80.3424 | 47.3424 | Francis Carlo Tadena |  | NEW | Coffee | TARGET | 0
| FFE-RARE | <FFE-RARE> | AMM | 2024-07-01 | NOT STARTED | 2024-08-03 | 80.3424 | 47.3424 | Francis Carlo Tadena |  | NEW | Coffee | TARGET | 1
| FFE-RARE | <FFE-RARE> | MPLAN | 2024-07-01 | NOT STARTED | 2024-08-03 | 80.3424 | 47.3424 | Francis Carlo Tadena |  | NEW | Coffee | TARGET | 1
| PEC 2020: Spot Cooling | NOTICE DOCUMENT - MPLAN | MPLAN | 2024-07-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-19 | 80.3424 | 31.3424 | Jenelyn Allado | Waiting for docu assessment form to be fully signed by Sir Mark | NEW | Coffee | TARGET | 1
| PEC 2020: Spot Cooling | NOTICE DOCUMENT - AMM | AMM | 2024-07-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-19 | 80.3424 | 31.3424 | Jenelyn Allado | Waiting for docu assessment form to be fully signed by Sir Mark | NEW | Coffee | TARGET | 1
| PACKING VENTILATION | 4W B1V1 CONDITION MONITORING INSPECTION | MPLAN | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-09 | 30.3424 | 10.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| PACKING VENTILATION | 13W B1V1 Condition Inspection of Fan assembly | MPLAN | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-09 | 30.3424 | 10.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| PACKING VENTILATION | 13W B1V1 Inspection of fan bearing lubrication | MPLAN | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-09 | 30.3424 | 10.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| PACKING VENTILATION | 13W B1V1 Servicing Inspection of Motor | MPLAN | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-09 | 30.3424 | 10.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| PACKING VENTILATION | 26W B1V1 Fan Drive Belt Replacement | MPLAN | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-09 | 30.3424 | 10.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| PACKING VENTILATION | 104W B1V1 Fan & Motor Servicing | MPLAN | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-09 | 30.3424 | 10.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| PACKING VENTILATION | Bearing Flange ASAHI UCF208-24 | AMM | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-11 | 30.3424 | 8.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| PACKING VENTILATION | Belt V BANDO A-61 | AMM | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-11 | 30.3424 | 8.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| PACKING VENTILATION | Induction Motor WEG 3HP/3ph/220V/1800rpm | AMM | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-11 | 30.3424 | 8.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| Wet Process Upgrade | <Wet Process Upgrade> | AMM | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena | Already Hand-over, MUEE DONE | OLD | Milks | TARGET | 0
| Wet Process Upgrade | <Wet Process Upgrade> | MPLAN | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena | Already Hand-over, MUEE DONE | OLD | Milks | TARGET | 0
| AFBB Smokestack Upgrade | <AFBB Smokestack Upgrade> | AMM | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena | Ongoing review, Lightning Arrestor Only | OLD | Milks | TARGET | 0
| AFBB Smokestack Upgrade | <AFBB Smokestack Upgrade> | MPLAN | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena | Ongoing review, Lightning Arrestor Only | OLD | Milks | TARGET | 0
| Secondary Packaging Area Ventilation (DHNS) | <Secondary Packaging Area Ventilation (DHNS)> | AMM | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena |  | OLD | Milks | TARGET | 0
| Secondary Packaging Area Ventilation (DHNS) | <Secondary Packaging Area Ventilation (DHNS)> | MPLAN | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena |  | OLD | Milks | TARGET | 0
| ETS 2021: AFBB Heat Recovery System | <ETS 2021: AFBB Heat Recovery System> | AMM | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena | MUEE & MPLAN - for review, Not sure if the manuals are incomplete | OLD | Milks | TARGET | 0
| ETS 2021: AFBB Heat Recovery System | <ETS 2021: AFBB Heat Recovery System> | MPLAN | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena | MUEE & MPLAN - for review, Not sure if the manuals are incomplete | OLD | Milks | TARGET | 0
| Project Elmer (Phase 1) - DHNS | <Project Elmer (Phase 1) - DHNS > | AMM | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena | Already Hand-over by Mimi, Remaining Docs: Punchlist | OLD | Milks | TARGET | 0
| Project Elmer (Phase 1) - DHNS | <Project Elmer (Phase 1) - DHNS > | MPLAN | 2024-08-20 | NOT STARTED |  | 30.3424 |  | Francis Carlo Tadena | Already Hand-over by Mimi, Remaining Docs: Punchlist | OLD | Milks | TARGET | 0
| Homogenizers and HPP Cooling Water Recovery System | Motor EMOD | AMM | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-10 | 30.3424 | 9.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| Homogenizers and HPP Cooling Water Recovery System | Seal Mechanical, FRISTAM FP722 | AMM | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-10 | 30.3424 | 9.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| Homogenizers and HPP Cooling Water Recovery System | O-ring, FRISTAM FP722 | AMM | 2024-08-20 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-09-10 | 30.3424 | 9.3424 | Cogalito July Renz |  | OLD | Milks | TARGET | 1
| Homogenizers and HPP Cooling Water Recovery System | 52W Overhauling of Pump | MPLAN | 2024-08-20 | ON-GOING FIRST DRAFT | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Milks | TARGET | 1
| Homogenizers and HPP Cooling Water Recovery System | 26W Inspection of Pump | MPLAN | 2024-08-20 | ON-GOING FIRST DRAFT | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Milks | TARGET | 1
| Homogenizers and HPP Cooling Water Recovery System | 52W Overhauling of Motor | MPLAN | 2024-08-20 | ON-GOING FIRST DRAFT | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Milks | TARGET | 1
| Homogenizers and HPP Cooling Water Recovery System | 26W Inspection of Motor | MPLAN | 2024-08-20 | ON-GOING FIRST DRAFT | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Milks | TARGET | 1
| UPS Battery Temperature Interlock - 3CBU | <UPS Battery Temperature Interlock - 3CBU > | AMM | 2024-08-20 | NOT STARTED | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Milks | TARGET | 0
| UPS Battery Temperature Interlock - 3CBU | <UPS Battery Temperature Interlock - 3CBU > | MPLAN | 2024-08-20 | NOT STARTED | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Milks | TARGET | 0
| Solar Street Lights | <Solar Street Lights> | AMM | 2024-08-20 | NOT STARTED | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Milks | TARGET | 0
| Solar Street Lights | <Solar Street Lights> | MPLAN | 2024-08-20 | NOT STARTED | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Milks | TARGET | 0
| Final Cooler | <Final cooler AMM> | AMM | 2024-08-20 | NOT STARTED | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| Final Cooler | <Final cooler MPLAN> | MPLAN | 2024-08-20 | NOT STARTED | 2024-09-12 | 30.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | <pump assembly> | AMM | 2024-09-09 | NOT STARTED | 2024-09-12 | 10.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | <mechanical seal> | AMM | 2024-09-09 | NOT STARTED | 2024-09-12 | 10.3424 | 7.3424 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| GC Van Unloading Facility | <recommended spare parts> | AMM | 2024-09-12 | NOT STARTED | 2024-09-12 | 7.3424 | 7.3424 | Francis Carlo Tadena |  | NEW | Coffee | TARGET | 1

## deleted
PART / MPLAN NO. | PROJECT | DESCRIPTION | DOC_TYPE | INIT DATE | STATUS | TIMESTAMP | INIT_AGE (DAYS) | AGE (DAYS) | PIC | REMARKS | PROJECT_TYPE | AREA | TYPE | SWITCH | REMARKS FOR WEEKLY REPORT
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 189041100202 (not found on order conf) | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 133.3647 | 14.3647 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Silverpress flexible tubing - 1089041000201 (not found on order conf) | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 133.3647 | 14.3647 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Silverpress Tubing - 10890812200002 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 133.3647 | 14.3647 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic Flexible Tubing - 1122120500004 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 133.3647 | 14.3647 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Baering Bush DA115 - 1005115004 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 133.3647 | 14.3647 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Thermal Sleeve Braided Fibreglass - 398-896 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 133.3647 | 14.3647 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Oil Level switch | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 133.3647 | 14.3647 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic Internal Gear Pump | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 133.3647 | 14.3647 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Shaft Socket - | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-28 | 133.3647 | 14.3647 | John Carlo Baltazar |  | OLD | Coffee | TARGET | 1

## list
STATUS | TYPE | DOC_TYPE | PIC | AREA | PROJECT | PROJECT_TYPE | doc_status | gen_status | Motor Vibrating VV40B/4
DONE | TARGET | AMM | Alan Cris Caintic | Coffee | <X> VACUUM PUMP | OLD | Complete | NOT-AVAILABLE | Peripheral rVibrating Rods
FULLY SIGNED - FOR ENROLLMENT | ADDITIONAL | MPLAN | Alfred Martin Torcende | Milks | AFBB Smokestack Upgrade | NEW | Lacking | COMPLETE | Switch Limit General Purpose 500V 10A
NOT STARTED |  |  | Allan Cuarteros | IS | AUTOCOMPACTOR |  | No available |  | Hoist Electric ZNK 100 A8/2
ON-GOING FIRST DRAFT |  |  | Andrean Candeloza | Others | ETS 2021: AFBB Heat Recovery System |  | Incomplete |  | Motor Gear Sew SEW R 27 DRN71M4/BE1, Hel
ON-GOING REFLECTING COMMENTS |  |  | April Kaye Uayan |  | FFE-RARE |  |  |  | Sensor Proximity Inductive PA 40mm
ON-GOING ROUTING/REVIEW (DOCUSIGN) |  |  | Camposano Aubrey |  | Final Cooler |  |  |  | Cylinder SMC CP96SDB80-150C Bore Size 80
ON-GOING ROUTING/REVIEW (PHYSICAL) |  |  | Celerito Cardines |  | GC Van Unloading Facility |  |  |  | Controller Unit SMC AS3001F-12
WAITING FOR OTHER DOCS |  |  | Christine Estoque |  | GCCD Transport Phase 1 |  |  |  | Knocker Controller SB-1A SIC Maghammer
WAITING FOR QUOTATION |  |  | Christopher Donguines |  | GCU+ |  |  |  | Knocker Nippon Maghammer SIC-1AS
WAITING FOR STAKEHOLDER INPUT |  |  | Cogalito July Renz |  | Homogenizers and HPP Cooling Water Recovery System |  |  |  | Chain Link
|  |  | Elleh Jipos |  | HYDRAULIC PROJECT |  |  |  | End Bracket
|  |  | Emmanuel Ben Jr. Roa |  | ICIP |  |  |  | Switch Selector 3 10A at 400V 2NO
|  |  | Francis Carlo Tadena |  | IPTA VACUUM PUMP |  |  |  | Switch Selector 12VDC 25A
|  |  | Janeth Jabien |  | PACKING VENTILATION |  |  |  | Switch Pushbutton Momentary 600VAC 10A
|  |  | Jenelyn Allado |  | PEC 2020: PE Panel Cooling |  |  |  | Switch Selector 3 3P CA10A212624FT6V
|  |  | Joel Echem |  | PEC 2020: Process adaptation |  |  |  | Gauge Temp 100mm 0-120C Direct
|  |  | John Carlo Baltazar |  | PEC 2020: Spot Cooling |  |  |  | Relay Safety 1P 24VDC 5-110VDC SPDT
|  |  | John Rey Santander |  | Project Elmer (Phase 1) - DHNS |  |  |  | Relay Em Screw Terminal or Spring Clamp
|  |  | Madeleine Parojinog |  | Secondary Packaging Area Ventilation (DHNS) |  |  |  | Hoist Demag (DC PRO 10-2000 2/1)
|  |  | Marcos Davo-davo |  | SIR |  |  |  | Energy Chaing, IGUS E4.42.20.200
|  |  | Maria Jean Walag |  | Solar Street Lights
|  |  | Marian Louise Rosaldo |  | UPS Battery Temperature Interlock - 3CBU
|  |  | Marian Zarate |  | WATER HEATER
|  |  | Mark Anthony Pana |  | Wet Process Upgrade
|  |  | Marlon Pingoy |  | Example Project
Merachell Escobido
Rosiell Suello
Zaira April Flores

## legend
PART / MPLAN NO. | MPLAN number or Material number from the maintenance planner after enrollment.
PROJECT | Project name where the spare parts is for.
DESCRIPTION | Description of the spare part.
DOC_TYPE | Use to filter AMM AND MPLAN.
INIT DATE | The date when the document was first started.
STATUS | Status of the document in terms of processing and approval.
TIMESTAMP | The date of the latest updated status.
INIT_AGE (DAYS)
AGE (DAYS)
PIC
REMARKS
PROJECT_TYPE
AREA
TYPE
SWITCH
REMARKS FOR WEEKLY REPORT

## SUMMARY
OVERALL PROGRESS (WEEK 37) COFFEE | MPLAN |  |  | SPARE PARTS
| 100% |  |  | 100%
| 24.44% |  |  | #DIV/0!
WEEK36 | 39.53% |  |  | 51.88%
WEEK35 | 39.53% |  |  | 51.88%
PROJECTS | MPLAN |  |  | SPARE PARTS
| LISTED | DONE (FULLY SIGNED FOR ENROLLMENT) | DONE (ENROLLED) | LISTED | DONE (FULLY SIGNED FOR ENROLLMENT) | DONE
AUTOCOMPACTOR | 17 | 6 | 11
HYDRAULIC PROJECT | 11
GCU+ | 1
WATER HEATER | 1
GCCD Transport Phase 1 | 6
SIR | 9
IPTA VACUUM PUMP | 2
<X> VACUUM PUMP | 84
ICIP | 9
GC Van Unloading Facility | 4
PEC 2020: PE Panel Cooling | 1
PEC 2020: Process adaptation | 1
FFE-RARE | 1
PEC 2020: Spot Cooling | 1
Final Cooler | 1
TOTAL | 45 | 6 | 11 | 0 |  | 0
Legend:
Done = MPLAN is fully signed
Done = AMM fully signed & with material number
AUTOCOMPACTOR
HYDRAULIC PROJECT
GCU+
WATER HEATER
GCCD Transport Phase 1
SIR
IPTA VACUUM PUMP
<X> VACUUM PUMP
ICIP
GC Van Unloading Facility
PEC 2020: PE Panel Cooling
PEC 2020: Process adaptation
FFE-RARE
PEC 2020: Spot Cooling
Final Cooler
PACKING VENTILATION
Wet Process Upgrade
AFBB Smokestack Upgrade
Secondary Packaging Area Ventilation (DHNS)
ETS 2021: AFBB Heat Recovery System
Project Elmer (Phase 1) - DHNS
Homogenizers and HPP Cooling Water Recovery System
UPS Battery Temperature Interlock - 3CBU
Solar Street Lights
IPTA VACUUM PUMP
PACKING VENTILATION
PEC 2020: PE Panel Cooling