## Slide 1: Improvement of Load Cell Frame
AUTOMATIC COMPACTOR

## Slide 2
METHODOLOGY
  Install temporary support member below the beam that will be aligned
  Perform cutting on both ends of the beam joint.
  Align beam and perform initial welding. This will be the first checking of the beam level with TBMC and Megantech.
  Conduct first phase of welding. Do not full weld on one side. See details of weld sequence.
  TBMC and Megantech will conduct the 2nd beam alignment verification. If beam is still not horizontally aligned, redo the process.

## Slide 3
REPLACEMENT METHOD:
1. Install temporary support member below the beam that will be aligned
Temporary Support
Beam to be aligned

## Slide 4
REPLACEMENT METHOD:
2. Perform cutting on both ends of the beam joint.
Temporary Support
Joint to cut

## Slide 5
REPLACEMENT METHOD:
3. Align beam and perform initial welding. This will be the first checking of the beam level with TBMC and Megantech.
Temporary Support
Use level bar to verify beam alignment, if OK, proceed with the welding

## Slide 6
REPLACEMENT METHOD:
4. Conduct first phase of welding. Do not full weld on one side. See details of weld sequence.
Temporary Support
1st
4th
3rd
2nd
8th
8th
7th
7th
5th
5th
6th
6th

## Slide 7
REPLACEMENT METHOD:
5. TBMC and Megantech will conduct the 2nd beam alignment verification. If beam is still not horizontally aligned, redo the process.
Temporary Support
Use level bar to verify beam alignment, if OK, proceed with the finishing activities

## Slide 8
WARPING SAMPLE IMAGES
WARPING

## Slide 9
REPLACEMENT METHOD:
4. Conduct first phase of welding. Do not full weld on one side. See details of weld sequence.
Temporary Support

## Slide 10
END