## Sheet1
Note: This tool is intended to identify potential issues experienced during Start-up which ultimately cause delays. |  |  | VSU Risk Assessment Tool
Project Name : Safety Upgrade - Punchlist closure | [6 empty] | Assessment Date/Time:
Contractor: MICHROM | [6 empty] | Start Date:
PO No. | [6 empty] | End Date:
No. | Specific Activity |  | Location |  | Identified Risk causing VSU delays | Controls ( Startup Checklists, Procedures, etc ) |  | Remarks ( Check if needed )
| Alignment of tubings for punchlist items 10, 13, 14, 45, 46. |  | E54 Hydraulic System (1st & 2nd Floor) |  | M.01, M.02 | See checklist |  | Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Tick: Identified Risk causing VSU delays
| Mechanical |  |  | Electrical |  |  | Instrumentation & Automation
| M.01 External Leaks ( Welds, Flanges, Valves, etc ) |  |  | E.01 No Power ( Mis-Tapping, Disconnections, … ) |  |  | IA.01 No/wrong Signal ( Mis-Tapping, Disconnections,…)
| M.02 Fouled Lines ( Dirt, Debris, etc ) |  |  | E.02 Wrong Rotation |  |  | IA.02 Incorrect Sequence / Response
| M.03 Presence of Foreign Body ( inside Pipes, equipt ) |  |  | E.03 Burnt / Malfunctioned Components |  |  | IA.03 Insufficent Interlocks
| M.04 No, Insufficent Flow of Utilities ( Steam, Water, etc ) |  |  | E.04 … |  |  | IA.04 Inaccurate Data ( No calibration, etc )
| M.05 Excessive Vibration |  |  | E.05 … |  |  | IA.05 …
| M.06 Stucked Moving Parts |  |  | E.06 … |  |  | IA.06 …
|  | Performing Authority |  | Approved by Project Engineer |  |  | Noted by Project Head
Date & Time:
Signature
Name:

## Sheet2
EMAIL USE DISCLAIMER