## Sheet1
Note: This tool is intended to identify potential issues experienced during Start-up which ultimately cause delays. |  |  | VSU Risk Assessment Tool
Project Name : Compactor - Improvement of load cell frame | [6 empty] | Assessment Date/Time:
Contractor: MEGANTECH | [6 empty] | Start Date:
PO No. | [6 empty] | End Date:
No. | Specific Activity |  | Location |  | Identified Risk causing VSU delays | Controls ( Startup Checklists, Procedures, etc ) |  | Remarks ( Check if needed )
| Full welding of load cell structure |  | Compactor Load Cell Frame |  | Damaged load cell | Electrical group must make sure that all electrical lines relating to the load cell is disconnected. |  | Checklist Controls
| Misaligned structure after full welding. |  | Compactor Load Cell Frame |  | Misaligned beam | See checklist for level checking timing |  | Checklist Controls
| Improper alignment of test stones holder. |  | Compactor Load Cell Frame |  | Misaligned test stones holder | Conduct test lifting of test stones before and after fixing the bolts. |  | Checklist Controls
| Damaged nearby electrical wires and other components near the welding location. |  | Compactor Load Cell Frame |  | Absence of welding blanket | Provide welding blankets and do not proceed if no welding blankets is available. |  | Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Checklist Controls
Tick: Identified Risk causing VSU delays
| Mechanical |  |  | Electrical |  |  | Instrumentation & Automation
| M.01 External Leaks ( Welds, Flanges, Valves, etc ) |  |  | E.01 No Power ( Mis-Tapping, Disconnections, … ) |  |  | IA.01 No/wrong Signal ( Mis-Tapping, Disconnections,…)
| M.02 Fouled Lines ( Dirt, Debris, etc ) |  |  | E.02 Wrong Rotation |  |  | IA.02 Incorrect Sequence / Response
| M.03 Presence of Foreign Body ( inside Pipes, equipt ) |  |  | E.03 Burnt / Malfunctioned Components |  |  | IA.03 Insufficent Interlocks
| M.04 No, Insufficent Flow of Utilities ( Steam, Water, etc ) |  |  | E.04 … |  |  | IA.04 Inaccurate Data ( No calibration, etc )
| M.05 Excessive Vibration |  |  | E.05 … |  |  | IA.05 …
| M.06 Stucked Moving Parts |  |  | E.06 … |  |  | IA.06 …
|  | Performing Authority |  | Approved by Project Engineer |  |  | Noted by Project Head
Date & Time:
Signature
Name:

## Sheet2
EMAIL USE DISCLAIMER