## RAW
PART / MPLAN NO. | PROJECT | DESCRIPTION | DOC_TYPE | INIT DATE | STATUS | TIMESTAMP | INIT_AGE (DAYS) | AGE (DAYS) | PIC | REMARKS | PROJECT_TYPE | AREA | TYPE | SWITCH
| AUTOCOMPACTOR | DOOR FLAP PNUEMATIC CYLINDER - REPAIR | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 14W ENERGY CHAIN - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 6M DRIVE GEAR MOTOR - PM INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3Y DRIVE GEAR MOTOR PM CHANGE GEAR OIL | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3W VIBRATOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3W DRIVE GEAR MOTOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3W COMPACTOR HOIST - PM - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3M VIBRATOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3M KNOCKER HAMMER Inspection | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3M DRIVE GEAR MOTOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 3M COMPACTOR HOIST - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1Y VIBRATOR MOTOR - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1Y DRIVE GEAR MOTOR - INSPECTION - | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1Y COMPACTOR HOIST - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1M VIBRATOR MOTOR - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1M KNOCKER HAMMER Inspection | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | 1D VIBRATOR MOTOR - INSPECTION | MPLAN | 2024-03-01 | DONE | 2024-08-02 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | EXPULSION VALVE CYLINDER SERVICING E54 2.5Y | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC BYPASS VALVE SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC LID CYLINDER SERVICING E54 2Y | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC LID LOCK CYLINDER SERVICING E542Y | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC OVER CENTRE VALVE SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC PRESSURE RELIEF VALVE SERVICING | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC QUICK ACTING VALVE SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC SPEED REGULATOR VALVE SERVICING | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC STOP VALVE (HS-22W-6M) SERVICING | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC VALVE (HS-43W-6) SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | HYDRAULIC VALVE (HS-43W-6V) SERVICING E54 | MPLAN | 2024-03-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-14 | 169.6493 | 3.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCU+ | <to utilize existing MPLAN> | MPLAN | 2024-03-01 | DONE | 2024-07-29 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | <to utilize existing MPLAN> | MPLAN | 2024-03-01 | DONE | 2024-07-29 | 169.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 2Y (15000H) Diverter Maintenance | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 108.6493 | 14.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 6M (4000H) Diverter Maintenance | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 108.6493 | 14.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 3Y DRIVE GEAR MOTOR PM | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 108.6493 | 14.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 6M DRIVE GEAR MOTOR PM | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 108.6493 | 14.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Rotary Valve GL 300 - 3M (2500OH) Inspection | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 108.6493 | 14.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Rotary Valve GL 300 - 12M (10000OH) Servicing | MPLAN | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-08-03 | 108.6493 | 14.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Sealing or Quenching Liquid Check 2Y | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Sealing or Quenching Liquid Check 1D | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Replacement of Shaft Seal 2Y | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Replacement of Motor 2Y (Existing MPLAN) | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Calibration of Pressure Transmitter 52W | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Replacement of Valve Terminal | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | 3M 2000L Sludge Tank Agitator Gearbox - INSPECTION | MPLAN | 2024-06-01 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 77.6493 | 12.6493 | Jenelyn Allado | Hand over to Maam Allado for review. | OLD | Coffee | TARGET | 1
| SIR | 3Y 2000L Sludge Tank Agitator Gearbox - CHANGE GEAR OIL | MPLAN | 2024-06-01 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 77.6493 | 12.6493 | Jenelyn Allado | Hand over to Maam Allado for review. | OLD | Coffee | TARGET | 1
| SIR | 6M 2000L Sludge Tank Agitator Gearbox - INSPECTION | MPLAN | 2024-06-01 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 77.6493 | 12.6493 | Jenelyn Allado | Hand over to Maam Allado for review. | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | 12W VACUUM PUMP LEMA 251 9Z Inspection | MPLAN | 2024-07-08 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-09 | 40.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | 12W VACUUM PUMP LEMA 425 AZ Inspection | MPLAN | 2024-07-08 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-09 | 40.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | MPlan1_Butterfly Valves.FS | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | MPlan2_Mixproof Valves.FS | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | MPlan3_Pneumatic Actuator Replacement.FS | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Replacement of Motor - 801 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Replacement of Shaft Seal - 803 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Sealing or Quenching Liquid Check - 802 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Replacement of Motor - 798 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Replacement of Shaft Seal - 800 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Sealing or Quenching Liquid Check - 799 | MPLAN | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-01-01 | 229.6493 | 229.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Nozzle Spray 1/4 | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 229.6493 | 138.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hoist Control Set DEMAG | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 229.6493 | 138.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hoist Electric DEMAG | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 229.6493 | 138.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hose pre-wet ESI-NEP 6 | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 229.6493 | 138.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hose water nipple union | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 229.6493 | 138.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hose water pipe union | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 229.6493 | 138.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Hose water nipple union ESIC BSP 4mtrs | AMM | 2024-01-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 229.6493 | 138.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Motor vibrating flap ESIC VV40B | AMM | 2024-01-01 | DONE | 2024-04-01 | 229.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Valve Solenoid Spray | AMM | 2024-01-01 | DONE | 2024-04-01 | 229.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Valve Solenoid Spray 1 1/2" DP100 | AMM | 2024-01-01 | DONE | 2024-04-01 | 229.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Chain Duplex ESIC | AMM | 2024-01-01 | DONE | 2024-04-01 | 229.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Motor Gear SW Helical | AMM | 2024-01-01 | DONE | 2024-04-01 | 229.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | MaghSpare Partser Knocker Nippon SIC-1AS | AMM | 2024-01-01 | DONE | 2024-04-01 | 229.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | MaghSpare Partser Knocker Nippon SB-1A | AMM | 2024-01-01 | DONE | 2024-04-01 | 229.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Actuator Door Flap ESIC MDUH 1003 | AMM | 2024-01-01 | DONE | 2024-04-01 | 229.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | Switch Proximity | AMM | 2024-01-01 | DONE | 2024-04-01 | 229.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| AUTOCOMPACTOR | SKF Bearing FYTB 15 FM | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | John Rey Santander |  | OLD | Coffee | ADDITIONAL | 1
| AUTOCOMPACTOR | Spring Compression, OD 50-51mm 100mm L | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-04-01 | 108.6493 | 138.6493 | Jenelyn Allado |  | OLD | Coffee | ADDITIONAL | 1
| AUTOCOMPACTOR | Cylinder Pneumatic 160x100 mm 12kN Festo | AMM | 2024-05-01 | DONE | 2024-04-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | 1
| AUTOCOMPACTOR | Hose PTFE Exitflex EF179 1/4" OL=30cm | AMM | 2024-05-01 | DONE | 2024-04-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | 1
| AUTOCOMPACTOR | Vibrator Assembly | AMM | 2024-05-01 | DONE | 2024-04-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | ADDITIONAL | 1
| HYDRAULIC PROJECT | Hydraulic cylinder - Expulsion valve - D130L09E0254028 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Tubing Flexible Compair 1089041000205 1000mm nipples FL6.35/FL6.35, Inox | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1089041050201 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1178012011 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2318N001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2018N002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2102N001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V2218N001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - 1118072 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE MATERIAL FOR EXPULSION VALVE OPERATION - V1502A001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - D150L11C0330019 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1122120700002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1122120800003 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - V2818B001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - V2418B005 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1089040850202 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1089040950202 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1115006144 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - D090L11C0155007 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1122120800002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1122120850002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040570202 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - E050A05F0020012 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Silverpress Flexible Tubing - 1089040550204 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - E125B09E0010124 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - 1089041100202 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1119002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1116014 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1096160003 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1107006 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 10990016002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1107007 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079D130L10014 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079D150L12011 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079D090L12009 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2018002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2118002 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079E125A10042 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V0100001 | AMM | 2024-05-01 | DONE | 2024-07-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hose Flex Compair 1122120800001 800mm type: 15L-1ST-15K90L, 800 mm long | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 108.6493 | 9.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 189041100202 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 108.6493 | 9.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic valve - V2318N002 type: HS-4/3W-6 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 108.6493 | 9.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic valve - V2318N004 type: HS-2/2W-6/M | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 108.6493 | 9.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Pneum.- throttle-check valve - 1135016001 type: DRV-18 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 108.6493 | 9.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic solenoid valve 4/2 - 1096000022 type: MS-W 4/2W-10 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 108.6493 | 9.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Stiffener sleeve INOX - 1115006061 Type: SO 50003-6-4 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 108.6493 | 9.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Repair kit for pneum. locking-cylinder - 1079E050A06008 V50-20EdK/spez.9 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-08 | 108.6493 | 9.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hose Flexible Compair 1122120950002 950mm | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1178012012 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE EXPULSION VALVE CYLINDER - 1115006117 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE LID CYLINDER - 1089081200001 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040610201 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040630201 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE RING CYLINDER AND RING LOCK CYLINDER "VH2" - 1089040500205 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - 1089040950203 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | SPARE FILTER LOCK CYLINDER - 1115006497 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1096100001 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1144007 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1115006439 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2318002 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2318001 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2118001 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1090V2418004 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | GENERALLY SPARES FOR HYDRAULIC SYSTEM - 1079E125A10041 | AMM | 2024-05-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-29 | 108.6493 | 19.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Silverpress flexible tubing - 1089041000201 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Silverpress Tubing - 10890812200002 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic Flexible Tubing - 1122120500004 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Baering Bush DA115 - 1005115004 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Thermal Sleeve Braided Fibreglass - 398-896 | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Oil Level switch | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Hydraulic Internal Gear Pump | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Shaft Socket - | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| HYDRAULIC PROJECT | Suction filter - 10990040001 type: S45 - G1"-A | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 108.6493 | 8.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| GCU+ | Gasket Klinger C4408 107x52x1.5mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| GCU+ | Gasket Klinger C4408 145x80x1.5mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| GCU+ | Gasket Klinger C4408 107x50x1.5mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| GCU+ | Gasket Steelflon 98x50x2mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | Gasket head Ginox 3813/22A 735x3mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | Gasket head Ginox 3813/22A 585x3mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | Gasket head Ginox 3813/22B 735x3mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | Gasket head Ginox 3813/22B 585x3mm | AMM | 2024-05-01 | DONE | 2024-05-01 | 108.6493 |  | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| WATER HEATER | 3/4"W Flanges Stud A193 Gr B7 (ZN) SET (+ 3/4"W Stud nuts ASTM A184 Gr 2H DIN-934,3/4"W Stud washer HV140 (ZN) dia21 DIN125) | AMM | 2024-05-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-03 | 108.6493 | 14.6493 | John Rey Santander | Forwarded to Maam Jen for review last July 4 but no feedback. Decided to proceed with docusign. | OLD | Coffee | ADDITIONAL | 1
| GCCD Transport Phase 1 | Gearmotor SEW EURODRIVE R57 DRN80M4/TF | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 77.6493 | 8.6493 | John Rey Santander |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Ball-bearing 6314-2RS1 PN:03431534 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 77.6493 | 108.6493 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Nilos ring 6314 ZJV PN:03433034 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 77.6493 | 108.6493 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Key 10x8x50 St PN:46016050 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 77.6493 | 108.6493 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Packingset AL-BL 300/350 TEADIT 2005 FDA EC 1935/2004 PN:20803094 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 77.6493 | 108.6493 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Chain wheel 3/4''-21t-dia38 St PN:CW0202138 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 77.6493 | 108.6493 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Chain wheel 3/4''-13t-dia35 St PN:CW0201335 | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-05-01 | 77.6493 | 108.6493 | Jenelyn Allado | Only Maam Allado and Sir JC is the lacking signatures. | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | 12B-1 Roller Chain L=43.52in | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-09 | 77.6493 | 8.6493 | John Rey Santander |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Seal PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 77.6493 | 1.6493 | John Rey Santander |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Ball Bearing PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 77.6493 | 1.6493 | John Rey Santander |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Lip Seal PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 77.6493 | 1.6493 | John Rey Santander |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Plain Bearing PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 77.6493 | 1.6493 | John Rey Santander |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Slide Bearing PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 77.6493 | 1.6493 | John Rey Santander |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | Retainer Ring PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 77.6493 | 1.6493 | John Rey Santander |  | OLD | Coffee | TARGET | 1
| GCCD Transport Phase 1 | O' ring PTD II 125 Diverter valve | AMM | 2024-06-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 77.6493 | 1.6493 | John Rey Santander |  | OLD | Coffee | TARGET | 1
817330413 | SIR | Spare mec. seal 9.667a 2K 10V2/2N 5V2 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
180350376 | SIR | O-Ring 376 ARP Ø247,02x5,33 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
180350029 | SIR | O-Ring 029 ARP Ø37,82x1,78 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
817330413 | SIR | Spare mec. seal 9.667a 2K 10V2/2N 5V2 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
180350376 | SIR | O-Ring 376 ARP Ø247,02x5,33 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
180350029 | SIR | O-Ring 029 ARP Ø37,82x1,78 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
816310629 | SIR | Spare mec. seal 9.468 2N 5V2 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
180350364 | SIR | O-Ring 364 ARP Ø170,82x5,33 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
180350022 | SIR | O-Ring 022 ARP Ø25,12x1,78 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
816330271 | SIR | Seal Mechanical Fristam (Model: Fristam 752/250 VA) | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
1803500377 | SIR | O-Ring Ø253 37x5 | AMM | 2024-08-02 | WAITING FOR QUOTATION | 2024-08-02 | 15.6493 | 15.6493 | Zaira April Flores | Zaira, waiting for supplier's qoutation | OLD | Coffee | TARGET | 1
| SIR | Seal Mechanical Fristam FPE 752/250 VA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | O-ring Firstam FPE 752/250 VA 376 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | O-ring Firstam FPE 752/250 VA 029 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Pneumatic Control Valve 3730-3 | AMM | 2024-07-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-07-01 | 47.6493 | 47.6493 | Zaira April Flores | For docusign Sir JC | OLD | Coffee | TARGET | 1
| SIR | O-Ring Fristam 180350377 Ø253 37x5 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Seal Mechanical Fristam 816330271 9.467a 2K 10V2 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Transmitter Temperature Rosemount 248 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Transmitter Temperature Rosemount 2051TG3A2B21AS5B4Q4 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Transmitter Temperature Rosemount 2051 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Sensor Magnetic Flow Meter Rosemount 8705 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Valve Terminal Festo HY-MPA-FB-VI-MSB6 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Base-sub VMPA1-FB-AP-4-1 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Seal VMPA1-DP | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Electrical Manifold VMPA1-FB-EV-AB | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Electronics VMPA1-FB-EMG-8 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Valve Solenoid VMPA1-M1H-J-PI | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Input CVX-16DE | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Analogue Input CVX-4AE-1 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Module Analogue Output CPX-2AA-U-I | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Transmitter Pressure UPT-20 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Load cell Controller Minebea PR 5230/02 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Valve Pneumatic Samson 3730-3 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| SIR | Valve Control Samson 3241-7 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-01 | 47.6493 | 47.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Digital Conductivity | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Control Board Pneumatic V70 Think Top | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Control Board Pneumatic V50 Think Top | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Control Unique RV-P | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Flowmeter Magnetic Rosemount | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Sensor Toroidal Conductivity Rosemount | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Power Supply Board for 1056-01 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | O-Ring Cover Fristman 3552/215 B | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Impeller Nut O-Ring | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Seal Mechanical Fristam 3552/215B | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Motor Theo Halter GmbH Elektromotoren | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Unique Mixproof Welded DN 50/50 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Unique Mixproof Welded DN 40/40 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Pneumatic Macainox 3"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Pneumatic Macainox 2"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Pneumatic Ball SS Macainox 2"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Mixproof Unique Mecainox 3-Body ISO-DN 100/110 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Mixproof Unique Mecainox 3-Body ISO-DN 76/76 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Butterfly w/ Actuator LKB-F ISO WELD-38 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Butterfly w/ Actuator LKB-F ISO WELD-51 | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Manual Ball Mecainox 1" | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Manual Ball Mecainox 3/4" | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Manual Ball SS Macainox 1"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Non-Return LKC-2 ISO- SMS -51 EPDM | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve Non-Return LKC-2 ISO- SMS -76 EPDM | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve ButterFly Macainox 6"DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| ICIP | Valve ButterFly Macainox 4" DIA | AMM | 2024-07-01 | FULLY SIGNED - FOR ENROLLMENT | 2024-07-15 | 47.6493 | 33.6493 | Jenelyn Allado |  | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | Guide Disc Assy LEMA 425 AZ PN20017164 | AMM | 2024-07-25 | ON-GOING FIRST DRAFT | 2024-08-14 | 23.6493 | 3.6493 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | Guide Disc LEMA 251 9Z BLU 4B PN20044252 | AMM | 2024-07-25 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 23.6493 | 1.6493 | John Rey Santander | Already have qoutation, waiting for guide disc to be included | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | Repair Kit Basic LEMA 251 PN65008395 | AMM | 2024-07-25 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 23.6493 | 1.6493 | John Rey Santander | Already have qoutation, waiting for guide disc to be included | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | Level indicator LV-300 L=300 LEMA 251 9Z BLU 4B | AMM | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-02 | 23.6493 | 15.6493 | Francis Carlo Tadena | Not included in the qoutation P124-2034-2 | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | Repair Kit Basic LEMA 425 AZ PN65007942 | AMM | 2024-07-25 | ON-GOING FIRST DRAFT | 2024-08-14 | 23.6493 | 3.6493 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | Vane wheel impeller assy LEMA PN20017131 | AMM | 2024-07-25 | ON-GOING FIRST DRAFT | 2024-08-14 | 23.6493 | 3.6493 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | Vane wheel impeller assy LEMA PN20072583 | AMM | 2024-07-25 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-16 | 23.6493 | 1.6493 | John Rey Santander | Already have qoutation, waiting for guide disc to be included | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | Level Indicator LV-300 L=500 LEMA 9Z BLU 4B | AMM | 2024-07-25 | WAITING FOR QUOTATION | 2024-08-14 | 23.6493 | 3.6493 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | Motor Sterling SIHI GmbH 8.0KW 1750RPM | AMM | 2024-08-05 | WAITING FOR QUOTATION | 2024-08-10 | 12.6493 | 7.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | Motor Sterling SIHI GmbH 18KW 1765RPM | AMM | 2024-08-05 | WAITING FOR QUOTATION | 2024-08-14 | 12.6493 | 3.6493 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | <Heat Exchanger (AMM)> | AMM | 2024-08-05 | NOT STARTED | 2024-08-05 | 12.6493 | 12.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| IPTA VACUUM PUMP | 52W Heat Exchanger for IPTA Vacuum Pump Inpsection & Servicing | MPLAN | 2024-08-05 | NOT STARTED | 2024-08-05 | 12.6493 | 12.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | <Heat Exchanger (AMM)> | AMM | 2024-08-05 | NOT STARTED | 2024-08-14 | 12.6493 | 3.6493 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 1
| <X> VACUUM PUMP | <Heat Exchanger (MPLAN)> | MPLAN | 2024-08-05 | NOT STARTED | 2024-08-14 | 12.6493 | 3.6493 | Francis Carlo Tadena | These pump is not for IPTA as per Sir Chris | OLD | Coffee | TARGET | 1
| GC Van Unloading Facility | 1M Green Coffee Transport Unimaster Dust Collector Inspection | MPLAN | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 26.6493 | 12.6493 | Jenelyn Allado |  | NEW | Coffee | TARGET | 1
| GC Van Unloading Facility | 1W Green Coffee Transport Unimaster Dust Collector Inspection | MPLAN | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 26.6493 | 12.6493 | Jenelyn Allado |  | NEW | Coffee | TARGET | 1
| GC Van Unloading Facility | 1Y Green Coffee Transport Unimaster Dust Collector Inspection | MPLAN | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 26.6493 | 12.6493 | Jenelyn Allado |  | NEW | Coffee | TARGET | 1
| GC Van Unloading Facility | 6M Green Coffee Transport Unimaster Dust Collector Inspection | MPLAN | 2024-07-22 | ON-GOING ROUTING/REVIEW (PHYSICAL) | 2024-08-05 | 26.6493 | 12.6493 | Jenelyn Allado |  | NEW | Coffee | TARGET | 1
| PEC 2020: PE Panel Cooling | <all MPLAN> | MPLAN | 2024-07-01 | WAITING FOR OTHER DOCS | 2024-07-22 | 47.6493 | 26.6493 | Rosiell Suello | Material list from SE for equipment data | NEW | Coffee | TARGET | 0
| PEC 2020: PE Panel Cooling | <all AMM> | AMM | 2024-07-01 | WAITING FOR OTHER DOCS | 2024-07-22 | 47.6493 | 26.6493 | Rosiell Suello | Material list from SE for equipment data | NEW | Coffee | TARGET | 1
| PEC 2020: Process adaptation | <all> |  | 2024-07-01 | NOT STARTED | 2024-08-03 | 47.6493 | 14.6493 | Francis Carlo Tadena |  | NEW | Coffee | TARGET | 0
| FFE-RARE | <all> |  | 2024-07-01 | NOT STARTED | 2024-08-03 | 47.6493 | 14.6493 | Francis Carlo Tadena |  | NEW | Coffee | TARGET | 0
| PEC 2020: Spot Cooling | <Dosusign to inform stakeholders of the unnecessary MPLAN> | MPLAN | 2024-07-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-10 | 47.6493 | 7.6493 | John Rey Santander | Waiting for docu assessment form to be fully signed by Sir Mark | NEW | Coffee | TARGET | 1
| PEC 2020: Spot Cooling | <Dosusign to inform stakeholders of the unnecessary AMM> | AMM | 2024-07-01 | ON-GOING ROUTING/REVIEW (DOCUSIGN) | 2024-08-10 | 47.6493 | 7.6493 | John Rey Santander | Waiting for docu assessment form to be fully signed by Sir Mark | NEW | Coffee | TARGET | 1
|  | <milks 1> |  |  | NOT STARTED |  |  |  | Francis Carlo Tadena |  |  | Milks | TARGET
|  | <milks 2> |  |  | NOT STARTED |  |  |  | Francis Carlo Tadena |  |  | Milks | TARGET
|  | <milks 3> |  |  | NOT STARTED |  |  |  | Francis Carlo Tadena |  |  | Milks | TARGET
|  | <milks 4> |  |  | NOT STARTED |  |  |  | Francis Carlo Tadena |  |  | Milks | TARGET
|  | <milks 5> |  |  | NOT STARTED |  |  |  | Francis Carlo Tadena |  |  | Milks | TARGET
| HYDRAULIC PROJECT | Grease Rivolta GT-2 | AMM | 2024-08-16 | NOT STARTED | 2024-08-16 | 1.6493 | 1.6493 | Francis Carlo Tadena |  | OLD | Coffee | TARGET | 1

## Sheet4
STATUS | Count of STATUS
ON-GOING FIRST DRAFT | 4 | 3
WAITING FOR OTHER DOCS | 4 | 2
NOT STARTED | 5 | 12
ON-GOING ROUTING/REVIEW (PHYSICAL) | 7 | 9
WAITING FOR QUOTATION | 16 | 15
ON-GOING ROUTING/REVIEW (DOCUSIGN) | 27 | 40
DONE | 89 | 78
FULLY SIGNED - FOR ENROLLMENT | 95 | 106

## list
STATUS | TYPE | DOC_TYPE | PIC | AREA | PROJECT | PROJECT_TYPE | doc_status | gen_status | Motor Vibrating VV40B/4
DONE | TARGET | AMM | Alan Cris Caintic | Coffee | AUTOCOMPACTOR | OLD | Complete | NOT-AVAILABLE | Peripheral rVibrating Rods
FULLY SIGNED - FOR ENROLLMENT | ADDITIONAL | MPLAN | Alfred Martin Torcende | Milks | FFE-RARE | NEW | Lacking | COMPLETE | Switch Limit General Purpose 500V 10A
NOT STARTED |  |  | Allan Cuarteros | IS | GC Van Unloading Facility |  | No available |  | Hoist Electric ZNK 100 A8/2
ON-GOING FIRST DRAFT |  |  | Andrean Candeloza | Others | GCCD Transport Phase 1 |  | Incomplete |  | Motor Gear Sew SEW R 27 DRN71M4/BE1, Hel
ON-GOING REFLECTING COMMENTS |  |  | April Kaye Uayan |  | GCU+ |  |  |  | Sensor Proximity Inductive PA 40mm
ON-GOING ROUTING/REVIEW (DOCUSIGN) |  |  | Celerito Cardines |  | HYDRAULIC PROJECT |  |  |  | Cylinder SMC CP96SDB80-150C Bore Size 80
ON-GOING ROUTING/REVIEW (PHYSICAL) |  |  | Christine Estoque |  | ICIP |  |  |  | Controller Unit SMC AS3001F-12
WAITING FOR OTHER DOCS |  |  | Christopher Donguines |  | PEC 2020: PE Panel Cooling |  |  |  | Knocker Controller SB-1A SIC Maghammer
WAITING FOR QUOTATION |  |  | Elleh Jipos |  | PEC 2020: Process adaptation |  |  |  | Knocker Nippon Maghammer SIC-1AS
WAITING FOR STAKEHOLDER INPUT |  |  | Emmanuel Ben Jr. Roa |  | PEC 2020: Spot Cooling |  |  |  | Chain Link
|  |  | Francis Carlo Tadena |  | SIR |  |  |  | End Bracket
|  |  | Janeth Jabien |  | WATER HEATER |  |  |  | Switch Selector 3 10A at 400V 2NO
|  |  | Jenelyn Allado |  | IPTA VACUUM PUMP |  |  |  | Switch Selector 12VDC 25A
|  |  | Joel Echem |  | <X> VACUUM PUMP |  |  |  | Switch Pushbutton Momentary 600VAC 10A
|  |  | John Carlo Baltazar | [5 empty] | Switch Selector 3 3P CA10A212624FT6V
|  |  | John Rey Santander | [5 empty] | Gauge Temp 100mm 0-120C Direct
|  |  | Madeleine Parojinog | [5 empty] | Relay Safety 1P 24VDC 5-110VDC SPDT
|  |  | Maria Jean Walag | [5 empty] | Relay Em Screw Terminal or Spring Clamp
|  |  | Marian Louise Rosaldo | [5 empty] | Hoist Demag (DC PRO 10-2000 2/1)
|  |  | Marian Zarate | [5 empty] | Energy Chaing, IGUS E4.42.20.200
Mark Anthony Pana
Marlon Pingoy
Merachell Escobido
Zaira April Flores
Rosiell Suello