## UPDATE MEETING
ACTION STATUS INDICATOR - Coffee Process Mechanical ASI | [8 empty] | 2024-06-29 14:58
Last Updated:
2024-06-29 14:58
Important : Must enter MEETING DATE for the template to keep track the status of action plan
No. | Sub | Project | Date | Action Plan | Who | Support | Planned | Remarks | Status
1 |  | SCRF |  | Proposed modification drawing for E54 SCRF | FCT | FCT | Wk 22 Wk 23 | On-going approval, require time to discuss with Sir JC. To confirm Sir Mark if Sir JC has alloted 1 hour per week to discuss document for docusign. | Done
2 |  | SCRF | 2024-01-08 | Transfer of valve from v8 to NAZ line E54 (SCRF E54 - Relocate supply valve @ E54) | FCT | REC | Wk 22 Wk 23 | On-going routing, 89% | done
3 |  | SCRF | 2024-01-08 | Relocation of bursting disk E54 | FCT | REC | Wk 22 Wk 23 | On-going routing, 89% | done
4 |  | Hydraulic Upgrade | 2023-12-02 | Hydraulic Project: Add Tagging on Lines and Equipment | FCT | REC | Wk 30 |  | Pending
5 |  | Hydraulic Upgrade | 2024-01-08 | Hydraulic Project: Maintenance Plan | FCT |  | Wk 22 Wk 23 WK25 | On-going, move to WK25, waiting for M&I feedback. | Pending
6 |  | Hydraulic Upgrade | 2024-01-08 | Hydraulic Project: Spare Parts | FCT |  | Wk 22 Wk 23 WK24 | On-going, Move to WK25, no spare parts enrolled by Mplanner last Week. | Pending
7 |  | COMPACTOR | 2024-03-27 | Additional spare parts requested by M&I to be enroll. (SKF Bearing FYTB 15 FM, Spring Compression, OD 50-51mm 100mm L, Cylinder Pneumatic 160x100 mm 12kN Festo, Hose PTFE Exitflex EF179 1/4" OL=30cm) | FCT | FCT | Wk 22 Wk 23 WK25 | On-going * SKF Bearing FYTB 15 FM - Waiting for Quotation * Spring Compression, OD 50-51mm 100mm L - Waiiting for M&I to confirmed if done enrollment * Cylinder Pneumatic 160x100 mm 12kN Festo - For rerouting, declined by technical store. * Hose PTFE Exitflex EF179 1/4" OL=30cm) -For rerouting, declined by technical store. | Pending
8 |  | Auto Compactor | 2024-05-24 | Removal of E54 prewitting lines near cell; to invite Rhajtek & Joors for Go-see for the job @ Monday 05-27 | dtl | DTL |  |  | done
9 |  | SIR | 2024-04-24 | finalize dwg of test stone and pneu cylinder | Kid | Kid | Wk 22 Wk24 Wk 27 | On-going draftsman prioritize pec dwg | Pending
10 |  | SIR | 2024-05-16 | update clarifier p&id based on the discussion with operator | Kid |  | Wk21 Wk24 | follow up Production team for the final set up. | Pending
11 |  | SIR | 2024-05-16 | discuss with OSL the new p&id based on discussion with operator | Kid | Cris | WK23 |  | done
12 |  | SIR | 2024-05-16 | RFQ for the new scope of clarifier | Kid |  | Wk21 | with quote but on hold. | Pending
13 |  | Improvement of FFE RARE Filtering System | 2024-04-12 | PO for FFE RARE Mechanical Works | FCT | REC | WK24 WK25 | Ongoing approval from sir Aaron, To follow up again this week | done
14 |  | Improvement of FFE RARE Filtering System | 2024-05-15 | Approved Drawing (Mechanical) | FCT | FCT | Wk 22 Wk 23 | Done routing, forwarded to Sir Ryan by Roro, forwarded to Maam Dairo from Sir Ryan. | done
15 |  | Improvement of FFE RARE Filtering System | 2024-05-20 | Pump readiness test (Electrical) | FCT | ABP | WK22 |  | done
16 |  | Green Coffee Van Unloading Facility | 2023-12-01 | enrollment of Dust collector | FCT | DTL | NA | on hold, equipment not yet ordered | Pending
17 |  | Green Coffee Van Unloading Facility | 2024-01-13 | PEP processing (BP Industrial) | DTL | DTL | Wk 23, wk24, wk26 | 95% complete (balance SHE signatory) | Pending
18 |  | Green Coffee Van Unloading Facility | 2024-01-13 | Delivery of equipment (dust collector) | DTL | DTL | Wk 26, wk27 |  | Pending
19 |  | Green Coffee Van Unloading Facility | 2024-01-13 | inspection of pre fabricated ducting & supports @ workshop | DTL | DTL | WK23 | do photo updating from contractor | cancel
20 |  | Green Coffee Van Unloading Facility | 2024-02-17 | orientation @ NTCC prior to day 1 execution | JA | DTL | NA |  | done
21 |  | WATER HEATER | 2023-12-27 | Steam Cladding c/o Cost plus @ E54 water heater | DTL |  |  | check with cost plus activities | Pending
22 |  | WATER HEATER | 2024-01-09 | davit arm delivery on site | WGE | DTL | Wk 23, wk49 | Inland corp- logistic incharge (tracking) | on going
23 |  | WATER HEATER | 2024-01-09 | davit arm installation c/o FEDCON | DTL | REC | tbd | on going arrange of shipment | Pending
24 |  | WATER HEATER | 2024-01-20 | create manpower for E54 water heater tagging | DTL |  | tbd | check with cost plus activities | Pending
25 |  | WATER HEATER | 2024-02-10 | create CPES for E54 HP water heater c/o fedcon | DTL |  | tbd | need to install davit arm- balance activity | Pending
26 |  | GCU plus | 2024-05-20 | machining of hub for V4 line | Kid |  | WK 22 Wk24 Wk 27 | machinist busy | on going
27 |  | GCU plus | 2024-05-20 | prepare plate for hub machining | Kid |  | WK 22 |  | done
28 |  | GCU plus | 2024-05-29 | meeting with rhajtek and costplus for the v4v6 issue in e54 | Kid |  | WK 22 |  | done
29 |  | GCU plus | 2024-05-29 | email sir ben ragarding the plan of V4V6 issue | Kid |  | WK 22 |  | done
30 |  | GCU plus | 2024-05-29 | create PPT presentation for the V4V6 chronology | Kid |  | Wk23 |  | done
|  | GCU plus | 2024-06-10 | update PPT presentation for the V4V6 installation as per sir chris comment | Kid |  | Wk24 |  | done
31 |  | PEC MECH | 2024-04-23 | withdraw checkvalves at stores as per WGE | Kid |  | WK 22 | no store stock, proceed on ordering | done
32 |  | PEC MECH | 2024-05-16 | doc 9 additional works quotation | Kid |  | WK 22 Wk23 | 3 contractors submitted quotation | done
33 |  | PEC MECH | 2024-05-16 | doc 5 additional works quotation | Kid |  | WK 22 Wk23 | 3 contractors submitted quotation | done
34 |  | PEC MECH | 2024-05-16 | prebidding meeting for group 1 additional works | Kid |  | Wk 23 Wk24 | Aaron moved to wk24 since he is not available | done
35 |  | PEC MECH | 2024-05-29 | RFQ of check valve | WGE |  | Wk 23 Wk24 | WGE to send URS to maam dairo
36 |  | PEC MECH | 2024-05-29 | RFQ of valtaco valves | WGE |  | Wk 23 Wk24 | WGE to send URS to maam dairo
37 |  | PEC MECH | 2024-05-29 | PO of tuflin valves | WGE |  | Wk 24 | for PO approval
38 |  | PEC MECH | 2024-05-29 | PO of PM valves | WGE |  | Wk 24 | for PO approval
39 |  | PEC MECH | 2024-05-29 | PO of mixed proof valves | WGE |  | Wk 26 | on going technical discussion
40 |  | PEC MECH | 2024-05-29 | PO of sight glass | WGE |  | Wk 26 | on going technical discussion
41 |  | PEC MECH PE PANEL | 2024-01-13 | Prebidding of PE Panel Cooling System (ducting works) | DTL |  | Wk 27 | the same as existing (10 tonner)
42 |  | PEC MECH PE PANEL | 2024-01-13 | create prebidding drawing- mechanical works | DTL |  | Wk 23, wk24 | priority no.1 for drafting | done
|  | PEC MECH PE PANEL | 2024-06-04 | prebidding |  | DTL | WK27
43 |  | PEC MECH PE PANEL | 2024-04-18 | create scope detailing for PE Panel cooling | DTL | dtl | Wk 24, wk26, wk27 | draftsman drawing- not prioritize | on going
|  | PEC MECH PE PANEL | 2024-06-06 | BOM creation for entire scope | DTL |  | Wk 23, wk24 | priority no.1 for SE | done
44 |  | Hydraulic Upgrade | 2024-05-28 | Punchlist Updates | Kid |  | Wk 26 | Percent completion in the ESD report. | done
45 |  | GCCD Transport PH1 | 2024-05-31 | Commisssioing w/ NEU JKF- Gregory | CD | DTL | Wk 22 | set final parameters | done
46 |  | GCCD Transport PH1 | 2024-05-31 | Conduct alignment meeting w/ Gregory & production team | CD | DTL | Wk 22 |  | done
47 |  | GCCD Transport PH1 | 2024-06-01 | switching of pipe from direct transport to bypass tipping | DTL | DTL | Wk 22 |  | done
48 |  | GCCD Transport PH2 | 2024-05-31 | Conduct alignment w/ production w/ new P&ID (2 dust collectors for roast & coffee dust) | WGE | DTL | Wk 22 |  | done
49 |  | GCCD Transport PH2 | 2024-05-31 | Conduct alignment w/ TCU w/ new P&ID (2 dust collectors for roast & coffee dust) | WGE | DTL | Wk 24 | waiting for TCU response | not yet
50 |  | Improvement of FFE RARE Filtering System | 2024-04-12 | SOO for FFE-RARE | FCT | FCT | wk 23 |  | Done
51 |  | Auto Compactor | 2024-06-10 | create VSU checklist | DTL |  | Wk24 |  | done
52 |  | Auto Compactor | 2024-06-11 | check column actual alignment | DTL |  | Wk24 |  | done
53 |  | GCCD Transport P1 | 2024-06-04 | CILT creation- rotary valve | DTL |  | wk27
54 |  | WATER HEATER | 2024-06-04 | CILT | DTL |  | WK25 | E45 -done, E54- on going | done
55 |  | GC Transport PH1 | 2024-06-12 | Drawing of the sensor position & dimension | DTL |  | 2024-07-13 | Go see w/ ABP & REC- done | done
56 |  | GC Transport PH1 | 2024-06-12 | Mech'l job during ICIP ot night shift | DTL |  | wk25 |  | on hold
57 |  | GC Transport PH1 | 2024-06-12 | To install strainer at the vent of cyclone separator to be able to measure the actual transport loss | RLN | DTL | 2024-06-30 | drawing- on going, Go see w/ ABP & REC- done, fine screen availability; inform R. torres- done | done
58 |  | Auto Compactor | 2024-06-04 | create 3 quotations for E54 old prewetting line removal | RD | DTL | wk24 | 2 quotes- done, 1 quote balance- not yet | done
59 |  | PEC MECH PE PANEL | 2024-06-04 | create 3 quotations for PE Panel ACU | RD | DTL | wk24 | 1 quotes- done, 2 quote balance- not yet | done
60 |  | IPTA Vaccum Pump | 2024-06-04 | create 3 quotations for commissioning G&R | RD | DTL | wk24 |  | done
61 |  |  | 2024-06-13 | send prebidding sched to WGE | DTL |  | wk24 |  | done
62 |  | Spare Parts & MPLAN | 2024-06-13 | Set meeting with M&I & technical store to agree spare parts to be enroll | FCT | WGE | WK25 | print excel file for discussion with M&I and stores. | Done
63 |  | Project GCU+ | 2024-06-19 | Verify Quality Officer if he has already received the Punchlist | JA | KJT | WK25
64 |  | PEC 2020 | 2024-06-19 | NAVIS Work - Follow up IT | JV |  | WK25 | not possible
65 |  |  | 2024-06-19 | Gasket material subtitute to Peckos | FCT | WGE | WK25
66 |  |  | 2024-06-19 | Identify filter spare parts on biomass and turnover to store | FCT | WGE | WK26
67 |  | GCCD Transport P1 | 2024-06-24 | Transfer old star valve from biomass to 2nd hand | DTL | WGE | WK26, wk27 | after CIP, inform Robin T- done, fill-up form- done
68 |  | GCCD Transport P1 | 2024-06-24 | Transfer eurac couplings stock from biomass to maintenance | DTL | WGE | WK26, wk27 | after CIP, inform Robin T- done, fill-up form- done
69 |  | Auto Compactor | 2024-06-24 | Transfer old compactor from biomass to 2nd hand | DTL | WGE | WK26, wk27 | after CIP, inform Robin T- done, fill-up form- done
70 |  |  | 2024-06-24 | Inform sir Janjo about conveyor from biomass to transfer 2nd hand | DTL | WGE | WK27 | during biomass go-see w/ WGE
71 |  | IPTA Vaccum Pump | 2024-06-24 | removal of E45 Vauum pump mechanical seal w/ costplus | DTL | WGE | wk26 | forward to High Line- done | done
72 |  | water heater | 2024-06-24 | revision of CILT as per OSL | DTL | CD | wk26 | E54 revision- done, E45 revision- done | done
73 |  | Green Coffee Van Unloading Facility | 2024-06-24 | Inform GCCD area owner for temporary staging area | DTL | WGE | Wk 26 | re-divert to roasting hallway staging area (Rhajtek location)
74 |  | IPTA Vaccum Pump | 2024-06-26 | flushing of vacuum line w/ costplus | DTL | WGE | wk 26 |  | done
|  | IPTA Vaccum Pump | 2024-06-28 | checking of check valve w/ Sir G. Rosales & costplus | DTL | WGE | 2024-07-01 | CIP activity @ 07-01 by G&R
|  | GCCD Transport P1 | 2024-06-28 | installation of low level sensor @ star valve silo | DTL | WGE | 2024-07-01 | CIP activity @ 07-01 by Costplus
75 |  | Auto Compactor | 2024-06-24 | E54 removal of old pre-wetting line | DTL | REC | 2024-07-01 | CIP activity @ 07-01 by EDP
76 |  | Auto Compactor | 2024-06-24 | Removal of Platform @ compactor loading bay & railing installation | DTL | REC | 2024-07-01 | CIP activity @ 07-01 by Joors
77 |  | PEC MECH PE PANEL | 2024-06-26 | Check BOM w/ Janjo, REC, WGE | DTL | WGE | Wk 27 | PE to conduct alignment meeting
|  | GCCD Transport P1 | 2024-06-27 | forward to dairo for 3 quotes, fabrication of dedusting strainer as per OSL | DTL | CD | wk28 | Draftsman strainer drawing- on going
78 |  | SCRF | 2024-06-26 | Trolley modification on all SCRF | FCT | WGE | WK28
79 |  | ICIP | 2024-06-26 | Condensate valves timing | FCT | WGE | WK28
80 |  | FFE RARE | 2024-06-26 | Shipment of rotary filter ETA | WGE | FCT | WK26
81 |  | GCCD Transport | 2024-06-26 | Forward Draft MPLAN to DTL | FCT |  | WK27 |  | Done
Note on E6: Note : Input as mm/dd/yyyy
Note on I6: Note : Input as mm/dd/yyyy

## ASI Closure Perf
ACTION STATUS INDICATOR CLOSURE PERFORMANCE - Improvement of FFE RARE Filtering System | [8 empty] | 2024-06-29 14:58
Last Update:
2024-06-29 14:58
PERFORMANCE TRACKING FOR CLOSURE OF DUE ACTIONS |  | WEEKS
|  | 46 | 47 | 48 | 49 | 50 | 51 | 52
A. TOTAL ACTIONS DUE FOR PREVIOUS WEEK
B. DUE ACTIONS CLOSED / DONE FOR PREVIOUS WEEK
| C. % CLOSURE PERFORMANCE | - | - | - | - | - | - | -

## ASI Closure Perf 2023
ACTION STATUS INDICATOR CLOSURE PERFORMANCE - Improvement of FFE RARE Filtering System | [36 empty] | 2024-06-29 14:58
Last Update:
2024-06-29 14:58
PERFORMANCE TRACKING FOR CLOSURE OF DUE ACTIONS |  | WEEKS
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 30 | 32 | 33 | 34 | 35
| A. TOTAL ACTIONS DUE FOR PREVIOUS WEEK |  |  | 2 | 2 | 3 | 0 | 2 | 1 | 3 | 1 | 2 | 5 | 4 | 3 | 5 | 3 | 4 | 1 | 5 | 1 | 0 | 1 | 1 | 4 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| B. DUE ACTIONS CLOSED / DONE FOR PREVIOUS WEEK |  |  | 0 | 0 | 2 | 0 | 2 | 0 | 1 | 1 | 0 | 3 | 4 | 1 | 2 | 3 | 3 | 1 | 3 | 2 | 0 | 1 | 1 | 2 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0
| C. % CLOSURE PERFORMANCE | - | - | 0% | 0% | 66.67% | - | 100% | 0% | 33.33% | 100% | 0% | 60% | 100% | 33.33% | 40% | 100% | 75% | 100% | 60% | 200% | - | 100% | 100% | 50% | 0% | 100% | 0% | 100% | 0% | 100% | 0% | 100% | - | - | -