## S-curve CP SP
Daily Progress Tracker
as of. June 29, 2024
Month |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
Weeks |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Daily Target % (original) |  | 0% | 0% | 4% | 4% | 8% | 12% | 12% | 16% | 16% | 116% | 56% | 60% | 60% | 60% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 64% | 80% | 92% | 100% | 100% | 100% | 100% | 100% | 100%
Daily Target % (revised) |  | March 10: 0%; March 11: 0%; March 12: 6.061%; March 13: 6.061%; April 14: 9.091%; April 15: 9.091%; April 16: 9.091%; April 17: 9.091%; May 18: 9.091%; May 19: 9.091%; May 20: 27.27%; May 21: 27.27%; May 22: 27.27%; June 23: 27.27%; June 24: 27.27%; June 25: 30.3%; June 26: 36.36%
Daily Actual % |  | March 12: 6.061%; March 13: 6.061%; April 14: 9.091%; April 15: 9.091%; April 16: 9.091%; April 17: 9.091%; May 18: 9.091%; May 19: 9.091%; May 20: 27.27%; May 21: 27.27%; May 22: 27.27%; June 23: 27.27%; June 24: 27.27%; June 25: 30.3%; June 26: 30.3%
Variance % |  | March 10: #VALUE!; March 11: #VALUE!; March 12: 0%; March 13: 0%; April 14: 0%; April 15: 0%; April 16: 0%; April 17: 0%; May 18: 0%; May 19: 0%; May 20: 0%; May 21: 0%; May 22: 0%; June 23: 0%; June 24: 0%; June 25: 0%; June 26: 6.061%
Completion Outlook |  | March 10: ontrack
COFFEE PROCESS PROJECT UPDATE
[14 empty] | ao. | 2024-06-29 14:53
Coffee Process Project Title / Activity Area |  | April 16: PIC ( PE/SE ); May 18: loading schedule and Date updated; May 22: Target Completion Date; June 24: % Target; June 26: % Actual; July 28: Variance; July 30: Completion Outlook; August 32: Catch up Date; August 34: Catch up Plan (Reason of Delay, Catch up activities, PIC)
I. | E54 High Pressure Water Heater | April 16: WGE/DTL; May 20: 2024-06-29; May 22: 2024-11-30; June 24: 15.75%; June 26: 13.25%; July 28: 2.5%; July 30: On-track; August 34: New timeline is given by PE reflected.
A. | Preparation Stage | April 16: WGE/DTL; June 24: 31.5%; June 26: 26.5%; July 28: 5%
| I. Governance | April 16: WGE/DTL; May 18: Done; May 20: 2024-06-29; May 22: Week 50; June 24: 63%; June 26: 53%; July 28: 10%; July 30: On-track; August 32: Week 30 Week 29; August 34: Delayed Project Kick-off due to other priority. Delayed Scope detailing due to other priority. To finish pending activity to proceed water heater installation project. To follow-up SE for update
| II. Shutdown Preparation Works | April 16: WGE/DTL; May 18: n/a; May 22: Week 50; June 24: 0%; June 26: 0%; July 28: 0%; July 30: On-track
B. | Mechanical Works | April 16: WGE/DTL; May 18: Done; May 22: Week 50; June 24: 0%; June 26: 0%; July 28: 0%; July 30: On-track
C. | Electrical Works | May 18: n/a
D | Automation | May 18: n/a
E. | OSL Works | May 18: n/a
F. | Punchlist closure | May 18: n/a
I. Civil
II. Mechanical
III. Electrical
IV. Automation
G. | Documentation | May 18: n/a
| I. MOC | May 18: n/a
| II Phase 1 | May 18: n/a
| III. Phase 2 | May 18: n/a
H. | VSU risk assessment | May 18: n/a
| I. Pre-shutdown stage | May 18: n/a
| II. Execution stage | May 18: n/a
On-track |  | March 10: not started
Delayed |  | March 10: n/a
Cancelled |  | March 10: Done
Done |  | March 10: partial
OTHER ACTIVITY PERFORMANCE INDICATORS
APIs |  | March 10: Link; March 11: December
|  |  |  | Wed | Thu | Fri | Sat | Sun
|  |  | Day | 27 | 28 | 29 | 30 | 31
a. Over-all Contractor Attendance ( by MQI ) |  | March 10: 1; March 11: Plan; March 12: 16; March 13: 158; April 14: 168; April 15: 131
|  |  | Actual | 11 | 146 | 134 | 114
|  |  | % | 68.75% | 92.41% | 79.76% | 87.02% | #DIV/0!
b. Safety Site Audit ( by RSP ) |  | March 10: 1; March 11: Plan; March 13: 7; April 14: 7; April 15: 7
|  |  | Actual |  | 7 | 7 | 7
|  |  | % | #DIV/0! | 100% | 100% | 100% | #DIV/0!
c. Quality Site Audit ( by JA) |  | March 10: 1; March 11: Plan; March 13: 18; April 14: 22; April 15: 20
|  |  | Actual |  | 18 | 22 | 20
|  |  | % | #DIV/0! | 100% | 100% | 100% | #DIV/0!
d. QMP Checklist Perf ( by JA) |  | March 10: 1; March 11: Plan; March 13: 6; April 14: 10; April 15: 39
|  |  | Actual |  | 6 | 10 | 0
|  |  | % | #DIV/0! | 100% | 100% | 0% | #DIV/0!
e. Startup Checklist Perf ( by RPD) |  | March 10: 1; March 11: Plan; March 13: 11; April 14: 15; April 15: 15
|  |  | Actual |  | 11 | 15 | 15
|  |  | % | #DIV/0! | 100% | 100% | 100% | #DIV/0!
f. SE Daily Contractor Audit |  | March 10: 1; March 11: Plan; March 13: 16; April 14: 16; April 15: 16
|  |  | Actual |  | 12 | 9 | 4
|  |  | % | #DIV/0! | 75% | 56.25% | 25% | #DIV/0!
<95%
=/> 95%

## CP SP
PROJECT TITLE:
AREA:
2024-06-29 14:53
| LEGEND |  | WEEK | [5 empty] | Year |  |  | 2024 | [51 empty] | 2025
|  |  | DAY | [5 empty] | Month |  |  | January |  |  |  | February |  |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
[9 empty] | Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 = No Activity
|  |  | a. | Total Planned Activity ( Project Overall ) |  |  |  |  | Total Planned Activity ( Project Overall ) |  |  | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
| 2 = Missed Activity |  | b. | Completed (for the Day) |  |  |  |  | Completed (for the Day) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 = Planned Activity |  | c. | Total Planned Activity (for the DAY) |  |  |  |  | Total Planned Activity (for the DAY) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 = Completed Activity |  | d. | Adherence ( DAILY ) --> Bar ( Target: 100% ) |  |  |  |  | Adherence ( DAILY ) --> Bar ( Target: 100% ) |  |  | March 12: 100%; April 14: 100%; May 20: 100%; June 25: 100%; June 26: 0%; July 28: 0%; July 29: 0%; July 30: 0%; August 34: 0%; November 46: 0%; November 47: 0%; November 48: 0%; December 50: 0%
|  |  | e. | Completed (YTD) |  |  |  |  | Completed (YTD) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
|  |  | f. | Total Planned Activity (YTD) |  |  |  |  | Total Planned Activity (YTD) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 9 | 9 | 9 | 9 | 9 | 10 | 12 | 12 | 13 | 15 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 22 | 26 | 27 | 27 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33 | 33
|  |  | g. | Adherence ( YTD ) |  |  |  |  | Adherence ( YTD ) | [13 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 83.33% | 83.33% | 76.92% | 66.67% | 62.5% | 62.5% | 62.5% | 62.5% | 58.82% | 58.82% | 58.82% | 58.82% | 58.82% | 58.82% | 58.82% | 58.82% | 58.82% | 58.82% | 58.82% | 58.82% | 45.45% | 38.46% | 37.04% | 37.04% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3%
|  |  | h. | Daily Target Cummulative ( Project Overall ) |  |  |  |  | Daily Target Cummulative ( Project Overall ) |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.061% | 6.061% | 9.091% | 9.091% | 9.091% | 9.091% | 9.091% | 9.091% | 27.27% | 27.27% | 27.27% | 27.27% | 27.27% | 30.3% | 36.36% | 36.36% | 39.39% | 45.45% | 48.48% | 48.48% | 48.48% | 48.48% | 51.52% | 51.52% | 51.52% | 51.52% | 51.52% | 51.52% | 51.52% | 51.52% | 51.52% | 51.52% | 51.52% | 51.52% | 66.67% | 78.79% | 81.82% | 81.82% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  |  | i. | Daily Actuals Cummulative ( Project Overall ) |  |  |  |  | Daily Actuals Cummulative ( Project Overall ) | [13 empty] | 6.061% | 6.061% | 9.091% | 9.091% | 9.091% | 9.091% | 9.091% | 9.091% | 27.27% | 27.27% | 27.27% | 27.27% | 27.27% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3% | 30.3%
Item | ACTIVITIES | Requirement to consider done | PIC | Contractor | AREA | Type | COMPLETION STATUS | Remarks | P | A | %
I. | E54 High Pressure Water Heater | SP |  |  |  | Title
A. | Preparation Stage
| I. Governance | [6 empty] | At the start of that project based on HL timeline | 19 | 10 | 52.63%
0 | Establish complete PLAN for Activity Tracker | PLAN of all Activities in I.Governance are already completed and reflected in the Activity Tracker | Controller |  |  |  | Done |  | 1 | 1 | 100% | April 14: 4
1 | Establish Governance Meeting | Agenda and conduct weekly meeting | SE |  |  |  | Done |  | 1 | 1 | 100% | May 20: 4
2 | Establish Activity Tracker | With activity tracker with approval of PM | SE |  |  |  | Done |  | 1 | 1 | 100% | May 20: 4
3 | Establish Project Timeline | Timeline is already approved by PM and PE | SE |  |  |  | Done |  | 1 | 1 | 100% | May 20: 4
4 | Establish ASI | ASI must be standard formst and link to link table | SE |  |  |  | Done |  | 1 | 1 | 100% | May 20: 4
5 | Establish PM Routines | Conduct weekly ASI closure governance | Controller |  |  |  | Done |  | 1 | 1 | 100% | May 20: 4
6 | Establish Project Management Dashboard Tracking | Completely inputed in the system | Controller |  |  |  | Done |  | 1 | 1 | 100% | May 20: 4
7 | Project Kick-off ( Start of the project ) | Submission of kick off material based on template and presented to the team | NPI/SE | [5 empty] | 1 | 0 | 0% | June 26: 3
8 | Scope Detailing | Submission o f scope detailing material with approved and sign | NPI/SE | [5 empty] | 1 | 0 | 0% | June 26: 3
9 | Design Freeze | Sign design documents ( P& ID etc.) | NPI/SE | [5 empty] | 1 | 0 | 0% | July 29: 3
| Approved Drawing for High Pressure Water Heater | [7 empty] | 0 | 0 | 0%
10 | URS | Submit signed URS documents | NPI/SE | [5 empty] | 1 | 0 | 0% | July 30: 3
| Low Pressure Water Heater | [7 empty] | 0 | 0 | 0%
11 | Initiate PR |  | NPI/SE | [5 empty] | 0 | 0 | 0%
| Water Heater Equipment | [5 empty] | Done |  | 1 | 1 | 100% | March 12: 4
| Mechanical Works - Piping Works | [7 empty] | 1 | 0 | 0% | July 28: 3
12 | Pre-bidding |  | NPI/SE | [5 empty] | 0 | 0 | 0%
| Water Heater Equipment | [5 empty] | Done |  | 1 | 1 | 100% | March 12: 4
| Mechanical Works - Piping Works | [7 empty] | 1 | 0 | 0% | July 29: 3
13 | PO ( Critical Matls ) | Official hard copy of PO from procurement | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
| 3401565163 - Water Heater Equipment | [7 empty] | 1 | 1 | 100% | June 25: 4
| Mechanical Works - Piping Works | [7 empty] | 1 | 0 | 0% | August 34: 3
14 | Delivery ( Critical Matls ) | Physical arrival of materials in the factory | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
| Water Heater Equipment | [7 empty] | 1 | 0 | 0% | November 48: 3
| Mechanical Works - Piping Works | [7 empty] | 1 | 0 | 0% | December 50: 3
| II. Shutdown Preparation Works: |  |  |  |  | Title |  |  | 10 | 0 | 0%
1 | Ask Project Engineers for the SD Activities confirmed with the Contractor |  | NPI/SE |  |  |  |  | 1 month before Sd | 1 | 0 | 0% | November 46: 3
2 | Submit shifting plan of project team |  | NPI/SE | [5 empty] | 1 | 0 | 0% | December 50: 3
3 | Conduct & submit Vertical Start Up ( VSU ) Risk analysis |  | NPI/SE |  |  |  |  | 3 wks before SD | 1 | 0 | 0% | November 47: 3
4 | Review and submit justification of manpower loading and required additional support |  | NPI/SE |  |  |  |  | 3 wks before SD | 1 | 0 | 0% | November 47: 3
5 | Submission of detailed Activity Tracker for 2024 Activities |  | NPI/SE |  |  |  |  | 3 wks before SD | 1 | 0 | 0% | November 47: 3
5 | Submit blank form startup Checklists to Controller |  | SE |  |  |  |  | 3 wks before SD | 1 | 0 | 0% | November 47: 3
6 | PEP Compliance |  | SO/QO |  |  |  |  | 4 wks before SD | 1 | 0 | 0% | November 46: 3
7 | Risk Assessment of Methodology |  | SO |  |  |  |  | 4 wks before SD | 1 | 0 | 0% | November 46: 3
8 | Project Kick - off w/ Stakeholders & Area Owners |  | NPI/SE |  |  |  |  | 4 wks before SD | 1 | 0 | 0% | November 46: 3
9 | Conduct Alignment Meeting w/ Production |  | NPI/SE | [5 empty] | 0 | 0 | 0%
10 | Discuss / Align SD Activities with project Team |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
11 | Alignment meeting with Key personnel (Contractor, PE, SO, QO, Supervisor, & Foreman) |  | NPI/SE/SO | [5 empty] | 0 | 0 | 0%
12 | Review of completenes of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
13 | Send mobilization plan and final scoping |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
14 | Project Management Plan for SD |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
15 | Plot the schedule for the execution of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
16 | Complete mobilization on site by Contractor: |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
17 | Balikatan with all contractors |  | SO |  |  |  |  | N/A | 0 | 0 | 0%
18 | Line tracing of LOTO points and submit report |  | SO |  |  |  |  | 1wk before SD | 0 | 0 | 0%
19 | Validation of LOTO Points |  | SO |  |  |  |  | 1st day of SD | 0 | 0 | 0%
20 | Submission of Quality Master Plan with Inspection Date |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
21 | Quality Management Plan - Submission of Blank Checklist |  | QO |  |  |  |  | 2 wk before SD | 1 | 0 | 0% | November 46: 3
22 | Welding Inspection |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
23 | Submission of Start up Execution checklist |  | SE |  |  |  |  | after SD | 0 | 0 | 0%
24 | Safety Mapping |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
25 | Discuss Risk Assessment of Methodolgy (per project) |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
26 | Hazard familiarization with contractor |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
27 | Installation of Tempacil |  | SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
28 | Activity tracker for Quality |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
29 | Submit Man Power Loading Plan (per contractor) |  | SE |  |  |  |  | N/A | 0 | 0 | 0%
B. | Mechanical Works | [7 empty] | 4 | 0 | 0%
Installation
| Equipment delivery and custom release | [7 empty] | 0 | 0 | 0%
| GR of Equipment | [7 empty] | 0 | 0 | 0%
Installation on site
| Equipment Unloading/Inspection | [7 empty] | 0 | 0 | 0%
| Installation of equipment | [7 empty] | 0 | 0 | 0%
| Look Check | [7 empty] | 1 | 0 | 0% | December 50: 3
| I/O Check | [7 empty] | 1 | 0 | 0% | December 50: 3
Commission
| Commissioning/Trial run | [7 empty] | 1 | 0 | 0% | December 50: 3
| Commercial Run | [7 empty] | 1 | 0 | 0% | December 50: 3
| OSL/Vertical Start-up Assessment (Use official template) | to be done 1 month after credit approval |  |  |  |  | n/a
1 | Perform Current Operations Assessment ( COA ) | Complete requirements
2 | Initiate Management of Change ( MOC )/ HACCP
3 | Training for Operators, Mechanics, EIs & FLMs ( AWGs & MWGs )
4 | Update QMS and Standard Operational Procedure (SOP)
5 | Product Commissioning
6 | Hand-over of OSL related documents
[6 empty] | SELECTION: | STATUS:
[6 empty] | Title | On-Track
[6 empty] | CP | Delayed
[6 empty] | Ord | Cancelled
n/a
Done
on hold
Note on P9: PHMichelIb: CIP

## S-curve MAOA
Daily Progress Tracker
as of. June 29, 2024
Month |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
Weeks |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Daily Target % (original) |  | 21% | 22% | 22% | 22% | 22% | 24% | 25% | 26% | 30% | 34% | 41% | 51% | 72% | 78% | 83% | 91% | 93% | 95% | 95% | 97% | 99% | 99% | 99% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Daily Target % (revised) |  | 20.89% | 21.52% | 22.15% | 22.15% | 22.15% | 23.42% | 25.32% | 25.95% | 29.75% | 33.54% | 40.51% | 50% | 70.25% | 76.58% | 81.01% | 85.44% | 89.87% | 94.94% | 95.57% | 96.84% | 98.73% | 99.37% | 99.37% | 99.37% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Daily Actual % |  | March 10: 20.89%; March 11: 21.52%; March 12: 22.15%; March 13: 22.15%; April 14: 22.15%; April 15: 22.78%; April 16: 24.68%; April 17: 24.68%; May 18: 27.85%; May 19: 31.65%; May 20: 38.61%; May 21: 47.47%; May 22: 66.46%; June 23: 72.78%; June 24: 77.22%; June 25: 79.75%; June 26: 82.91%
Variance % |  | March 10: 0%; March 11: 0%; March 12: 0%; March 13: 0%; April 14: 0%; April 15: 0.6329%; April 16: 0.6329%; April 17: 1.266%; May 18: 1.899%; May 19: 1.899%; May 20: 1.899%; May 21: 2.532%; May 22: 3.797%; June 23: 3.797%; June 24: 3.797%; June 25: 5.696%; June 26: 6.962%
Completion Outlook |  | March 10: ontrack; March 11: ontrack; March 12: ontrack; March 13: ontrack; April 14: ontrack; April 15: ontrack; April 16: ontrack; April 17: ontrack; May 18: ontrack; May 19: ontrack; May 20: ontrack; May 21: ontrack; May 22: ontrack; June 23: ontrack; June 24: ontrack; June 25: ontrack; June 26: ontrack
MAOA OVER-ALL PROJECT UPDATE
[14 empty] | ao. | 2024-06-29 14:53
Coffee Process Project Title / Activity Area |  | April 16: PIC ( PE/SE ); May 18: loading schedule and Date updated; May 22: Target Completion Date; June 24: % Target; June 26: % Actual; July 28: Variance; July 30: Completion Outlook; August 32: Catch up Date; August 34: Catch up Plan (Reason of Delay, Catch up activities, PIC)
I. | Upgrade of Soft Water Plants | April 16: JRUS; May 20: 2024-06-15; June 24: 75%; June 26: 73.75%; July 28: 1.25%; July 30: Delayed
A. | Preparation Stage
| I. Governance | April 16: BDY; May 18: Done; May 20: 2024-06-15; May 22: Week 25; June 24: 100%; June 26: 95%; July 28: 0%; July 30: Delayed; August 32: Week 26; August 34: Delayed delivery of Pump due contractor cannot be contacted. To follow-up contractor and SE for updates
| II. Shutdown Preparation Works | April 16: BDY; May 18: n/a
B. | Mechanical Works | April 16: BDY; May 18: Done; May 20: 2024-06-10; May 22: Week 23 Week 24; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
C. | Electrical Works | April 16: MGS; May 18: Done; May 20: 2024-06-10; May 22: Week 22; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
D. | Testing & Commissioning | April 16: BDY/MGS; May 18: Done; May 20: 2024-06-15; May 22: Week 27; June 24: 0%; June 26: 0%; July 28: 0%; July 30: On-track; August 34: Pending works on Back-wash
E. | OSL Works | May 18: n/a
F. | Punchlist Closure | bar: April 16; July 28
I. Civil
II. Mechanical
III. Electrical
IV. Automation
G. | Documentation | bar: April 16; July 28
| I. MOC | June 24: 44%; June 26: 44%
II Phase 1
III. Phase 2
H. | VSU risk assessment | bar: July 28
| I. Pre-shutdown stage | April 16: BDY; May 18: Done; May 20: 09.Mar.24; May 22: 2024-02-28; June 24: 0%; June 26: 0%; July 28: 0%
| II. Execution stage | April 16: BDY; May 18: Done; May 20: 09.Mar.24; May 22: 2024-03-10; June 24: 0%; June 26: 0%; July 28: 0%
II | Zurich Gap Closure ( Purchase Only ) | April 16: RADY; May 20: 2024-06-21; May 22: 2024-05-31; June 24: 100%; June 26: 76.95%; July 28: 23.05%; July 30: Delayed; August 34: CRF on route
| i. BEAM DETECTOR & SMOKE SENSOR INSTALLATION | April 16: ADC; May 18: Done; May 20: 2024-06-15; May 22: 2024-05-29; June 24: 100%; June 26: 53.9%; July 28: 46.1%; July 30: Delayed
| ii. Structural Integrity Assesment | April 16: AVI; May 18: Done; May 20: 23.Mar.24; May 22: 2024-04-30; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
| A. PR to PO - Equipment | April 16: RADY; May 18: Done; May 20: 09.Mar.24; May 22: 2023-10-19; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
| B.Awarding of PO - Equipment | April 16: RADY; May 18: Done; May 20: 09.Mar.24; May 22: 2023-10-19; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
| C. Delivery of Equipment | April 16: RADY; May 18: Done; May 20: 2024-05-25; June 24: 100%; June 26: 56.5%; July 28: 43.5%; July 30: Delayed
| C1. Electrical | April 16: ADC; May 18: Done; May 20: 2024-06-21; May 22: 2024-05-31; June 24: 100%; June 26: 13%; July 28: 87%; July 30: Delayed; August 32: Week 34; August 34: Delayed Delivery of main components and Installation works due to On-going PEP and Lacking manpower. To follow-up SE for updates
| C2. Civil | April 16: AVI; May 18: Done; May 20: 20.Apr.24; May 22: 2024-04-30; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
| D. Electrical Works | April 16: ADC/MGS; May 18: Done; May 20: 2024-06-15; May 22: 2024-05-31; June 24: 100%; June 26: 0%; July 28: 100%; July 30: Delayed; August 32: Week 34; August 34: Delayed Delivery of main components and Installation works due to On-going PEP and Lacking manpower. To follow-up SE for updates
| E.Testing & Commissioning | April 16: RADY; May 18: Done; May 20: 09.Mar.24; May 22: 2024-05-29; June 24: 0%; June 26: 0%; July 28: 0%; August 34: Waiting for revised timeline from contractor from chittik
III | Shoe Rack Modification (Purchase only from FOB1 Budget) | April 16: RADY; May 20: 2024-06-29; June 24: 75%; June 26: 72.5%; July 28: 2.5%; July 30: Delayed
| A. PR to PO | April 16: SMG; May 18: Done; May 20: 2024-05-04; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
| B.Awarding of PO | April 16: SMG; May 18: Done; May 20: 2024-05-04; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
| C. Delivery - Modification of shoe rack | April 16: SMG; May 18: n/a
| D. Civil works | April 16: SMG; May 18: Done; May 20: 2024-06-29; May 22: Week 26, 2024; June 24: 100%; June 26: 90%; July 28: 10%; July 30: Delayed; August 32: Week 27; August 34: Delayed Completion of Civil works due to additional request for quotation for painting. Follow-up contractor. To follow-up SE/PE for updates
| E. Turn-over to FNP team | April 16: SMG; May 18: Done; May 20: 2024-05-04; May 22: Week 26, 2024; June 24: 0%; June 26: 0%; July 28: 0%
On-track |  | March 10: not started
Delayed |  | March 10: n/a
Cancelled |  | March 10: Done
Done |  | March 10: partial
OTHER ACTIVITY PERFORMANCE INDICATORS
APIs |  | March 10: Link; March 11: December
|  |  |  | Wed | Thu | Fri | Sat | Sun
|  |  | Day | 27 | 28 | 29 | 30 | 31
a. Over-all Contractor Attendance ( by MQI ) |  | March 10: 1; March 11: Plan; March 12: 16; March 13: 158; April 14: 168; April 15: 131
|  |  | Actual | 11 | 146 | 134 | 114
|  |  | % | 68.75% | 92.41% | 79.76% | 87.02% | #DIV/0!
b. Safety Site Audit ( by RSP ) |  | March 10: 1; March 11: Plan; March 13: 7; April 14: 7; April 15: 7
|  |  | Actual |  | 7 | 7 | 7
|  |  | % | #DIV/0! | 100% | 100% | 100% | #DIV/0!
c. Quality Site Audit ( by JA) |  | March 10: 1; March 11: Plan; March 13: 18; April 14: 22; April 15: 20
|  |  | Actual |  | 18 | 22 | 20
|  |  | % | #DIV/0! | 100% | 100% | 100% | #DIV/0!
d. QMP Checklist Perf ( by JA) |  | March 10: 1; March 11: Plan; March 13: 6; April 14: 10; April 15: 39
|  |  | Actual |  | 6 | 10 | 0
|  |  | % | #DIV/0! | 100% | 100% | 0% | #DIV/0!
e. Startup Checklist Perf ( by RPD) |  | March 10: 1; March 11: Plan; March 13: 11; April 14: 15; April 15: 15
|  |  | Actual |  | 11 | 15 | 15
|  |  | % | #DIV/0! | 100% | 100% | 100% | #DIV/0!
f. SE Daily Contractor Audit |  | March 10: 1; March 11: Plan; March 13: 16; April 14: 16; April 15: 16
|  |  | Actual |  | 12 | 9 | 4
|  |  | % | #DIV/0! | 75% | 56.25% | 25% | #DIV/0!
<95%
=/> 95%
Note on Q92: phcabilokh: June 2024

## MAOA
PROJECT TITLE:
AREA:
2024-06-29 14:53
| LEGEND |  | WEEK | [5 empty] | Year |  |  | 2024 | [51 empty] | 2025
|  |  | DAY | [5 empty] | Month |  |  | January |  |  |  | February |  |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
[9 empty] | Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 = No Activity
|  |  | a. | Total Planned Activity ( Project Overall ) |  |  |  |  | Total Planned Activity ( Project Overall ) |  |  | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158
| 2 = Missed Activity |  | b. | Completed (for the Day) |  |  |  |  | Completed (for the Day) |  |  | 17 | 2 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 7 | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 5 | 6 | 11 | 14 | 30 | 10 | 7 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 = Planned Activity |  | c. | Total Planned Activity (for the DAY) |  |  |  |  | Total Planned Activity (for the DAY) |  |  | 17 | 2 | 0 | 0 | 2 | 2 | 1 | 1 | 1 | 7 | 1 | 1 | 0 | 0 | 2 | 3 | 1 | 6 | 6 | 11 | 15 | 32 | 10 | 7 | 7 | 7 | 8 | 1 | 2 | 3 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 = Completed Activity |  | d. | Adherence ( DAILY ) --> Bar ( Target: 100% ) |  |  |  |  | Adherence ( DAILY ) --> Bar ( Target: 100% ) |  |  | January 1: 100%; January 2: 100%; February 5: 100%; February 6: 100%; February 7: 100%; February 8: 100%; February 9: 100%; March 10: 100%; March 11: 100%; March 12: 100%; April 15: 50%; April 16: 100%; April 17: 0%; May 18: 83.33%; May 19: 100%; May 20: 100%; May 21: 93.33%; May 22: 93.75%; June 23: 100%; June 24: 100%; June 25: 57.14%; June 26: 71.43%; July 27: 0%; July 28: 0%; July 29: 0%; July 30: 0%; August 31: 0%; August 34: 0%
|  |  | e. | Completed (YTD) |  |  |  |  | Completed (YTD) |  |  | 17 | 19 | 19 | 19 | 21 | 23 | 24 | 25 | 26 | 33 | 34 | 35 | 35 | 35 | 36 | 39 | 39 | 44 | 50 | 61 | 75 | 105 | 115 | 122 | 126 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131 | 131
|  |  | f. | Total Planned Activity (YTD) |  |  |  |  | Total Planned Activity (YTD) |  |  | 17 | 19 | 19 | 19 | 21 | 23 | 24 | 25 | 26 | 33 | 34 | 35 | 35 | 35 | 37 | 40 | 41 | 47 | 53 | 64 | 79 | 111 | 121 | 128 | 135 | 142 | 150 | 151 | 153 | 156 | 157 | 157 | 157 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158 | 158
|  |  | g. | Adherence ( YTD ) |  |  |  |  | Adherence ( YTD ) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 97.3% | 97.5% | 95.12% | 93.62% | 94.34% | 95.31% | 94.94% | 94.59% | 95.04% | 95.31% | 93.33% | 92.25% | 87.33% | 86.75% | 85.62% | 83.97% | 83.44% | 83.44% | 83.44% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91%
|  |  | h. | Daily Target Cummulative ( Project Overall ) |  |  |  |  | Daily Target Cummulative ( Project Overall ) |  |  | 10.76% | 12.03% | 12.03% | 12.03% | 13.29% | 14.56% | 15.19% | 15.82% | 16.46% | 20.89% | 21.52% | 22.15% | 22.15% | 22.15% | 23.42% | 25.32% | 25.95% | 29.75% | 33.54% | 40.51% | 50% | 70.25% | 76.58% | 81.01% | 85.44% | 89.87% | 94.94% | 95.57% | 96.84% | 98.73% | 99.37% | 99.37% | 99.37% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  |  | i. | Daily Actuals Cummulative ( Project Overall ) |  |  |  |  | Daily Actuals Cummulative ( Project Overall ) |  |  | 10.76% | 12.03% | 12.03% | 12.03% | 13.29% | 14.56% | 15.19% | 15.82% | 16.46% | 20.89% | 21.52% | 22.15% | 22.15% | 22.15% | 22.78% | 24.68% | 24.68% | 27.85% | 31.65% | 38.61% | 47.47% | 66.46% | 72.78% | 77.22% | 79.75% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91% | 82.91%
Item | ACTIVITIES | Requirement to consider done | PIC | Contractor | AREA | Type | COMPLETION STATUS | Remarks | P | A | %
I. | Upgrade of Soft Water Plants | SP |  |  |  | Title
A. | Preparation Stage
| I. Governance | [6 empty] | At the start of that project based on HL timeline | 20 | 19 | 95%
0 | Establish complete PLAN for Activity Tracker | PLAN of all Activities in I.Governance are already completed and reflected in the Activity Tracker | Controller | [5 empty] | 1 | 1 | 100% | April 15: 4
1 | Establish Governance Meeting | Agenda and conduct weekly meeting | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
2 | Establish Activity Tracker | With activity tracker with approval of PM | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
3 | Establish Project Timeline | Timeline is already approved by PM and PE | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
4 | Establish ASI | ASI must be standard formst and link to link table | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
5 | Establish PM Routines | Conduct weekly ASI closure governance | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
6 | Establish Project Management Dashboard Tracking | Completely inputed in the system | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
7 | Project Kick-off ( Start of the project ) | Submission of kick off material based on template and presented to the team | NPI/SE | [5 empty] | 1 | 1 | 100% | January 1: 4
8 | Scope Detailing | Submission o f scope detailing material with approved and sign | NPI/SE | [5 empty] | 1 | 1 | 100% | January 1: 4
9 | Design Freeze | Sign design documents ( P& ID etc.) | NPI/SE | [5 empty] | 0 | 0 | 0%
| Vicinity Map, Location Plan & Perspective View | [7 empty] | 1 | 1 | 100% | January 1: 4
| Block Diagram | [7 empty] | 1 | 1 | 100% | January 1: 4
| P&ID | [7 empty] | 1 | 1 | 100% | January 1: 4
| Proposed Equipment Layout Plan | [7 empty] | 1 | 1 | 100% | January 1: 4
10 | URS | Submit signed URS documents | NPI/SE | [5 empty] | 0 | 0 | 0%
| Softener Upgrade - Supply of Equipment and Installation | [7 empty] | 1 | 1 | 100% | January 1: 4
11 | Initiate PR |  | NPI/SE | [5 empty] | 0 | 0 | 0%
| Softener Upgrade - Supply of Equipment and Installation | [7 empty] | 1 | 1 | 100% | January 1: 4
12 | PO ( Critical Matls ) | Official hard copy of PO from procurement | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
| 3401515521 - Soft water plant upgrade | [7 empty] | 1 | 1 | 100% | January 1: 4
13 | Delivery ( Critical Matls ) | Physical arrival of materials in the factory | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
| Pump | [7 empty] | 1 | 0 | 0% | June 25: 2
| Brine Tank | [7 empty] | 1 | 1 | 100% | April 16: 4
| 2 MMF | [7 empty] | 1 | 1 | 100% | April 16: 4
| 2 ACF | [7 empty] | 1 | 1 | 100% | April 16: 4
| II. Shutdown Preparation Works: |  |  |  |  | Title |  |  | 0 | 0 | 0%
1 | Ask Project Engineers for the SD Activities confirmed with the Contractor |  | NPI/SE | PT Cerna | IS | Ord |  | 1 month before Sd | 0 | 0 | 0%
2 | Submit shifting plan of project team |  | NPI/SE | PT Cerna | IS | Ord |  |  | 0 | 0 | 0%
3 | Conduct & submit Vertical Start Up ( VSU ) Risk analysis |  | NPI/SE | PT Cerna | IS | Ord |  | 3 wks before SD | 0 | 0 | 0%
4 | Review and submit justification of manpower loading and required additional support |  | NPI/SE | PT Cerna | IS | Ord |  | 3 wks before SD | 0 | 0 | 0%
5 | Submission of detailed Activity Tracker for 2024 Activities |  | NPI/SE | PT Cerna | IS | Ord |  | 3 wks before SD | 0 | 0 | 0%
5 | Submit blank form startup Checklists to Controller |  | SE | PT Cerna | IS | Ord |  | 3 wks before SD | 0 | 0 | 0%
6 | PEP Compliance |  | SO/QO | PT Cerna | IS | Ord |  | 4 wks before SD | 0 | 0 | 0%
7 | Risk Assessment of Methodology |  | SO | PT Cerna | IS | Ord |  | 4 wks before SD | 0 | 0 | 0%
8 | Project Kick - off w/ Stakeholders & Area Owners |  | NPI/SE | PT Cerna | IS | Ord |  | 4 wks before SD | 0 | 0 | 0%
9 | Conduct Alignment Meeting w/ Production |  | NPI/SE | PT Cerna | IS | Ord |  |  | 0 | 0 | 0%
10 | Discuss / Align SD Activities with project Team |  | NPI/SE | PT Cerna | IS | Ord |  | N/A | 0 | 0 | 0%
11 | Alignment meeting with Key personnel (Contractor, PE, SO, QO, Supervisor, & Foreman) |  | NPI/SE/SO | PT Cerna | IS | Ord |  |  | 0 | 0 | 0%
12 | Review of completenes of start up checklist |  | Controller | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
13 | Send mobilization plan and final scoping |  | NPI/SE | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
14 | Project Management Plan for SD |  | NPI/SE | PT Cerna | IS | Ord |  | N/A | 0 | 0 | 0%
15 | Plot the schedule for the execution of start up checklist |  | Controller | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
16 | Complete mobilization on site by Contractor: |  | NPI/SE | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
17 | Balikatan with all contractors |  | SO | PT Cerna | IS | Ord |  | N/A | 0 | 0 | 0%
18 | Line tracing of LOTO points and submit report |  | SO | PT Cerna | IS | Ord |  | 1wk before SD | 0 | 0 | 0%
19 | Validation of LOTO Points |  | SO | PT Cerna | IS | Ord |  | 1st day of SD | 0 | 0 | 0%
20 | Submission of Quality Master Plan with Inspection Date |  | QO | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
21 | Quality Management Plan - Submission of Blank Checklist |  | QO | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
22 | Welding Inspection |  | QO | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
23 | Submission of Start up Execution checklist |  | SE | PT Cerna | IS | Ord |  | after SD | 0 | 0 | 0%
24 | Safety Mapping |  | SO | PT Cerna | IS | Ord |  | 4 wks before SD | 0 | 0 | 0%
25 | Discuss Risk Assessment of Methodolgy (per project) |  | SO | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
26 | Hazard familiarization with contractor |  | SO | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
27 | Installation of Tempacil |  | SE | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
28 | Activity tracker for Quality |  | QO | PT Cerna | IS | Ord |  | 2 wk before SD | 0 | 0 | 0%
29 | Submit Man Power Loading Plan (per contractor) |  | SE | PT Cerna | IS | Ord |  | N/A | 0 | 0 | 0%
B. | Mechanical Works | [7 empty] | 61 | 61 | 100%
| CIP WORKS - Installation | [7 empty] | 0 | 0 | 0%
1 | Tapping Point #1 Softwater for 4" dia BI pipe existing |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 18: 4
2 | Tapping Point #2 Raw water for 4" dia BI pipe existing |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 18: 4
3 | Tapping Point #5 Raw soft water for 4" dia BI pipe existing |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 18: 4
4 | Tapping Point #3 Raw water for 4" dia BI pipe existing |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 18: 4
5 | Tapping Point #4 Raw Backwash for 4" dia BI pipe existing |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 18: 4
| INSTALLATION | [7 empty] | 0 | 0 | 0%
1 | Mobilization |  |  | PT Cerna | IS | Ord | Done |  | 0 | 0 | 0%
2 | Hazzard Familization/Safety Orientation |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 20: 4
3 | Mobilization of Scaffold |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 20: 4
4 | Erection of Scaffolding |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 20: 4
5 | Positioning of 2-units MMF, 2-units ACF |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 20: 4
6 | Positioning of 1-unit Brine Tank |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 20: 4; May 21: 4
8 | PVC Piping (MMF&ACF) |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 20: 4; May 21: 4
7 | Piping Tie-in Works |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 20: 4; May 21: 4
7.1 | Interconnection of PVC & BI Pipe MMF1 (RAW WATER) |  |  | PT Cerna | IS | Ord | Done |  | 3 | 3 | 100% | May 20: 4; May 21: 4; May 22: 4
7.2 | Interconnection of PVC & BI Pipe MMF2 (RAW WATER) |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 21: 4; May 22: 4
7.3 | Interconnection of PVC & BI Pipe MMF1 (SOFT WATER) |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 21: 4; May 22: 4
7.4 | Interconnection of PVC & BI Pipe MMF2 (SOFT WATER) |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 21: 4; May 22: 4
7.5 | Interconnection of PVC & BI Pipe ACF1 (RAW WATER) |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 21: 4; May 22: 4
7.6 | Interconnection of PVC & BI Pipe ACF2 (RAW WATER) |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 21: 4; May 22: 4
7.7 | Interconnection of PVC & BI Pipe ACF1 (SOFT WATER) |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 21: 4; May 22: 4
7.8 | Interconnection of PVC & BI Pipe ACF2 (SOFT WATER) |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 21: 4; May 22: 4
8 | Conduct leak test (perform NDT procedures) |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | May 21: 4; May 22: 4
8.1 | Apply Cleaning |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
8.2 | Apply Penetrant |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
8.3 | Apply Developer |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
9 | Checking of filters top to bottom (ACF) |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
9.1 | Loading of 2 units ACF |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
10 | Checking of filters top to bottom (MMF) |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
10.1 | Loading of 2 units MMF |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
11 | Tightening Bolts |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
12 | Hydrotest |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
13 | Fabrication of Pump Skid |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
14 | Fabrication of Pipe support for Brine System |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
15 | PVC & Pipe Support |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
16 | Commissioning of 2MMF & 2ACF |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
17 | PVC Piping (BRINE) to Salt Dissolving |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
18 | PVC Piping (BRINE) to Softener 2 & 3 |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
| BACKWASH | [7 empty] | 0 | 0 | 0%
1 | Tie In to existing backwash Softener Tank 4 |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | June 23: 4
2 | Tie in to Existing PVC Pipe ST 2 |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | June 23: 4
3 | Valve Fittings ST 2 |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | June 23: 4; June 24: 4
4 | Tie in to Existing PVC Pipe ST 3 |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | June 23: 4
5 | Valve Fittings ST 3 |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | June 23: 4; June 24: 4
6 | Valve Fittings ST 4 |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | June 23: 4; June 24: 4
7 | Testing & Commisioning |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | June 23: 4
8 | Pneumatic Valve Automation Works |  |  | PT Cerna | IS | Ord | Done |  | 2 | 2 | 100% | June 23: 4; June 24: 4
C. | Electrical Works | [5 empty] | Done |  | 3 | 3 | 100%
1 | Cable pulling for Pump |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
2 | Installation of AB hardware to existing panel |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
3 | Commissioning of systems (Integrated) |  |  | PT Cerna | IS | Ord | Done |  | 1 | 1 | 100% | May 22: 4
D. | Automation Works | [7 empty] | 7 | 1 | 14.29%
1 | Backwashing new MMF#1 & ACF#1 |  |  | PT Cerna | IS | Ord |  |  | 1 | 0 | 0% | July 27: 3
2 | Backwashing new MMF#2 & ACF#2 |  |  | PT Cerna | IS | Ord |  |  | 1 | 0 | 0% | July 27: 3
3 | Commissioning of Brine Tank to Softener 2 & 3 |  |  | PT Cerna | IS | Ord |  |  | 1 | 0 | 0% | July 27: 3
4 | Backwash pipe - Sequence Integration S2, S3, & S4 | [7 empty] | 1 | 0 | 0% | July 27: 3
5 | Push button - Brine Tank; Salt dissolving to brine tank | [7 empty] | 1 | 0 | 0% | July 27: 3
6 | Field Pneumatic Valve for Installation for S4 | [7 empty] | 1 | 1 | 100% | June 25: 4
7 | Punchlist | [7 empty] | 1 | 0 | 0% | July 27: 3
2 | Initiate Management of Change ( MOC )/ HACCP
3 | Training for Operators, Mechanics, EIs & FLMs ( AWGs & MWGs )
4 | Update QMS and Standard Operational Procedure (SOP)
5 | Product Commissioning
6 | Hand-over of OSL related documents
II | Zurich Gap Closure ( Purchase only )
I. | Smoke Detector | [7 empty] | 36 | 4 | 11.11%
A. | PR to PO - Equipment | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
B. | Awarding of PO - Equipment |  |  | Chittik | AOA | Ord | Done |  | 1 | 1 | 100% | January 1: 4
C. | Delivery of Equipment |  |  | Chittik | AOA | Ord | Delayed |  | 2 | 0 | 0% | April 15: 2; August 34: 3
D. | Electrical Works - Installation |  |  | Chittik | AOA | Ord | Delayed |  | 12 | 1 | 8.333%
1 | Permits and JHA |  |  | Chittik | AOA | Ord |  |  | 3 | 1 | 33.33% | April 17: 2; May 20: 4; June 25: 2
2 | Roughing ins and cable pulling |  |  | Chittik | AOA | Ord |  |  | 6 | 0 | 0% | May 18: 2; June 26: 2; July 27: 3; July 28: 3; July 29: 3; July 30: 3
3 | Installation of imported materials |  |  | Chittik | AOA | Ord |  |  | 3 | 0 | 0% | May 21: 2; July 29: 3; July 30: 3
E. | Testing & Commissioning |  |  | Chittik | AOA | Ord | Delayed |  | 4 | 0 | 0%
1 | Initial |  |  | Chittik | AOA | Ord |  |  | 2 | 0 | 0% | May 22: 2; July 30: 3
2 | Final |  |  | Chittik | AOA | Ord |  |  | 2 | 0 | 0% | May 22: 2; August 31: 3
| Project Hand-over |  |  | Chittik | AOA | Ord | Delayed |  | 0 | 0 | 0%
II. | Structural Integrity Assesment | [7 empty] | 16 | 16 | 100%
A. | PR to PO - |  |  | EDP | AOA | Ord | Done |  | 1 | 1 | 100% | January 2: 4
B. | Awarding of PO - |  |  | EDP | AOA | Ord | Done |  | 1 | 1 | 100% | January 2: 4
C. | Delivery of Signed nd Seal papers |  |  | EDP | AOA | Ord | Done |  | 2 | 2 | 100% | March 11: 4; March 12: 4
D. | Civil Works |  |  | EDP | AOA | Ord | Done |  | 0 | 0 | 0%
1 | As-built drawings released from NPI |  |  | EDP | AOA | Ord | Done |  | 1 | 1 | 100% | March 10: 4
2 | Building Inspection and Assesment |  |  | EDP | AOA | Ord | Done |  | 1 | 1 | 100% | February 5: 4
3 | Rebound Hammer Test on Areas |  |  | EDP | AOA | Ord | Done |  | 1 | 1 | 100% | February 6: 4
4 | Start of Structural design analysis |  |  | EDP | AOA | Ord | Done |  | 6 | 6 | 100% | February 5: 4; February 6: 4; February 7: 4; February 8: 4; February 9: 4; March 10: 4
5 | Signed and Sealed Structural design and Analysis |  |  | EDP | AOA | Ord | Done |  | 1 | 1 | 100% | March 10: 4
6 | Signed and Sealed Structural investigation and assesment |  |  | EDP | AOA | Ord | Done |  | 1 | 1 | 100% | March 10: 4
7 | Signed and Sealed Structural integrity certificate |  |  | EDP | AOA | Ord | Done |  | 1 | 1 | 100% | March 10: 4
III | Shoe Rack Modification | [7 empty] | 31 | 28 | 90.32%
A. | PR to PO - Equipment | [5 empty] | Done |  | 1 | 1 | 100% | March 10: 4
B. | Awarding of PO - Equipment | [5 empty] | Done |  | 1 | 1 | 100% | March 10: 4
C. | Delivery of Equipment | [5 empty] | n/a |  | 0 | 0 | 0%
D. | Civil Works | [7 empty] | 29 | 26 | 89.66%
1 | Line release of Tarp Enclosure | [5 empty] | Done |  | 1 | 1 | 100% | May 19: 4
2 | Installation of Tarp Enclosure | [5 empty] | Done |  | 1 | 1 | 100% | May 19: 4
3 | Cutting of Stainless Bench | [5 empty] | Done |  | 1 | 1 | 100% | May 19: 4
4 | Demolition of wall opening | [5 empty] | Done |  | 1 | 1 | 100% | May 19: 4
5 | Installation of Tarp Enclosure | [5 empty] | Done |  | 1 | 1 | 100% | May 19: 4
6 | Removal of Shoe rack #1 | [5 empty] | Done |  | 1 | 1 | 100% | May 19: 4
7 | Modification Works at Megantech Workshop | [5 empty] | Done |  | 1 | 1 | 100% | May 20: 4
8 | Restore area for production use | [5 empty] | Done |  | 1 | 1 | 100% | May 20: 4
9 | Installation of Tarp Enclosure | [5 empty] | Done |  | 1 | 1 | 100% | May 21: 4
10 | Return of modified rack #1 and line release | [5 empty] | Done |  | 1 | 1 | 100% | May 21: 4
11 | Removal of Rack #2 | [5 empty] | Done |  | 1 | 1 | 100% | May 22: 4
12 | Modification Works at Megantech Workshop | [5 empty] | Done |  | 1 | 1 | 100% | May 22: 4
13 | Restore area for production use | [5 empty] | Done |  | 1 | 1 | 100% | May 22: 4
14 | Installation of Tarp Enclosure | [5 empty] | Done |  | 1 | 1 | 100% | June 23: 4
15 | Return of modified rack #2 and line release | [5 empty] | Done |  | 1 | 1 | 100% | June 23: 4
16 | removal of Rack #3 | [5 empty] | Done |  | 1 | 1 | 100% | June 24: 4
17 | Modification Works at Megantech Workshop | [5 empty] | On-Track |  | 2 | 2 | 100% | June 24: 4; June 25: 4
18 | Restore area for production use | [5 empty] | Done |  | 1 | 1 | 100% | June 24: 4
19 | Installation of Tarp Enclosure | [7 empty] | 2 | 2 | 100% | June 25: 4; June 26: 4
20 | Return of modified rack #3 | [7 empty] | 1 | 1 | 100% | June 25: 4
| Line release of modified rack #3 | [7 empty] | 1 | 1 | 100% | June 26: 4
21 | Re-installation | [7 empty] | 2 | 1 | 50% | June 25: 2; June 26: 4
22 | Re-installation of bench and railings | [7 empty] | 1 | 1 | 100% | June 26: 4
23 | Restore area for production use | [7 empty] | 1 | 1 | 100% | June 26: 4
24 | Painting Works and turn-over | [7 empty] | 2 | 0 | 0% | June 26: 2; July 27: 3
[6 empty] | SELECTION: | STATUS:
[6 empty] | Title | On-Track
[6 empty] | CP | Delayed
[6 empty] | Ord | Cancelled
n/a
Done
on hold
Note on P9: PHMichelIb: CIP

## S-curve CP
Daily Progress Tracker
as of. June 29, 2024
Month |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
Weeks |  | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Daily Target % (original) |  | 54% | 54% | 55% | 55% | 55% | 55% | 56% | 57% | 59% | 60% | 61% | 62% | 63% | 64% | 65% | 67% | 75% | 77% | 79% | 80% | 83% | 86% | 87% | 88% | 90% | 91% | 92% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 94%
Daily Target % (revised) |  | March 10: 50.57%; March 11: 51.15%; March 12: 51.44%; March 13: 51.44%; April 14: 51.44%; April 15: 51.44%; April 16: 52.3%; April 17: 53.16%; May 18: 55.46%; May 19: 56.03%; May 20: 56.9%; May 21: 58.05%; May 22: 59.2%; June 23: 60.63%; June 24: 62.36%; June 25: 62.93%; June 26: 68.1%
Daily Actual % |  | March 10: 50.57%; March 11: 51.15%; March 12: 51.44%; March 13: 51.44%; April 14: 51.44%; April 15: 51.44%; April 16: 52.3%; April 17: 53.16%; May 18: 55.46%; May 19: 56.03%; May 20: 56.9%; May 21: 58.05%; May 22: 59.2%; June 23: 60.63%; June 24: 62.36%; June 25: 62.93%; June 26: 63.51%
Variance % |  | March 10: 0%; March 11: 0%; March 12: 0%; March 13: 0%; April 14: 0%; April 15: 0%; April 16: 0%; April 17: 0%; May 18: 0%; May 19: 0%; May 20: 0%; May 21: 0%; May 22: 0%; June 23: 0%; June 24: 0%; June 25: 0%; June 26: 4.598%
Completion Outlook |  | March 10: on-track; March 11: on-track; March 12: on-track; March 13: on-track; April 14: on-track; April 15: on-track; April 16: on-track; April 17: on-track; May 18: on-track; May 19: on-track; May 20: on-track; May 21: on-track; May 22: on-track; June 23: on-track; June 24: on-track; June 25: on-track; June 26: on-track
COFFEE PROCESS PROJECT UPDATE
[14 empty] | ao. | 2024-06-29 14:53
Coffee Process Project Title / Activity Area |  | April 16: PIC ( PE/SE ); May 18: loading schedule and Date updated; May 22: Target Completion Date; June 24: % Target; June 26: % Actual; July 28: Variance; July 30: Completion Outlook; August 32: Catch up Date; August 34: Catch up Plan (Reason of Delay, Catch up activities, PIC)
I. | GC Transport Upgrade (Phase 2) | April 16: WGE/ADC; May 20: 2024-06-15; June 24: 12%; June 26: 12%; July 28: 0%; July 30: On-track; August 34: Reflected new timeline from WGE
A. | Preparation Stage
| I. Governance | April 16: DTL/ABP; May 18: Done; May 20: 2024-06-15; May 22: Week 25 Week 6, 2025; June 24: 48%; June 26: 48%; July 28: 0%; July 30: On-track
| II. Shutdown Preparation Works | April 16: DTL/ABP; May 18: n/a
B. | Mechanical Works | April 16: DTL; May 18: partial; May 20: 2024-06-15; May 22: Week 23, Week 24 Week 8, 2025; June 24: 0%; June 26: 0%; July 28: 0%; July 30: Done
C. | Electrical Works | April 16: ABP; May 18: Done; May 20: 2024-06-15; May 22: Week 22 Week 14, 2025; June 24: 0%; June 26: 0%; July 28: 0%; July 30: Done
D. | Automation Works | April 16: ABP; May 18: Done; May 20: 2024-06-15; May 22: Week 27 Week 15, 2025; June 24: 0%; June 26: 0%; July 28: 0%; July 30: On-track
E. | Punchlist Closure | bar: April 16; July 28
I. Civil
II. Mechanical
III. Electrical
IV. Automation
F. | OSL Works | April 16: CMD; May 18: n/a
G. | Documentation | April 16: RES; July 28: 0%
| I. MOC | June 24: 44%; June 26: 44%
II Phase 1
III. Phase 2
H. | VSU risk assessment | bar: July 28
| I. Pre-shutdown stage | April 16: DTL/ABP; May 18: not started; June 24: 0%; June 26: 0%; July 28: 0%
| II. Execution stage | April 16: DTL/ABP; May 18: not started; June 24: 0%; June 26: 0%; July 28: 0%
II. | Green Coffee Van Unloading | April 16: WGE/REC/ ADC/RADY; May 18: Done; May 20: 2024-06-29; May 22: 2024-03-01; June 24: 51.11%; June 26: 49.11%; July 28: 2%; July 30: On-track
A. | Preparation stage | May 18: Done; June 24: 100%; June 26: 96%; July 28: 4%
| I. Govenrance | April 16: SMG/ABP/DTL; May 18: Done; May 20: 2024-06-29; May 22: Wk 18, Wk 21 Week 25, 2024; June 24: 100%; June 26: 96%; July 28: 4%; July 30: Delayed; August 32: Week 28; August 34: Delayed delivery of dust collector due to holidays & equipment defects during testing & return to their supplier. Close monitoring of the contractor. To follow-up SE for updates.
| II. Shutdown Preparation Works | April 16: SMG/ABP/DTL; May 18: n/a
B. | Mechanical Works | April 16: DTL; May 18: Done; May 20: 2024-06-29; May 22: 4/30/2024 Jul-24; June 24: 0%; June 26: 0%; July 28: 0%; July 30: On-track | Week 28 | Delayed Start of installation of MS ducting due to civil works completion moved to week 27 then mechanical works starts at week 28. Fast track revision of standard installation drawing and close coordination with WGE & MAPP for design. To follow-up SE/PE for updates.
C. | Civil Works | April 16: RADY; May 18: Done; May 20: 2024-06-29; May 22: 2024-06-24; June 24: 100%; June 26: 92%; July 28: 8%; July 30: Delayed; August 32: Week 28; August 34: Delayed completion of Civil works due to availabiliy of the area. Constant communication with operator. Follow-up SE/PE for updates
| I. Enclosure | June 24: 100%; June 26: 26%; July 28: 74%; July 30: On-track; August 34: On hold. Waiting for Logistic timeline
| II.Canopy | June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
D | Electrical Works | April 16: ADC; May 18: Done; May 20: 2024-04-06; May 22: Sept 2024 SD; June 24: 64%; June 26: 64%; July 28: 0%; July 30: On-track; August 34: Waiting for mechanical commissioning. Moved to Sep SD
E. | Automation Works | April 16: ADC; May 18: Done; May 22: Sept 2024 SD
F. | OSL Works | April 16: CMD; May 18: Done; May 20: 2024-05-01; May 22: 2024-12-31; June 24: 40%; June 26: 40%; July 28: 0%; July 30: On-track
G. | Punchlist closure | April 16: ja; May 18: partial; June 24: 0%; June 26: 0%
| I. Civil | May 18: partial; June 24: 0%; June 26: 0%; August 34: On-hold
| II. Mechanical | May 18: partial; June 24: 0%; June 26: 0%
| III. Electrical | May 18: partial; June 24: 0%; June 26: 0%
| IV. Automation | May 18: n/a
H. | Documentation | April 16: RES; June 24: 2.667%; June 26: 2.667%
I. MOC | bar: June 24; June 26
II Phase 1 | bar: June 24; June 26
III. Phase 2 | bar: June 24; June 26
I. | VSU risk assessment
| I. Pre-shutdown stage | April 16: SMG/ABP; May 18: n/a
| II. Execution stage | April 16: SMG/ABP; May 18: n/a
III. | Improvement of FFE RARE Filtering System | April 16: adc; May 18: Done; May 20: 2024-06-29; May 22: 2024-03-01; June 24: 39.93%; June 26: 39.53%; July 28: 0.4%; July 30: On-track; August 34: Reflected new timetine from WGE. Commissioning on Sept SD as per last Engineering meeting (06/14/24) For CRF Creation
A. | Preparation Stage | May 18: Done; June 24: 84%; June 26: 82%; July 28: 2%; July 30: On-track
| I. Governance | April 16: abp; May 18: Done; May 20: 2024-06-29; May 22: Wk 28 Week 37, 2024; June 24: 84%; June 26: 82%; July 28: 2%; July 30: On-track; August 32: Week 27 Week 27; August 34: Delayed PR for Civil work materials due to no WBS. Delayed PO release for Mechanical Works due to delayed approval of PO (1 signature approval remaining). To follow-up SE/PE for updates
| II. Shutdown Preparation Works | April 16: abp; May 18: n/a
B. | Mechanical Works | April 16: FCT; May 18: Done; May 20: 2024-06-15; May 22: 3/31/2024 Week 37, 2024; June 24: 0%; June 26: 0%; July 28: 0%; July 30: On-track
C. | Electrical Works | April 16: abp; May 18: Done; May 20: 2024-06-15; May 22: 3/31/2024 Week 37, 2024; June 24: 75%; June 26: 75%; July 28: 0%; July 30: On-track
D. | Automation Works | April 16: abp; May 18: Done; May 20: 2024-06-15; May 22: 3/31/2024 Week 37, 2024; June 24: 0%; June 26: 0%; July 28: 0%; July 30: On-track
E. | OSL Works | April 16: CMD; May 18: Done; May 20: 2024-04-22; August 34: Waiting for final commissioning date as per CMD. To be discussed with REC and WGE
F. | Punchlist closure | April 16: ja; May 18: Done; June 24: 0%; June 26: 0%; July 28: 0%
| I. Civil | May 18: n/a
| II. Mechanical | May 18: partial; June 24: 0%; June 26: 0%; August 34: March 2024 Installation
| III. Electrical | May 18: partial; June 24: 0%; June 26: 0%
| IV. Automation | May 18: n/a
G. | Documentation | April 16: RES; June 24: 40.67%; June 26: 40.67%
| I. MOC | June 24: 67%; June 26: 67%
| II Phase 1 | June 24: 50%; June 26: 50%
III. Phase 2 | bar: June 24; June 26
H. | VSU risk assessment
| I. Pre-shutdown stage | April 16: abp; May 18: n/a
| II. Execution stage | April 16: abp; May 18: n/a
IV. | SIR E54 (Piping Clarifier) | April 16: wge; May 18: Done; May 20: 2024-06-29; May 22: Week 30, 2024; June 24: 83.4%; June 26: 70.6%; July 28: 12.8%; July 30: On-track; August 34: For CRF creation for the delay on commissioning date
A. | Preparation stage | May 18: Done; June 24: 200%; June 26: 200%; July 28: 0%
| I. Govenrance | April 16: KJGT; May 18: Done; May 20: 2024-06-15; May 22: Week 30, 2024; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
| II. Shutdown Preparation Works | April 16: KJGT; May 18: n/a; May 20: 2024-01-02; May 22: Week 30, 2024; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
B. | Mechanical Works | April 16: KJGT; May 18: Done; May 20: 2024-06-29; May 22: Week 30, 2024; June 24: 64%; June 26: 0%; July 28: 64%; July 30: Delayed; August 32: Week 30; August 34: Delayed Piping works due to need to finalize the execution date and to discuss the concern of the switching of controls of clarifier with sir elleh, one clarifier offline. To set meeting with sir elleh. To follow-up PE/SE for update.
C. | OSL Works | April 16: CMD; May 18: Done; May 20: 2024-05-01; May 22: 2024-08-31; June 24: 60%; June 26: 60%; July 28: 0%; July 30: On-track
I. E54
II. E45
D. | Punchlist closure | bar: April 16; June 24; June 26
I. Civil | bar: June 24; June 26
II. Mechanical | bar: June 24; June 26
III. Electrical | bar: June 24; June 26
IV. Automation | bar: June 24; June 26
E. | Documentation | April 16: RES; June 24: 93%; June 26: 93%
| I. MOC | June 24: 100%; June 26: 100%
| II Phase 1 | June 24: 100%; June 26: 100%
| III. Phase 2 | June 24: 79%; June 26: 79%
F. | VSU risk assessment | April 16: fct
| I. Pre-shutdown stage | April 16: fct; May 18: n/a
| II. Execution stage | April 16: fct; May 18: n/a
V. | SCRF (self cleaning rotary filter) E54 | April 16: wge; May 18: Done; May 20: 2024-06-29; May 22: 2024-04-30; June 24: 72%; June 26: 65.2%; July 28: 6.8%; July 30: On-track; August 34: For CRF creation for the delay on commissioning date
A. | Preparation stage | May 18: Done; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
| I. Govenrance | April 16: fct; May 18: Done; May 20: 2024-02-03; May 22: wk45,2023; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
| II. Shutdown Preparation Works | April 16: fct; May 18: Done; May 20: 2024-01-02; May 22: dec 31,2023; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
B. | Mechanical Works | April 16: fct; May 18: Done; May 20: 2024-06-22; May 22: 4/30/2024 Week 26; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done; August 34: Commissioning @ E54 was done on week 24. Currently 1week running as per OSL. To finish Punchlist works to continue Qualification phase
C. | OSL Works | April 16: CMD; May 18: Done; May 20: 2024-06-29; May 22: 2024-08-31; June 24: 67%; June 26: 33%; July 28: 34%; July 30: Delayed; August 32: July; August 34: Delayed finilization of manufacturing standard due to SCRF performance during CP. Continue to gather data and observe SCRF performance during June CIP. To follow-up CMD for updates
I. E54
II. E45
D. | Punchlist closure | bar: April 16; June 24; June 26
I. Civil | bar: June 24; June 26
II. Mechanical | bar: June 24; June 26
III. Electrical | bar: June 24; June 26
IV. Automation | bar: June 24; June 26
E. | Documentation | April 16: RES; June 24: 93%; June 26: 93%
| I. MOC | June 24: 100%; June 26: 100%
| II Phase 1 | June 24: 100%; June 26: 100%
| III. Phase 2 | June 24: 79%; June 26: 79%
F. | VSU risk assessment | April 16: fct
| I. Pre-shutdown stage | April 16: fct; May 18: n/a
| II. Execution stage | April 16: fct; May 18: n/a
VI. | Independent CIP for Falling Film Evaporator | April 16: WGE/REC; May 20: 2024-06-29; June 24: 88.2%; June 26: 68.2%; July 28: 20%; July 30: Delayed; August 34: CRF on hold. Alignment meeting w/ OSL >Proposed CIP Farm Rotary filter commissioning was moved from Wk12 to August 2024.
A. | Preparation stage | June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
I. Govenrance
II. Shutdown Preparation Works
B. | Mechanical Works | April 16: FCT; May 18: Done; May 20: 2024-06-15; May 22: 3/31/2024 Week 26; June 24: 100%; June 26: 100%; July 28: 0%; July 30: Done
C. | Testing and Commissioning | April 16: CMD; May 18: Done; May 20: 2024-06-22; May 22: 2024-07-30; June 24: 100%; June 26: 0%; July 28: 100%; July 30: Delayed; August 32: 2024-07-30; August 34: Delayed commissioning due to revision of HMI Control. Commissioning date for Rotary Filter #4 for CIP during production CIP. To follow-up CMD for Updates
D. | OSL Works | April 16: CMD; May 18: Done; May 20: 2024-06-29; May 22: 2025-01-31; June 24: 50%; June 26: 50%; July 28: 0%; July 30: On-track
E. | Punchlist closure
I. Civil
II. Mechanical
III. Electrical
IV. Automation
F. | Documentation | April 16: RES; June 24: 91%; June 26: 91%
| I. MOC | May 18: Done; May 20: Nov.22,2023; June 24: 100%; June 26: 100%
| II Phase 1 | May 18: Done; May 20: Nov.22,2023; June 24: 100%; June 26: 100%
| III. Phase 2 | May 18: partial; May 20: 2024-01-15; June 24: 73%; June 26: 73%
G. | VSU risk assessment
I. Pre-shutdown stage
II. Execution stage
On-track |  | March 10: not started
Delayed |  | March 10: n/a
Cancelled |  | March 10: Done
Done |  | March 10: partial
OTHER ACTIVITY PERFORMANCE INDICATORS
APIs |  | March 10: Link; March 11: December
|  |  |  | Wed | Thu | Fri | Sat | Sun
|  |  | Day | 27 | 28 | 29 | 30 | 31
a. Over-all Contractor Attendance ( by MQI ) |  | March 10: 1; March 11: Plan; March 12: 16; March 13: 158; April 14: 168; April 15: 131
|  |  | Actual | 11 | 146 | 134 | 114
|  |  | % | 68.75% | 92.41% | 79.76% | 87.02% | #DIV/0!
b. Safety Site Audit ( by RSP ) |  | March 10: 1; March 11: Plan; March 13: 7; April 14: 7; April 15: 7
|  |  | Actual |  | 7 | 7 | 7
|  |  | % | #DIV/0! | 100% | 100% | 100% | #DIV/0!
c. Quality Site Audit ( by JA) |  | March 10: 1; March 11: Plan; March 13: 18; April 14: 22; April 15: 20
|  |  | Actual |  | 18 | 22 | 20
|  |  | % | #DIV/0! | 100% | 100% | 100% | #DIV/0!
d. QMP Checklist Perf ( by JA) |  | March 10: 1; March 11: Plan; March 13: 6; April 14: 10; April 15: 39
|  |  | Actual |  | 6 | 10 | 0
|  |  | % | #DIV/0! | 100% | 100% | 0% | #DIV/0!
e. Startup Checklist Perf ( by RPD) |  | March 10: 1; March 11: Plan; March 13: 11; April 14: 15; April 15: 15
|  |  | Actual |  | 11 | 15 | 15
|  |  | % | #DIV/0! | 100% | 100% | 100% | #DIV/0!
f. SE Daily Contractor Audit |  | March 10: 1; March 11: Plan; March 13: 16; April 14: 16; April 15: 16
|  |  | Actual |  | 12 | 9 | 4
|  |  | % | #DIV/0! | 75% | 56.25% | 25% | #DIV/0!
<95%
=/> 95%
Note on Q133: phcabilokh: Week 30, 2024
Note on Q134: phcabilokh: Week 30
Note on Q135: phcabilokh: Week 30

## CP
PROJECT TITLE:
AREA:
2024-06-29 14:53
| LEGEND |  | WEEK | [5 empty] | Year |  |  | 2024 | [51 empty] | 2025
|  |  | DAY | [5 empty] | Month |  |  | January |  |  |  | February |  |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
[9 empty] | Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 = No Activity
|  |  | a. | Total Planned Activity ( Project Overall ) |  |  |  |  | Total Planned Activity ( Project Overall ) |  |  | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348
| 2 = Missed Activity |  | b. | Completed (for the Day) |  |  |  |  | Completed (for the Day) |  |  | 128 | 0 | 1 | 2 | 3 | 5 | 9 | 16 | 5 | 7 | 2 | 1 | 0 | 0 | 0 | 3 | 3 | 8 | 2 | 3 | 4 | 4 | 5 | 6 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 = Planned Activity |  | c. | Total Planned Activity (for the DAY) |  |  |  |  | Total Planned Activity (for the DAY) |  |  | 128 | 0 | 1 | 2 | 3 | 5 | 9 | 16 | 5 | 7 | 2 | 1 | 0 | 0 | 0 | 3 | 3 | 8 | 2 | 3 | 4 | 4 | 5 | 6 | 2 | 18 | 13 | 14 | 7 | 21 | 8 | 5 | 4 | 4 | 3 | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 6 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 = Completed Activity |  | d. | Adherence ( DAILY ) --> Bar ( Target: 100% ) |  |  |  |  | Adherence ( DAILY ) --> Bar ( Target: 100% ) |  |  | January 1: 100%; January 3: 100%; January 4: 100%; February 5: 100%; February 6: 100%; February 7: 100%; February 8: 100%; February 9: 100%; March 10: 100%; March 11: 100%; March 12: 100%; April 16: 100%; April 17: 100%; May 18: 100%; May 19: 100%; May 20: 100%; May 21: 100%; May 22: 100%; June 23: 100%; June 24: 100%; June 25: 100%; June 26: 11.11%; July 27: 0%; July 28: 0%; July 29: 0%; July 30: 0%; August 31: 0%; August 32: 0%; August 33: 0%; August 34: 0%; August 35: 0%; September 36: 0%; September 37: 0%; October 44: 0%; December 4: 0%; December 6: 0%; December 8: 0%; December 9: 0%; December 10: 0%; December 11: 0%; December 12: 0%; December 13: 0%; December 14: 0%; December 15: 0%
|  |  | e. | Completed (YTD) |  |  |  |  | Completed (YTD) |  |  | 128 | 128 | 129 | 131 | 134 | 139 | 148 | 164 | 169 | 176 | 178 | 179 | 179 | 179 | 179 | 182 | 185 | 193 | 195 | 198 | 202 | 206 | 211 | 217 | 219 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221
|  |  | f. | Total Planned Activity (YTD) |  |  |  |  | Total Planned Activity (YTD) |  |  | 128 | 128 | 129 | 131 | 134 | 139 | 148 | 164 | 169 | 176 | 178 | 179 | 179 | 179 | 179 | 182 | 185 | 193 | 195 | 198 | 202 | 206 | 211 | 217 | 219 | 237 | 250 | 264 | 271 | 292 | 300 | 305 | 309 | 313 | 316 | 320 | 327 | 327 | 327 | 327 | 327 | 327 | 327 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 329 | 331 | 331 | 333 | 333 | 339 | 340 | 341 | 342 | 343 | 345 | 347 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348 | 348
|  |  | g. | Adherence ( YTD ) |  |  |  |  | Adherence ( YTD ) |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 93.25% | 88.4% | 83.71% | 81.55% | 75.68% | 73.67% | 72.46% | 71.52% | 70.61% | 69.94% | 69.06% | 67.58% | 67.58% | 67.58% | 67.58% | 67.58% | 67.58% | 67.58% | 67.17% | 67.17% | 67.17% | 67.17% | 67.17% | 67.17% | 67.17% | 67.17% | 67.17% | 67.17% | 67.17% | 67.17% | 66.77% | 66.77% | 66.37% | 66.37% | 65.19% | 65% | 64.81% | 64.62% | 64.43% | 64.06% | 63.69% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51%
|  |  | h. | Daily Target Cummulative ( Project Overall ) |  |  |  |  | Daily Target Cummulative ( Project Overall ) |  |  | 36.78% | 36.78% | 37.07% | 37.64% | 38.51% | 39.94% | 42.53% | 47.13% | 48.56% | 50.57% | 51.15% | 51.44% | 51.44% | 51.44% | 51.44% | 52.3% | 53.16% | 55.46% | 56.03% | 56.9% | 58.05% | 59.2% | 60.63% | 62.36% | 62.93% | 68.1% | 71.84% | 75.86% | 77.87% | 83.91% | 86.21% | 87.64% | 88.79% | 89.94% | 90.8% | 91.95% | 93.97% | 93.97% | 93.97% | 93.97% | 93.97% | 93.97% | 93.97% | 94.54% | 94.54% | 94.54% | 94.54% | 94.54% | 94.54% | 94.54% | 94.54% | 94.54% | 94.54% | 94.54% | 94.54% | 95.11% | 95.11% | 95.69% | 95.69% | 97.41% | 97.7% | 97.99% | 98.28% | 98.56% | 99.14% | 99.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  |  | i. | Daily Actuals Cummulative ( Project Overall ) |  |  |  |  | Daily Actuals Cummulative ( Project Overall ) |  |  | 36.78% | 36.78% | 37.07% | 37.64% | 38.51% | 39.94% | 42.53% | 47.13% | 48.56% | 50.57% | 51.15% | 51.44% | 51.44% | 51.44% | 51.44% | 52.3% | 53.16% | 55.46% | 56.03% | 56.9% | 58.05% | 59.2% | 60.63% | 62.36% | 62.93% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51% | 63.51%
Item | ACTIVITIES | Requirement to consider done | PIC | Contractor | AREA | Type | COMPLETION STATUS | Remarks | P | A | %
I. | GC Transport Upgrade |  |  |  |  | Title
A. | Preparation Stage
| I. Governance | [6 empty] | At the start of that project based on HL timeline | 21 | 10 | 47.62%
0 | Establish complete PLAN for Activity Tracker | PLAN of all Activities in I.Governance are already completed and reflected in the Activity Tracker | Controller | [5 empty] | 1 | 1 | 100% | February 8: 4
1 | Establish Governance Meeting | Agenda and conduct weekly meeting | SE | [5 empty] | 1 | 1 | 100% | February 8: 4
2 | Establish Activity Tracker | With activity tracker with approval of PM | SE | [5 empty] | 1 | 1 | 100% | February 8: 4
3 | Establish Project Timeline | Timeline is already approved by PM and PE | SE | [5 empty] | 1 | 1 | 100% | February 8: 4
4 | Establish ASI | ASI must be standard formst and link to link table | SE | [5 empty] | 1 | 1 | 100% | February 8: 4
5 | Establish PM Routines | Conduct weekly ASI closure governance | Controller | [5 empty] | 1 | 1 | 100% | February 8: 4
6 | Establish Project Management Dashboard Tracking | Completely inputed in the system | Controller | [5 empty] | 1 | 1 | 100% | February 8: 4
7 | Project Kick-off ( Start of the project ) | Submission of kick off material based on template and presented to the team | NPI/SE | [5 empty] | 1 | 1 | 100% | February 8: 4
8 | Scope Detailing | Submission o f scope detailing material with approved and sign | NPI/SE | [5 empty] | 0 | 0 | 0%
| Dust Collector (1 file for Mech, Civil and E&A) | [7 empty] | 1 | 1 | 100% | May 20: 4
9 | Design Freeze | Sign design documents ( P& ID etc.) | NPI/SE | [5 empty] | 0 | 0 | 0%
| Dust Collector | [7 empty] | 1 | 0 | 0% | July 28: 3
| Piping Lay-out | [7 empty] | 1 | 0 | 0% | July 28: 3
| P&ID | [7 empty] | 1 | 0 | 0% | July 28: 3
10 | URS | Submit signed URS documents | NPI/SE | [5 empty] | 0 | 0 | 0%
| Dust Collector for Cyclone B | [7 empty] | 1 | 1 | 100% | January 1: 4
11 | Initiate PR |  | NPI/SE | [5 empty] | 0 | 0 | 0%
| Dust Collector | [7 empty] | 1 | 0 | 0% | July 27: 3
| Mechanical Works (with Duct) | [7 empty] | 1 | 0 | 0% | September 37: 3
11 | Initiate PR |  | NPI/SE | [5 empty] | 0 | 0 | 0%
| Dust Collector | [7 empty] | 1 | 0 | 0% | July 27: 3
| Mechanical Works (with Duct) | [7 empty] | 1 | 0 | 0% | September 37: 3
11 | PO ( Critical Matls ) | Official hard copy of PO from procurement | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
| Dust Collector | [7 empty] | 1 | 0 | 0% | August 33: 3
| Mechanical Works (with Duct) | [7 empty] | 1 | 0 | 0% | October 44: 3
12 | Delivery ( Critical Matls ) | Physical arrival of materials in the factory | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
| Dust Collector | [7 empty] | 1 | 0 | 0% | December 6: 3
| Mechanical Works (with Duct) | [7 empty] | 1 | 0 | 0% | December 6: 3
| II. Shutdown Preparation Works: |  |  |  |  | Title |  |  | 0 | 0 | 0%
1 | Ask Project Engineers for the SD Activities confirmed with the Contractor |  | NPI/SE |  |  |  |  | 1 month before Sd | 0 | 0 | 0%
2 | Submit shifting plan of project team |  | NPI/SE | [5 empty] | 0 | 0 | 0%
3 | Conduct & submit Vertical Start Up ( VSU ) Risk analysis |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
4 | Review and submit justification of manpower loading and required additional support |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submission of detailed Activity Tracker for 2024 Activities |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submit blank form startup Checklists to Controller |  | SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
6 | PEP Compliance |  | SO/QO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
7 | Risk Assessment of Methodology |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
8 | Project Kick - off w/ Stakeholders & Area Owners |  | NPI/SE |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
9 | Conduct Alignment Meeting w/ Production |  | NPI/SE | [5 empty] | 0 | 0 | 0%
10 | Discuss / Align SD Activities with project Team |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
11 | Alignment meeting with Key personnel (Contractor, PE, SO, QO, Supervisor, & Foreman) |  | NPI/SE/SO | [5 empty] | 0 | 0 | 0%
12 | Review of completenes of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
13 | Send mobilization plan and final scoping |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
14 | Project Management Plan for SD |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
15 | Plot the schedule for the execution of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
16 | Complete mobilization on site by Contractor: |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
17 | Balikatan with all contractors |  | SO |  |  |  |  | N/A | 0 | 0 | 0%
18 | Line tracing of LOTO points and submit report |  | SO |  |  |  |  | 1wk before SD | 0 | 0 | 0%
19 | Validation of LOTO Points |  | SO |  |  |  |  | 1st day of SD | 0 | 0 | 0%
20 | Submission of Quality Master Plan with Inspection Date |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
21 | Quality Management Plan - Submission of Blank Checklist |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
22 | Welding Inspection |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
23 | Submission of Start up Execution checklist |  | SE |  |  |  |  | after SD | 0 | 0 | 0%
24 | Safety Mapping |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
25 | Discuss Risk Assessment of Methodolgy (per project) |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
26 | Hazard familiarization with contractor |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
27 | Installation of Tempacil |  | SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
28 | Activity tracker for Quality |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
29 | Submit Man Power Loading Plan (per contractor) |  | SE |  |  |  |  | N/A | 0 | 0 | 0%
B. | Mechanical Works | 2/10/25 (Dust Collector) 4/17/24 (Envi release, tagging and cleaning) | [6 empty] | 5 | 0 | 0%
1 | Installation of Dust Collector Line | [7 empty] | 1 | 0 | 0% | December 8: 3
2 | Installation of Dust Collector Equipment | [7 empty] | 1 | 0 | 0% | December 8: 3
3 | Tie In works | [7 empty] | 1 | 0 | 0% | December 8: 3
4 | Line Release | [7 empty] | 1 | 0 | 0% | December 8: 3
5 | Commsiioning | [7 empty] | 1 | 0 | 0% | December 8: 3
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
C. | Electrical Works | Waiting for mechanical final schedule | [6 empty] | 7 | 0 | 0%
1 | Fabrication of cable tray raceway droppings and supports | [6 empty] | 1wk from installation | 1 | 0 | 0% | December 8: 3
2 | Installation of cable tray | [6 empty] | 1wk | 1 | 0 | 0% | December 9: 3
3 | Installation of lighting brackets and supports | [6 empty] | 1wk | 1 | 0 | 0% | December 10: 3
4 | Installation and wiring of motor controls | [6 empty] | 1wk | 1 | 0 | 0% | December 11: 3
5 | Cable laying and harnessing of power supply, isulation and selector switch | [6 empty] | 1wk | 1 | 0 | 0% | December 12: 3
6 | Wiring and termination works | [6 empty] | 1wk | 1 | 0 | 0% | December 13: 3
7 | pre-commissioning | [6 empty] | 1wk | 1 | 0 | 0% | December 14: 3
D. | Automation Works | 2/10/25 (Dust Collector) 4/17/24 (Envi release, tagging and cleaning) | [6 empty] | 3 | 0 | 0%
| Programming works | [7 empty] | 2 | 0 | 0% | December 13: 3; December 14: 3
| Commissioning | [7 empty] | 1 | 0 | 0% | December 15: 3
| OSL/Vertical Start-up Assessment (Use official template) | to be done 1 month after credit approval | [6 empty] | 0 | 0 | 0%
0 | Submission of OSL Assesment | to be done 1 month after credit approval | [6 empty] | 0 | 0 | 0%
1 | Perform Current Operations Assessment ( COA ) | Complete requirements | [6 empty] | 0 | 0 | 0%
2 | Initiate Management of Change ( MOC )/ HACCP | [7 empty] | 0 | 0 | 0%
3 | Training for Operators, Mechanics, EIs & FLMs ( AWGs & MWGs ) | [7 empty] | 0 | 0 | 0%
4 | Update QMS and Standard Operational Procedure (SOP) | [7 empty] | 0 | 0 | 0%
5 | Product Commissioning | [7 empty] | 0 | 0 | 0%
6 | Hand-over of OSL related documents | [7 empty] | 0 | 0 | 0%
II. | Green Coffee Van Unloading\Tilting
A. | Preparation Stage
| I. Governance | [6 empty] | At the start of that project based on HL timeline | 27 | 25 | 92.59%
0 | Establish complete PLAN for Activity Tracker | PLAN of all Activities in I.Governance are already completed and reflected in the Activity Tracker | Controller | [5 empty] | 1 | 1 | 100% | February 7: 4
1 | Establish Governance Meeting | Agenda and conduct weekly meeting | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
2 | Establish Activity Tracker | With activity tracker with approval of PM | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
3 | Establish Project Timeline | Timeline is already approved by PM and PE | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
4 | Establish ASI | ASI must be standard formst and link to link table | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
5 | Establish PM Routines | Conduct weekly ASI closure governance | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
6 | Establish Project Management Dashboard Tracking | Completely inputed in the system | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
7 | Project Kick-off ( Start of the project ) | Submission of kick off material based on template and presented to the team | NPI/SE | [5 empty] | 1 | 1 | 100% | January 1: 4
8 | Scope Detailing | Submission o f scope detailing material with approved and sign | NPI/SE | [5 empty] | 0 | 0 | 0%
| Dust Collector (1 file for Mech, Civil and E&A) | [7 empty] | 1 | 1 | 100% | May 20: 4
9 | Design Freeze | Sign design documents ( P& ID etc.) | NPI/SE | [5 empty] | 0 | 0 | 0%
a. Civil
| Proposed Green Coffee Van Tilting | [7 empty] | 1 | 1 | 100% | June 23: 4
b. Mechanical
| Green Coffee Van Unloading Facility (Prop. GC Van Tilting Dust Collector) | [7 empty] | 1 | 1 | 100% | April 16: 4
c. Electrical
| Van Tilting_ Existing Location of Panels | [7 empty] | 1 | 1 | 100% | January 1: 4
| Green Coffee van Tilting | [7 empty] | 1 | 1 | 100% | January 1: 4
10 | URS | Submit signed URS documents | NPI/SE | [5 empty] | 0 | 0 | 0%
| Dust Collector GCCD Van Tilting | [7 empty] | 1 | 1 | 100% | March 12: 4
11 | Initiate PR |  | NPI/SE | [5 empty] | 0 | 0 | 0%
a. Civil
| 3401446485 - GC Van Tilting Facility | [7 empty] | 1 | 1 | 100% | January 1: 4
b. Mechanical
| 3401481979 - Fabrication Latching Mechanism Drawing | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3401544759 - Installation of Ducting and Fan | [7 empty] | 1 | 1 | 100% | January 1: 4
c. Electrical
| 3401439421 - Electrical Work for GC Automation Upgrade | [7 empty] | 1 | 1 | 100% | January 1: 4
d. Automation
| 3401446210 - Van Tilting Unloading SI Works | [7 empty] | 1 | 1 | 100% | January 1: 4
11 | PO ( Critical Matls ) | Official hard copy of PO from procurement | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
a. Civil
| 3401446485 - GC Van Tilting Facility | [7 empty] | 1 | 1 | 100% | January 1: 4
b. Mechanical
| 3401481979 - Fabrication Latching Mechanism Drawing | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3401544759 - Installation of Ducting and Fan | [7 empty] | 1 | 1 | 100% | April 16: 4
c. Electrical
| 3401439421 - Electrical Work for GC Automation Upgrade | [7 empty] | 1 | 1 | 100% | January 1: 4
d. Automation
| 3401446210 - Van Tilting Unloading SI Works | [7 empty] | 1 | 1 | 100% | January 1: 4
12 | Delivery ( Critical Matls ) | Physical arrival of materials in the factory | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
| a. Civil | [7 empty] | 0 | 0 | 0%
| Materials for Canopy and Enclosure | [7 empty] | 1 | 1 | 100% | January 1: 4
| b. Mechanical | [7 empty] | 0 | 0 | 0%
| Dust Collector | [7 empty] | 2 | 0 | 0% | June 26: 2; July 28: 3
| II. Shutdown Preparation Works: |  |  |  |  | Title |  |  | 0 | 0 | 0%
1 | Ask Project Engineers for the SD Activities confirmed with the Contractor |  | NPI/SE |  |  |  |  | 1 month before Sd | 0 | 0 | 0%
2 | Submit shifting plan of project team |  | NPI/SE | [5 empty] | 0 | 0 | 0%
3 | Conduct & submit Vertical Start Up ( VSU ) Risk analysis |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
4 | Review and submit justification of manpower loading and required additional support |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submission of detailed Activity Tracker for 2024 Activities |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submit blank form startup Checklists to Controller |  | SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
6 | PEP Compliance |  | SO/QO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
7 | Risk Assessment of Methodology |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
8 | Project Kick - off w/ Stakeholders & Area Owners |  | NPI/SE |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
9 | Conduct Alignment Meeting w/ Production |  | NPI/SE | [5 empty] | 0 | 0 | 0%
10 | Discuss / Align SD Activities with project Team |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
11 | Alignment meeting with Key personnel (Contractor, PE, SO, QO, Supervisor, & Foreman) |  | NPI/SE/SO | [5 empty] | 0 | 0 | 0%
12 | Review of completenes of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
13 | Send mobilization plan and final scoping |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
14 | Project Management Plan for SD |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
15 | Plot the schedule for the execution of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
16 | Complete mobilization on site by Contractor: |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
17 | Balikatan with all contractors |  | SO |  |  |  |  | N/A | 0 | 0 | 0%
18 | Line tracing of LOTO points and submit report |  | SO |  |  |  |  | 1wk before SD | 0 | 0 | 0%
19 | Validation of LOTO Points |  | SO |  |  |  |  | 1st day of SD | 0 | 0 | 0%
20 | Submission of Quality Master Plan with Inspection Date |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
21 | Quality Management Plan - Submission of Blank Checklist |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
22 | Welding Inspection |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
23 | Submission of Start up Execution checklist |  | SE |  |  |  |  | after SD | 0 | 0 | 0%
24 | Safety Mapping |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
25 | Discuss Risk Assessment of Methodolgy (per project) |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
26 | Hazard familiarization with contractor |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
27 | Installation of Tempacil |  | SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
28 | Activity tracker for Quality |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
29 | Submit Man Power Loading Plan (per contractor) |  | SE |  |  |  |  | N/A | 0 | 0 | 0%
B. | Civil Works | 2/10/25 (Dust Collector) 4/17/24 (Envi release, tagging and cleaning) | [6 empty] | 42 | 33 | 78.57%
| I. Enclosure |  | SMG | OGBI | Logistic | Ord |  |  | 0 | 0 | 0%
| Enclosure |  | SMG | OGBI | Logistic | Ord |  |  | 2 | 2 | 100% | May 20: 4; May 21: 4
| Scaffolding Works |  | SMG | OGBI | Logistic | Ord |  |  | 1 | 1 | 100% | May 21: 4
| Demolition of Existing wall |  | SMG | OGBI | Logistic | Ord |  |  | 1 | 1 | 100% | May 21: 4
| Concrete Stud |  | SMG | OGBI | Logistic | Ord |  |  | 2 | 2 | 100% | May 21: 4; May 22: 4
| Wall |  | SMG | OGBI | Logistic | Ord |  |  | 0 | 0 | 0%
| Structural Frames |  | SMG | OGBI | Logistic | Ord |  |  | 3 | 3 | 100% | May 22: 4; June 23: 4; June 24: 4
| 100mm thk Sandwich Panel - 7.875m (Height) |  | SMG | OGBI | Logistic | Ord |  |  | 1 | 1 | 100% | June 24: 4
| Masonry Works - Additional wall |  | SMG | OGBI | Logistic | Ord |  |  | 1 | 1 | 100% | May 22: 4
| Ceiling |  | SMG | OGBI | Logistic | Ord |  |  | 5 | 4 | 80% | June 23: 4; June 24: 4; June 25: 4; June 26: 4; July 27: 3
| Painting Works |  | SMG | OGBI | Logistic | Ord |  |  | 6 | 4 | 66.67% | June 23: 4; June 24: 4; June 25: 4; June 26: 4; July 27: 3; July 28: 3
| Doors |  | SMG | OGBI | Logistic | Ord |  |  | 0 | 0 | 0%
| Roll-up Door 6.010m H x 3.465m W with complete Accessories |  | SMG | OGBI | Logistic | Ord |  |  | 2 | 0 | 0% | June 26: 2; July 28: 3
| Roll-up Door 3.277m H x 3.4m W with complete Accessories |  | SMG | OGBI | Logistic | Ord |  |  | 2 | 0 | 0% | June 26: 2; July 28: 3
| Metal door 0.9mx2.1m with viewing glass and complete Accessories |  | SMG | OGBI | Logistic | Ord |  |  | 2 | 0 | 0% | June 26: 2; July 28: 3
| II. Canopy | [7 empty] | 0 | 0 | 0%
1 | Foundation Works |  | SMG | OGBI | Logistic | Ord |  |  | 1 | 1 | 100% | January 4: 4
2 | Concrete works |  | SMG | OGBI | Logistic | Ord |  |  | 1 | 1 | 100% | February 6: 4
3 | Installation of Scaffolding |  | SMG | OGBI | Logistic | Ord |  |  | 3 | 3 | 100% | January 4: 4; February 5: 4; February 6: 4
4 | Fabrication of Roofing support |  | SMG | OGBI | Logistic | Ord |  |  | 1 | 1 | 100% | January 3: 4
5 | Installation of Roofing support |  | SMG | OGBI | Logistic | Ord |  |  | 4 | 4 | 100% | February 7: 4; February 8: 4; February 9: 4; March 10: 4
6 | Painting Works & Rectification of affected Area |  | SMG | OGBI | Logistic | Ord |  |  | 2 | 2 | 100% | February 9: 4; March 10: 4
7 | Removal of Scaffolding & Enclosure |  | SMG | OGBI | Logistic | Ord |  |  | 1 | 1 | 100% | March 10: 4
8 | Demobilization |  | SMG | OGBI | Logistic | Ord |  |  | 1 | 1 | 100% | March 10: 4
C. | Mechanical Works | 2/10/25 (Dust Collector) 4/17/24 (Envi release, tagging and cleaning) | [6 empty] | 13 | 0 | 0%
1 | Installation of scaffoldings |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22 Wk24, WK27 | 1 | 0 | 0% | July 27: 3
2 | Removal of any obstacles |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22 Wk24, WK28 | 1 | 0 | 0% | July 27: 3
3 | Installation of ms duct supports |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22 Wk24, WK29 | 1 | 0 | 0% | July 27: 3
4 | ceiling drilling for ducting provision |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22 Wk24, WK30 | 1 | 0 | 0% | July 27: 3
5 | Installation of hood supports |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22 Wk25, WK28 | 1 | 0 | 0% | July 28: 3
6 | Installation of ms ducting |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22 Wk25, WK29 | 1 | 0 | 0% | July 28: 3
7 | Installation of isolation damper |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22 Wk25, WK30 | 1 | 0 | 0% | July 28: 3
8 | Installation of suction hood |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22 Wk25, WK31 | 1 | 0 | 0% | July 28: 3
9 | Installation of plastic curtain |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22Wk26, WK29 | 1 | 0 | 0% | July 29: 3
10 | final painting |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22Wk26, WK30 | 1 | 0 | 0% | July 29: 3
11 | Punchlist closure |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22Wk27, WK30 | 1 | 0 | 0% | July 30: 3
12 | 5s & demobilization |  | DTL | BP Industrial | Logistic | Ord |  | Wk 17, Wk22Wk27, WK31 | 1 | 0 | 0% | July 30: 3
13 | Installation of dust collector |  | DTL | BP Industrial | Logistic | Ord |  | Wk 23 Wk27 | 1 | 0 | 0% | July 28: 3
D. | Electrical Works | 2/10/25 (Dust Collector) 4/17/24 (Envi release, tagging and cleaning) | [6 empty] | 11 | 7 | 63.64%
1 | Line tracing and tagging |  | ABP | Jonrich | Logistic | Ord |  |  | 1 | 1 | 100% | February 6: 4
2 | Fabrication of cable tray raceway droppings and supports |  | ABP | Jonrich | Logistic | Ord |  |  | 1 | 1 | 100% | February 7: 4
3 | Installation of cable tray |  | ABP | Jonrich | Logistic | Ord |  |  | 1 | 1 | 100% | February 8: 4
4 | Installation of lighting brackets and supports |  | ABP | Jonrich | Logistic | Ord |  |  | 1 | 1 | 100% | February 8: 4
5 | Installation and wiring of motor controls |  | ABP | Jonrich | Logistic | Ord |  |  | 1 | 1 | 100% | March 10: 4
6 | cable laying of lighting supply and photo switch |  | ABP | Jonrich | Logistic | Ord |  |  | 2 | 2 | 100% | March 10: 4; March 11: 4
7 | Cable laying and harnessing of power supply, isulation and selector switch |  | ABP | Jonrich | Logistic | Ord |  | Week 23, Mech commisioning Move to week 37-38, 2024. need SD as per ADC | 1 | 0 | 0% | September 36: 3
8 | Relocation of Lighting Panels |  | ABP | Jonrich | Logistic | Ord |  | Week 23, Mech commisioning Move to week 37-38, 2024. need SD as per ADC | 1 | 0 | 0% | September 36: 3
9 | Wiring and termination works |  | ABP | Jonrich | Logistic | Ord |  | Week 23, Mech commisioning Move to week 37-38, 2024. need SD as per ADC | 1 | 0 | 0% | September 36: 3
10 | pre-commissioning |  | ABP | Mheco | Logistic | Ord |  | Week 23, Mech commisioning Move to week 37-38, 2024. need SD as per ADC | 1 | 0 | 0% | September 36: 3
E. | Automation Works | 2/10/25 (Dust Collector) 4/17/24 (Envi release, tagging and cleaning) | ABP | Jonrich/Mheco | Logistic | Ord |  |  | 0 | 0 | 0%
| Commissioning | [7 empty] | 1 | 0 | 0% | July 29: 3
| OSL/Vertical Start-up Assessment (Use official template) | to be done 1 month after credit approval | [6 empty] | 0 | 0 | 0%
0 | Submission of OSL Assesment | to be done 1 month after credit approval | [6 empty] | 0 | 0 | 0%
1 | Perform Current Operations Assessment ( COA ) | Complete requirements | [6 empty] | 0 | 0 | 0%
2 | Initiate Management of Change ( MOC )/ HACCP | [7 empty] | 0 | 0 | 0%
3 | Training for Operators, Mechanics, EIs & FLMs ( AWGs & MWGs ) | [7 empty] | 0 | 0 | 0%
4 | Update QMS and Standard Operational Procedure (SOP) | [7 empty] | 0 | 0 | 0%
5 | Product Commissioning | [7 empty] | 0 | 0 | 0%
6 | Hand-over of OSL related documents | [7 empty] | 0 | 0 | 0%
III | Improvement of FFE Rare
A. | Preparation Stage
| I. Governance | [6 empty] | At the start of that project based on HL timeline | 40 | 31 | 77.5%
0 | Establish complete PLAN for Activity Tracker | PLAN of all Activities in I.Governance are already completed and reflected in the Activity Tracker | Controller | [5 empty] | 1 | 1 | 100% | February 7: 4
1 | Establish Governance Meeting | Agenda and conduct weekly meeting | SE |  |  |  | Done |  | 1 | 1 | 100% | January 1: 4
2 | Establish Activity Tracker | With activity tracker with approval of PM | SE |  |  |  | Done |  | 1 | 1 | 100% | January 1: 4
3 | Establish Project Timeline | Timeline is already approved by PM and PE | SE |  |  |  | Done |  | 1 | 1 | 100% | January 1: 4
4 | Establish ASI | ASI must be standard formst and link to link table | SE |  |  |  | Done |  | 1 | 1 | 100% | January 1: 4
5 | Establish PM Routines | Conduct weekly ASI closure governance | Controller |  |  |  | Done |  | 1 | 1 | 100% | January 1: 4
6 | Establish Project Management Dashboard Tracking | Completely inputed in the system | Controller |  |  |  | Done |  | 1 | 1 | 100% | January 1: 4
7 | Project Kick-off ( Start of the project ) | Submission of kick off material based on template and presented to the team | NPI/SE |  |  |  | Done |  | 1 | 1 | 100% | January 1: 4
8 | Scope Detailing | Submission o f scope detailing material with approved and sign | NPI/SE |  |  |  | Done |  | 1 | 1 | 100% | January 1: 4
9 | Design Freeze | Sign design documents ( P& ID etc.) | NPI/SE
a. Civil
| E54_FFE Rare Rotary Filter_Construction drawing_Civil Work | [5 empty] | Done |  | 1 | 1 | 100% | June 24: 4
b. Mechanical
| E54 FFE RARE P&ID | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| E-54 FFE RARE Rotary Filter P1 | [5 empty] | Done |  | 1 | 1 | 100% | June 23: 4
c. Electrical
| E-54 FFE Rare Rotary filter_Proposed Festo valve Terminal Panel | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| FFE RARE Proposed Cable Tray | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
10 | URS | Submit signed URS documents | NPI/SE
| Final FFE_RARE_ROTARY_FILTER_VALVE_&_ACTUATOR_2 | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| Final URS FFE RARE ROTARY FILTER MIXPROOF VALVE & ACTUATOR | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| URS_FFE Rare Rotary Filter1 | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| FFE Rotary Filter (Pekos valves) | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| Final URS_Pump_for_FFE_RARE_Rotary_Filter | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
11 | Initiate PR |  | NPI/SE
a. Civil
| Materials | [5 empty] | On-Track |  | 2 | 0 | 0% | June 26: 2; July 27: 3
b. Mechanical
| 3401324270_Mechanical Support for Coffee projects | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| 3401425582_Improvement for FFE rare - Self Cleaning | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| Valves and Pumps | [5 empty] | Done | Check availability on stores | 1 | 1 | 100% | January 1: 4
| Mechanical works | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| Rotary Filter and Accessories | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
c. Electrical
| 3401443189_Coffee E54 improvement of FFE Rare Various Works | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
d. Automation
| 3401373879_System Integration (SI) works for COFFE | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
11 | PO ( Critical Matls ) | Official hard copy of PO from procurement | Procurement NPI/SE
a. Civil
| Materials | [5 empty] | On-Track |  | 1 | 0 | 0% | July 27: 3
b. Mechanical
| 3401324270_Mechanical Support for Coffee projects | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| 3401425582_Improvement for FFE rare - Self Cleaning | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
| Valves and Pumps | [5 empty] | Done | Check availability on stores | 1 | 1 | 100% | January 1: 4
| Mechanical works | [5 empty] | On-Track |  | 2 | 0 | 0% | June 26: 2; July 27: 3
| Rotary Filter and Accessories | [5 empty] | On-Track |  | 1 | 0 | 0% | July 30: 3
c. Electrical
| 3401443189_Coffee E54 improvement of FFE Rare Various Works | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
d. Automation
| 3401373879_System Integration (SI) works for COFFE | [5 empty] | Done |  | 1 | 1 | 100% | January 1: 4
12 | Delivery ( Critical Matls ) | Physical arrival of materials in the factory | Procurement NPI/SE
a. Civil
| Materials | [5 empty] | On-Track |  | 1 | 0 | 0% | July 28: 3
b. Mechanical
| Rotary Filter and Accessories | [5 empty] | On-Track |  | 1 | 0 | 0% | July 30: 3
| Installation of new equipment, piping and valves | [5 empty] | On-Track |  | 1 | 0 | 0% | September 37: 3
c. Electrical
d. Automation
| II. Shutdown Preparation Works: |  |  |  |  | Title |  |  | 0 | 0 | 0%
1 | Ask Project Engineers for the SD Activities confirmed with the Contractor |  | NPI/SE |  |  |  |  | 1 month before Sd | 0 | 0 | 0%
2 | Submit shifting plan of project team |  | NPI/SE | [5 empty] | 0 | 0 | 0%
3 | Conduct & submit Vertical Start Up ( VSU ) Risk analysis |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
4 | Review and submit justification of manpower loading and required additional support |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submission of detailed Activity Tracker for 2024 Activities |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submit blank form startup Checklists to Controller |  | SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
6 | PEP Compliance |  | SO/QO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
7 | Risk Assessment of Methodology |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
8 | Project Kick - off w/ Stakeholders & Area Owners |  | NPI/SE |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
9 | Conduct Alignment Meeting w/ Production |  | NPI/SE | [5 empty] | 0 | 0 | 0%
10 | Discuss / Align SD Activities with project Team |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
11 | Alignment meeting with Key personnel (Contractor, PE, SO, QO, Supervisor, & Foreman) |  | NPI/SE/SO | [5 empty] | 0 | 0 | 0%
12 | Review of completenes of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
13 | Send mobilization plan and final scoping |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
14 | Project Management Plan for SD |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
15 | Plot the schedule for the execution of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
16 | Complete mobilization on site by Contractor: |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
17 | Balikatan with all contractors |  | SO |  |  |  |  | N/A | 0 | 0 | 0%
18 | Line tracing of LOTO points and submit report |  | SO |  |  |  |  | 1wk before SD | 0 | 0 | 0%
19 | Validation of LOTO Points |  | SO |  |  |  |  | 1st day of SD | 0 | 0 | 0%
20 | Submission of Quality Master Plan with Inspection Date |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
21 | Quality Management Plan - Submission of Blank Checklist |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
22 | Welding Inspection |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
23 | Submission of Start up Execution checklist |  | SE |  |  |  |  | after SD | 0 | 0 | 0%
24 | Safety Mapping |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
25 | Discuss Risk Assessment of Methodolgy (per project) |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
26 | Hazard familiarization with contractor |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
27 | Installation of Tempacil |  | SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
28 | Activity tracker for Quality |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
29 | Submit Man Power Loading Plan (per contractor) |  | SE |  |  |  |  | N/A | 0 | 0 | 0%
B. | Civil Works | [7 empty] | 11 | 0 | 0%
1 | Mobilization | [7 empty] | 1 | 0 | 0% | July 29: 3
2 | Installation of enclosure and Lay-outing | [7 empty] | 1 | 0 | 0% | July 29: 3
3 | Removal of epoxy | [7 empty] | 1 | 0 | 0% | July 29: 3
4 | Drilling on slab for dowels | [7 empty] | 1 | 0 | 0% | July 29: 3
5 | Installation of rebars | [7 empty] | 1 | 0 | 0% | July 30: 3
6 | CHB laying | [7 empty] | 1 | 0 | 0% | July 30: 3
7 | Plastering | [7 empty] | 1 | 0 | 0% | July 30: 3
8 | Curring | [7 empty] | 1 | 0 | 0% | August 31: 3
9 | Painting Works | [7 empty] | 1 | 0 | 0% | August 31: 3
10 | Removal of Enclosure | [7 empty] | 1 | 0 | 0% | August 31: 3
11 | Demobilization | [7 empty] | 1 | 0 | 0% | August 31: 3
C. | Mechanical Works | [7 empty] | 17 | 0 | 0%
1 | Pump Installation & Base Fabrication | [7 empty] | 2 | 0 | 0% | August 31: 3; August 32: 3
2 | Piping Works( Hot water line, Product line and drain Line) | [7 empty] | 3 | 0 | 0% | August 32: 3; August 33: 3; August 34: 3
3 | Installation of Rotary Filter (FFE RARE) | [7 empty] | 1 | 0 | 0% | August 32: 3
4 | Installation of Valves around FFE RARE Filter | [7 empty] | 3 | 0 | 0% | August 32: 3; August 33: 3; August 34: 3
5 | Tie in Works | [7 empty] | 0 | 0 | 0%
| Product inlet | [7 empty] | 1 | 0 | 0% | August 31: 3
| Product outlet | [7 empty] | 1 | 0 | 0% | August 31: 3
6 | Valve Testing | [7 empty] | 1 | 0 | 0% | August 34: 3
7 | Hydrotesting & Water run | [7 empty] | 1 | 0 | 0% | August 34: 3
8 | Commisioning | [7 empty] | 1 | 0 | 0% | August 35: 3
9 | Cladding | [7 empty] | 3 | 0 | 0% | August 31: 3; August 32: 3; August 33: 3
D. | Electrical Works | [7 empty] | 10 | 8 | 80%
1 | Fabrication of cable tray raceway droppings and supports |  | ABP | Michrohm | E54 | ord | Done |  | 1 | 1 | 100% | February 7: 4
2 | Installation of Control Panel |  | ABP | Michrohm | E55 | ord | Done |  | 1 | 1 | 100% | February 7: 4
3 | Installation of cable tray |  | ABP | Michrohm | E56 | ord | Done |  | 0 | 0 | 0% | bar: February 7
4 | Laying of SS tubing |  | ABP | Michrohm | E57 | ord |  | Waiting for Mech Team to install the whole set of FFE RARE skid. Next Schd on Week 30 | 1 | 0 | 0% | September 37: 3
5 | Fabrication of lighting brackets and supports |  | ABP | Michrohm | E58 | ord | Done |  | 2 | 2 | 100% | February 5: 4; February 6: 4
5 | Installation of lighting brackets and supports |  | ABP | Michrohm | E59 | ord | Done |  | 1 | 1 | 100% | February 8: 4
6 | Installation of remote control panel |  | ABP | Michrohm | E60 | ord | Done |  | 1 | 1 | 100% | February 7: 4
7 | cable laying of proximity sensor and pressure transmitter |  | ABP | Michrohm | E61 | ord | Done |  | 1 | 1 | 100% | February 7: 4
8 | Cable laying and harnessing of power supply, isulation and selector switch ant ethernet CAT6 communication cable |  | ABP | Michrohm | E62 | ord | Done |  | 1 | 1 | 100% | March 10: 4
9 | Wiring and termination works |  | ABP | Michrohm | E63 | ord |  | Waiting for Mech Team to install the whole set of FFE RARE skid. Next Schd on Week 30 | 1 | 0 | 0% | September 37: 3
E. | Automation Works | [7 empty] | 2 | 0 | 0%
1 | pre-commissioning |  | ABP | Mheco | E54 | ord |  | Waiting for Mech Team to install the whole set of FFE RARE skid. Next Schd on Week 30 | 1 | 0 | 0% | September 37: 3
2 | Commissioning |  | ABP | Mheco | E55 | ord |  | Waiting for Mech Team to install the whole set of FFE RARE skid. Next Schd on Week 30 | 1 | 0 | 0% | September 37: 3
| OSL/Vertical Start-up Assessment (Use official template) | to be done 1 month after credit approval | [6 empty] | 0 | 0 | 0%
0 | Submission of OSL Assesment | to be done 1 month after credit approval | [6 empty] | 0 | 0 | 0%
1 | Perform Current Operations Assessment ( COA ) | Complete requirements | [6 empty] | 0 | 0 | 0%
2 | Initiate Management of Change ( MOC )/ HACCP | [7 empty] | 0 | 0 | 0%
3 | Training for Operators, Mechanics, EIs & FLMs ( AWGs & MWGs ) | [7 empty] | 0 | 0 | 0%
4 | Update QMS and Standard Operational Procedure (SOP) | [7 empty] | 0 | 0 | 0%
5 | Product Commissioning | [7 empty] | 0 | 0 | 0%
6 | Hand-over of OSL related documents | [7 empty] | 0 | 0 | 0%
IV | SIR E54 (Piping Clarifier)
A. | Preparation Stage
| I. Governance | [6 empty] | At the start of that project based on HL timeline | 0 | 0 | 0%
0 | Establish complete PLAN for Activity Tracker | PLAN of all Activities in I.Governance are already completed and reflected in the Activity Tracker | Controller | [5 empty] | 0 | 0 | 0%
1 | Establish Governance Meeting | Agenda and conduct weekly meeting | SE | [5 empty] | 0 | 0 | 0%
2 | Establish Activity Tracker | With activity tracker with approval of PM | SE | [5 empty] | 0 | 0 | 0%
3 | Establish Project Timeline | Timeline is already approved by PM and PE | SE | [5 empty] | 0 | 0 | 0%
4 | Establish ASI | ASI must be standard formst and link to link table | SE | [5 empty] | 0 | 0 | 0%
5 | Establish PM Routines | Conduct weekly ASI closure governance | Controller | [5 empty] | 0 | 0 | 0%
6 | Establish Project Management Dashboard Tracking | Completely inputed in the system | Controller | [5 empty] | 0 | 0 | 0%
7 | Project Kick-off ( Start of the project ) | Submission of kick off material based on template and presented to the team | NPI/SE | [5 empty] | 0 | 0 | 0%
8 | Scope Detailing | Submission o f scope detailing material with approved and sign | NPI/SE | [5 empty] | 0 | 0 | 0%
9 | Design Freeze | Sign design documents ( P& ID etc.) | NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
10 | URS | Submit signed URS documents | NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
11 | Initiate PR |  | NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
11 | PO ( Critical Matls ) | Official hard copy of PO from procurement | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
12 | Delivery ( Critical Matls ) | Physical arrival of materials in the factory | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
| II. Shutdown Preparation Works: |  |  |  |  | Title |  |  | 0 | 0 | 0%
1 | Ask Project Engineers for the SD Activities confirmed with the Contractor |  | NPI/SE |  |  |  |  | 1 month before Sd | 0 | 0 | 0%
2 | Submit shifting plan of project team |  | NPI/SE | [5 empty] | 0 | 0 | 0%
3 | Conduct & submit Vertical Start Up ( VSU ) Risk analysis |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
4 | Review and submit justification of manpower loading and required additional support |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submission of detailed Activity Tracker for 2024 Activities |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submit blank form startup Checklists to Controller |  | SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
6 | PEP Compliance |  | SO/QO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
7 | Risk Assessment of Methodology |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
8 | Project Kick - off w/ Stakeholders & Area Owners |  | NPI/SE |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
9 | Conduct Alignment Meeting w/ Production |  | NPI/SE | [5 empty] | 0 | 0 | 0%
10 | Discuss / Align SD Activities with project Team |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
11 | Alignment meeting with Key personnel (Contractor, PE, SO, QO, Supervisor, & Foreman) |  | NPI/SE/SO | [5 empty] | 0 | 0 | 0%
12 | Review of completenes of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
13 | Send mobilization plan and final scoping |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
14 | Project Management Plan for SD |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
15 | Plot the schedule for the execution of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
16 | Complete mobilization on site by Contractor: |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
17 | Balikatan with all contractors |  | SO |  |  |  |  | N/A | 0 | 0 | 0%
18 | Line tracing of LOTO points and submit report |  | SO |  |  |  |  | 1wk before SD | 0 | 0 | 0%
19 | Validation of LOTO Points |  | SO |  |  |  |  | 1st day of SD | 0 | 0 | 0%
20 | Submission of Quality Master Plan with Inspection Date |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
21 | Quality Management Plan - Submission of Blank Checklist |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
22 | Welding Inspection |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
23 | Submission of Start up Execution checklist |  | SE |  |  |  |  | after SD | 0 | 0 | 0%
24 | Safety Mapping |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
25 | Discuss Risk Assessment of Methodolgy (per project) |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
26 | Hazard familiarization with contractor |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
27 | Installation of Tempacil |  | SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
28 | Activity tracker for Quality |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
29 | Submit Man Power Loading Plan (per contractor) |  | SE |  |  |  |  | N/A | 0 | 0 | 0%
B. | Mechanical Works | [7 empty] | 18 | 0 | 0%
1 | installation piping clarifier 1 into thick (supply going clarifier) | [7 empty] | 2 | 0 | 0% | June 26: 2; July 30: 3
2 | installation piping clarifier 1 into thick (by-pass) | [7 empty] | 2 | 0 | 0% | June 26: 2; July 30: 3
3 | installation piping clarifier 1 into thick (discharge of clarifier) | [7 empty] | 2 | 0 | 0% | June 26: 2; July 30: 3
4 | installation piping clarifier 4 into thin (supply going clarifier) | [7 empty] | 2 | 0 | 0% | June 26: 2; July 30: 3
5 | installation piping clarifier 4 into thin (by-pass) | [7 empty] | 2 | 0 | 0% | June 26: 2; July 30: 3
6 | installation piping clarifier 4 into thin (discharge of clarifier) | [7 empty] | 2 | 0 | 0% | June 26: 2; July 30: 3
7 | switch piping of clarifier 1 and 2 (discharge of clarifier) | [7 empty] | 2 | 0 | 0% | June 26: 2; July 30: 3
8 | installation of new thin piping to clarifier 1 (supply going clarifier) | [7 empty] | 1 | 0 | 0% | July 30: 3
9 | installation of new thin piping to clarifier 1 (by-pass) | [7 empty] | 1 | 0 | 0% | July 30: 3
10 | installation of new thin piping to clarifier 1 (discharge of clarifier) | [7 empty] | 1 | 0 | 0% | July 30: 3
11 | Testing | [7 empty] | 1 | 0 | 0% | July 30: 3
| OSL/Vertical Start-up Assessment (Use official template) | [7 empty] | 0 | 0 | 0%
0 | Submission of OSL Assesment | to be done 1 month after credit approval | [6 empty] | 0 | 0 | 0%
1 | Perform Current Operations Assessment ( COA ) | Complete requirements | [6 empty] | 0 | 0 | 0%
2 | Initiate Management of Change ( MOC )/ HACCP | [7 empty] | 0 | 0 | 0%
3 | Training for Operators, Mechanics, EIs & FLMs ( AWGs & MWGs ) | [7 empty] | 0 | 0 | 0%
4 | Update QMS and Standard Operational Procedure (SOP) | [7 empty] | 0 | 0 | 0%
5 | Product Commissioning | [7 empty] | 0 | 0 | 0%
6 | Hand-over of OSL related documents | [7 empty] | 0 | 0 | 0%
V. | SCRF E54
A. | Preparation Stage
| I. Governance | [6 empty] | At the start of that project based on HL timeline | 26 | 26 | 100%
0 | Establish complete PLAN for Activity Tracker | PLAN of all Activities in I.Governance are already completed and reflected in the Activity Tracker | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
1 | Establish Governance Meeting | Agenda and conduct weekly meeting | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
2 | Establish Activity Tracker | With activity tracker with approval of PM | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
3 | Establish Project Timeline | Timeline is already approved by PM and PE | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
4 | Establish ASI | ASI must be standard formst and link to link table | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
5 | Establish PM Routines | Conduct weekly ASI closure governance | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
6 | Establish Project Management Dashboard Tracking | Completely inputed in the system | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
7 | Project Kick-off ( Start of the project ) | Submission of kick off material based on template and presented to the team | NPI/SE | [5 empty] | 1 | 1 | 100% | January 1: 4
8 | Scope Detailing | Submission o f scope detailing material with approved and sign | NPI/SE | [5 empty] | 0 | 0 | 0%
9 | Design Freeze | Sign design documents ( P& ID etc.) | NPI/SE | [5 empty] | 0 | 0 | 0%
a. Civil
b. Mechanical
| SelfCleaning Rotary Filter - E54.E45 P&ID - Flow Diagram | [7 empty] | 1 | 1 | 100% | January 1: 4
| Tapping pt for Hot Water System E54-E45 | [7 empty] | 1 | 1 | 100% | January 1: 4
| Relocation of Isolation Valves for Self Cleaning Filter @E54 (Checkprint).FS | [7 empty] | 1 | 1 | 100% | January 1: 4
c. Electrical
| SELF-CLEANING FILTER - Single Line Diagram | [7 empty] | 1 | 1 | 100% | January 1: 4
| SELF-CLEANING FILTER - System Architecture | [7 empty] | 1 | 1 | 100% | January 1: 4
| SELF-CLEANING FILTER - Cable Tray Layout | [7 empty] | 1 | 1 | 100% | January 1: 4
10 | URS | Submit signed URS documents | NPI/SE | [5 empty] | 0 | 0 | 0%
| Self Cleaning Rotary Valves | [7 empty] | 1 | 1 | 100% | January 1: 4
| Valves and Actuator for Self-Cleaning Rotary Filter | [7 empty] | 1 | 1 | 100% | January 1: 4
11 | Initiate PR |  | NPI/SE | [5 empty] | 0 | 0 | 0%
a. Civil
b. Mechanical
| 4553202673 - Self Cleaning Rotary Filters | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4553874444 - Peter Meyer Valve, PM C shape, DN80,PN40, MV and etc. | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4553876547 - PEKOS F.Z06 RRRG- PN40 DN80 and etc. | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400446602 - Mechanical works for Self Cleaning Filter (O&J) | [7 empty] | 1 | 1 | 100% | January 1: 4
c. Electrical
d. Automation
| 3400519118 - Coffee and Milk Plant System Integration | [10 empty] | January 1: 4
11 | PO ( Critical Matls ) | Official hard copy of PO from procurement | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
a. Civil
b. Mechanical
| 4553202673 - Self Cleaning Rotary Filters | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4553874444 - Peter Meyer Valve, PM C shape, DN80,PN40, MV and etc. | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4553876547 - PEKOS F.Z06 RRRG- PN40 DN80 and etc. | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400446602 - Mechanical works for Self Cleaning Filter (O&J) | [7 empty] | 1 | 1 | 100% | January 1: 4
c. Electrical
d. Automation
| 3400519118 - Coffee and Milk Plant System Integration | [10 empty] | January 1: 4
12 | Delivery ( Critical Matls ) | Physical arrival of materials in the factory | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
a. Civil
b. Mechanical
| 4553202673 - Self Cleaning Rotary Filters | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4553874444 - Peter Meyer Valve, PM C shape, DN80,PN40, MV and etc. | [7 empty] | 1 | 1 | 100% | January 1: 4
c. Electrical
d. Automation
| II. Shutdown Preparation Works: |  |  |  |  | Title |  |  | 0 | 0 | 0%
1 | Ask Project Engineers for the SD Activities confirmed with the Contractor |  | NPI/SE |  |  |  |  | 1 month before Sd | 0 | 0 | 0%
2 | Submit shifting plan of project team |  | NPI/SE | [5 empty] | 0 | 0 | 0%
3 | Conduct & submit Vertical Start Up ( VSU ) Risk analysis |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
4 | Review and submit justification of manpower loading and required additional support |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submission of detailed Activity Tracker for 2024 Activities |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submit blank form startup Checklists to Controller |  | SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
6 | PEP Compliance |  | SO/QO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
7 | Risk Assessment of Methodology |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
8 | Project Kick - off w/ Stakeholders & Area Owners |  | NPI/SE |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
9 | Conduct Alignment Meeting w/ Production |  | NPI/SE | [5 empty] | 0 | 0 | 0%
10 | Discuss / Align SD Activities with project Team |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
11 | Alignment meeting with Key personnel (Contractor, PE, SO, QO, Supervisor, & Foreman) |  | NPI/SE/SO | [5 empty] | 0 | 0 | 0%
12 | Review of completenes of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
13 | Send mobilization plan and final scoping |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
14 | Project Management Plan for SD |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
15 | Plot the schedule for the execution of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
16 | Complete mobilization on site by Contractor: |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
17 | Balikatan with all contractors |  | SO |  |  |  |  | N/A | 0 | 0 | 0%
18 | Line tracing of LOTO points and submit report |  | SO |  |  |  |  | 1wk before SD | 0 | 0 | 0%
19 | Validation of LOTO Points |  | SO |  |  |  |  | 1st day of SD | 0 | 0 | 0%
20 | Submission of Quality Master Plan with Inspection Date |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
21 | Quality Management Plan - Submission of Blank Checklist |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
22 | Welding Inspection |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
23 | Submission of Start up Execution checklist |  | SE |  |  |  |  | after SD | 0 | 0 | 0%
24 | Safety Mapping |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
25 | Discuss Risk Assessment of Methodolgy (per project) |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
26 | Hazard familiarization with contractor |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
27 | Installation of Tempacil |  | SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
28 | Activity tracker for Quality |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
29 | Submit Man Power Loading Plan (per contractor) |  | SE |  |  |  |  | N/A | 0 | 0 | 0%
B. | Mechanical Works | [7 empty] | 17 | 17 | 100%
1 | Inspect Rotary Filter screen w/ picture |  | FCT |  | E54 | ord | Done |  | 1 | 1 | 100% | February 8: 4
2 | Cleaning of filter screen |  | FCT |  | E54 | ord | Done |  | 1 | 1 | 100% | February 8: 4
3 | RBC |  | FCT |  | E54 | ord | Done |  | 1 | 1 | 100% | February 8: 4
4 | 3D Drawing approval based from TCU Standard |  | CR |  | E54 | ord | Done |  | 4 | 4 | 100% | February 6: 4; February 7: 4; February 8: 4; February 9: 4
5 | Flashing water (Check with Mheco |  | ABP |  | E54 | ord | Done |  | 1 | 1 | 100% | February 9: 4
6 | Re-orientation of isolation valves |  | ABP |  | E54 | ord | Done |  | 1 | 1 | 100% | May 18: 4
7 | Removal of vursting dist at SCRF as per TCU Standard |  | FCT |  | E54 | ord | Done |  | 1 | 1 | 100% | May 18: 4
8 | Removal of bursting disk and pressure relief valve at Nas filter as per TCU Standard |  | FCT |  | E54 | ord | Done |  | 1 | 1 | 100% | May 18: 4
9 | Installation of relief valve and piping works at main line of product inlet line |  | FCT |  | E54 | ord | Done |  | 1 | 1 | 100% | May 18: 4
10 | Installation of bursting disk and piping works at main line of product inlet line |  | FCT |  | E54 | ord | Done |  | 1 | 1 | 100% | May 18: 4
11 | Installation of Pneumatic valves at Hot water line |  | FCT |  | E54 | ord | n/a | on-hold not part of original scope | 0 | 0 | 0% | bar: March 13
12 | Installation of Pneumatic drain valves at Hot water line |  | FCT |  | E54 | ord | n/a | on-hold not part of original scope | 0 | 0 | 0% | bar: March 13
13 | Installation of FSL and PI instruments |  | FCT |  | E54 | ord | n/a | on-hold not part of original scope | 0 | 0 | 0% | bar: March 13
14 | Offline pre-commissioning with Mheco |  | ABP | Mheco | E54 | ord | Done |  | 1 | 1 | 100% | February 9: 4
15 | Commissioning @ E45 |  |  |  | E54 | ord | Done |  | 1 | 1 | 100% | May 19: 4
16 | Commissioning @ E54 |  |  |  | E54 | ord | Done |  | 1 | 1 | 100% | June 24: 4
17 | Allignment meeting with TCU |  |  |  | E54 | ord | Done |  | 1 | 1 | 100% | May 18: 4
C. | Punchlist Works | [7 empty] | 2 | 0 | 0% | bar: March 10; May 18
18 | Replacement of bursting disc ( to blind) at E54 |  |  |  | E54 | ord |  | On-hold. Waiting for further instruction from PE and Key Personnel. | 1 | 0 | 0% | July 27: 3
19 | Relocate supply valve @ E54 and tie-in works |  |  |  | E54 | ord |  | On-hold. Waiting for further instruction from PE and Key Personnel | 1 | 0 | 0% | July 27: 3
| OSL/Vertical Start-up Assessment (Use official template) | [7 empty] | 8 | 2 | 25%
0 | Submission of OSL Assesment | to be done 1 month after credit approval |  |  |  |  | Done | Waiting for final decision from REC and CMD | 1 | 1 | 100% | May 18: 4
1 | Perform Current Operations Assessment ( COA ) | Complete requirements |  |  |  |  | On-Track | April 2024 - August 2024 | 1 | 0 | 0% | August 35: 3
2 | Initiate Management of Change ( MOC )/ HACCP | [5 empty] | n/a |  | 0 | 0 | 0%
3 | Training for Operators, Mechanics, EIs & FLMs ( AWGs & MWGs ) | [5 empty] | Done | 2024-04-01 | 1 | 1 | 100% | May 22: 4
4 | Update QMS and Standard Operational Procedure (SOP) | [5 empty] | On-Track | 2024-06-01 | 2 | 0 | 0% | June 26: 2; July 30: 3
5 | Product Commissioning | [5 empty] | On-Track | 2024-06-01 | 2 | 0 | 0% | June 26: 2; July 30: 3
6 | Hand-over of OSL related documents | [5 empty] | On-Track | 2024-08-01 | 1 | 0 | 0% | August 35: 3
VI. | Independent CIP for Falling Film Evaporator
A. | Preparation Stage
| I. Governance | [6 empty] | At the start of that project based on HL timeline | 52 | 52 | 100%
0 | Establish complete PLAN for Activity Tracker | PLAN of all Activities in I.Governance are already completed and reflected in the Activity Tracker | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
| Submit Project Compliance Schedule Assessment | Conduct assessment based on approved NIMT. For any changes on timeline, conduct another assessment. (See separate form) | Controller | [5 empty] | 0 | 0 | 0%
| Submit OSL Assessment | Based on approved NIMT (See separate form) | Controller | [5 empty] | 0 | 0 | 0%
| Submit OSL Tracker and Master schedule | Based on Submitted OSL Assessment (See separate form) | Controller | [5 empty] | 0 | 0 | 0%
1 | Establish Governance Meeting | Agenda and conduct weekly meeting | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
2 | Establish Activity Tracker | With activity tracker with approval of PM | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
3 | Establish Project Timeline | Timeline is already approved by PM and PE | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
4 | Establish ASI | ASI must be standard formst and link to link table | SE | [5 empty] | 1 | 1 | 100% | January 1: 4
5 | Establish PM Routines | Conduct weekly ASI closure governance | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
6 | Establish Project Management Dashboard Tracking | Completely inputed in the system | Controller | [5 empty] | 1 | 1 | 100% | January 1: 4
7 | Project Kick-off ( Start of the project ) | Submission of kick off material based on template and presented to the team | NPI/SE | [5 empty] | 0 | 0 | 0%
8 | Scope Detailing | Submission o f scope detailing material with approved and sign | NPI/SE | [5 empty] | 0 | 0 | 0%
9 | Design Freeze | Sign design documents ( P& ID etc.) | NPI/SE | [5 empty] | 0 | 0 | 0%
| a. Civil | [7 empty] | 0 | 0 | 0%
| ICIP Platform Perspective | [7 empty] | 1 | 1 | 100% | January 1: 4
| b. Mechanical | [7 empty] | 0 | 0 | 0%
| CIP Flow P&ID (Rotary Filter) | [7 empty] | 1 | 1 | 100% | January 1: 4
| ICIP Tank Farm - Rotary Filter | [7 empty] | 1 | 1 | 100% | January 1: 4
| Independent CIP_Approved Pump Location | [7 empty] | 1 | 1 | 100% | January 1: 4
| c. Electrical | [7 empty] | 0 | 0 | 0%
| Schematic Diagram Ph1 | [7 empty] | 1 | 1 | 100% | January 1: 4
| CIP Cable Tray Lay-Out | [7 empty] | 1 | 1 | 100% | January 1: 4
| CIP Proposed Cable Tray Layout for Ethernet to WFE | [7 empty] | 1 | 1 | 100% | January 1: 4
| CIP Proposed Control Panel | [7 empty] | 1 | 1 | 100% | January 1: 4
| CIP Proposed Top Mounting and Re-rearrangement of Instrumentation | [7 empty] | 1 | 1 | 100% | January 1: 4
| Icip-proposed shed for conductivity transmitter | [7 empty] | 1 | 1 | 100% | January 1: 4
| Location of Conductivity Transmitter | [7 empty] | 1 | 1 | 100% | January 1: 4
| ICIP- self cleaning filter at tank farm-E&A | [7 empty] | 1 | 1 | 100% | January 1: 4
10 | URS | Submit signed URS documents | NPI/SE | [5 empty] | 0 | 0 | 0%
| Self cleaning wedge wire filter for independent evaporator CIP | [7 empty] | 1 | 1 | 100% | January 1: 4
| URS_Valves for Independent CIP(Ph1) | [7 empty] | 1 | 1 | 100% | January 1: 4
| URS_Valves for Independent CIP(Ph2) | [7 empty] | 1 | 1 | 100% | January 1: 4
11 | Initiate PR |  | NPI/SE | [5 empty] | 0 | 0 | 0%
| a. Civil | [7 empty] | 0 | 0 | 0%
| b. Mechanical | [7 empty] | 0 | 0 | 0%
| 3400866735 - Rotary Filter | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4555798473 - Wedge Wire Screen for Rotary filter | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400890704 - Mechanical Works ICIP Phase 2 | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400752917 - Mechanical Works for Independent CIP Eva | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400951728 - Mechanical Works for projects 21-21 | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3401107342 - Mechanical Works Installation and Commis | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4555214136 - Ball valve with actuator DN80 | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400911238 - PNEUMATIC BALL VALVE (Brand: MECA INOX) | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400882041 - Control valve for ICIP | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400866582 - UNIQUE MIXPROOF 3-BODY ISO 101/101.6,111 | [7 empty] | 1 | 1 | 100% | January 1: 4
| c. Electrical | [7 empty] | 0 | 0 | 0%
| 3400738873 - Coffee Project Electrical Works | [7 empty] | 1 | 1 | 100% | January 1: 4
| d. Automation | [7 empty] | 0 | 0 | 0%
| 3401373879 - System Integration (SI) works for COFFE (PH2) | [7 empty] | 1 | 1 | 100% | January 1: 4
11 | PO ( Critical Matls ) | Official hard copy of PO from procurement | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
| a. Civil | [7 empty] | 0 | 0 | 0%
| b. Mechanical | [7 empty] | 0 | 0 | 0%
| 3400866735 - Rotary Filter | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4555798473 - Wedge Wire Screen for Rotary filter | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400890704 - Mechanical Works ICIP Phase 2 | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400752917 - Mechanical Works for Independent CIP Eva | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400951728 - Mechanical Works for projects 21-21 | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3401107342 - Mechanical Works Installation and Commis | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4555214136 - Ball valve with actuator DN80 | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400911238 - PNEUMATIC BALL VALVE (Brand: MECA INOX) | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400882041 - Control valve for ICIP | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400866582 - UNIQUE MIXPROOF 3-BODY ISO 101/101.6,111 | [7 empty] | 1 | 1 | 100% | January 1: 4
| c. Electrical | [7 empty] | 0 | 0 | 0%
| 3400738873 - Coffee Project Electrical Works | [7 empty] | 1 | 1 | 100% | January 1: 4
| d. Automation | [7 empty] | 0 | 0 | 0%
| 3401373879 - System Integration (SI) works for COFFE (PH2) | [7 empty] | 1 | 1 | 100% | January 1: 4
12 | Delivery ( Critical Matls ) | Physical arrival of materials in the factory | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
| a. Civil | [7 empty] | 0 | 0 | 0%
| b. Mechanical | [7 empty] | 0 | 0 | 0%
| 3400866735 - Rotary Filter | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4555798473 - Wedge Wire Screen for Rotary filter | [7 empty] | 1 | 1 | 100% | January 1: 4
| 4555214136 - Ball valve with actuator DN80 | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400911238 - PNEUMATIC BALL VALVE (Brand: MECA INOX) | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400882041 - Control valve for ICIP | [7 empty] | 1 | 1 | 100% | January 1: 4
| 3400866582 - UNIQUE MIXPROOF 3-BODY ISO 101/101.6,111 | [7 empty] | 1 | 1 | 100% | January 1: 4
| c. Electrical | [7 empty] | 0 | 0 | 0%
| d. Automation | [7 empty] | 0 | 0 | 0%
| II. Shutdown Preparation Works: |  |  |  |  | Title |  |  | 0 | 0 | 0%
1 | Ask Project Engineers for the SD Activities confirmed with the Contractor |  | NPI/SE |  |  |  |  | 1 month before Sd | 0 | 0 | 0%
2 | Submit shifting plan of project team |  | NPI/SE | [5 empty] | 0 | 0 | 0%
3 | Conduct & submit Vertical Start Up ( VSU ) Risk analysis |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
4 | Review and submit justification of manpower loading and required additional support |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submission of detailed Activity Tracker for 2024 Activities |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submit blank form startup Checklists to Controller |  | SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
6 | PEP Compliance |  | SO/QO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
7 | Risk Assessment of Methodology |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
8 | Project Kick - off w/ Stakeholders & Area Owners |  | NPI/SE |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
9 | Conduct Alignment Meeting w/ Production |  | NPI/SE | [5 empty] | 0 | 0 | 0%
10 | Discuss / Align SD Activities with project Team |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
11 | Alignment meeting with Key personnel (Contractor, PE, SO, QO, Supervisor, & Foreman) |  | NPI/SE/SO | [5 empty] | 0 | 0 | 0%
12 | Review of completenes of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
13 | Send mobilization plan and final scoping |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
14 | Project Management Plan for SD |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
15 | Plot the schedule for the execution of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
16 | Complete mobilization on site by Contractor: |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
17 | Balikatan with all contractors |  | SO |  |  |  |  | N/A | 0 | 0 | 0%
18 | Line tracing of LOTO points and submit report |  | SO |  |  |  |  | 1wk before SD | 0 | 0 | 0%
19 | Validation of LOTO Points |  | SO |  |  |  |  | 1st day of SD | 0 | 0 | 0%
20 | Submission of Quality Master Plan with Inspection Date |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
21 | Quality Management Plan - Submission of Blank Checklist |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
22 | Welding Inspection |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
23 | Submission of Start up Execution checklist |  | SE |  |  |  |  | after SD | 0 | 0 | 0%
24 | Safety Mapping |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
25 | Discuss Risk Assessment of Methodolgy (per project) |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
26 | Hazard familiarization with contractor |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
27 | Installation of Tempacil |  | SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
28 | Activity tracker for Quality |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
29 | Submit Man Power Loading Plan (per contractor) |  | SE |  |  |  |  | N/A | 0 | 0 | 0%
B. | Mechanical Works | [7 empty] | 7 | 7 | 100%
1 | Finalize SOO |  | AHI |  |  |  | Done |  | 1 | 1 | 100% | February 5: 4
| Rotary Filter # 1 | [7 empty] | 0 | 0 | 0%
| Rotary Filter # 2 | [7 empty] | 0 | 0 | 0%
| Rotary Filter # 3 | [7 empty] | 0 | 0 | 0%
| Rotary Filter # 4 | [7 empty] | 1 | 1 | 100% | March 11: 4
2 | Create program |  | ABP | Mheco |  |  | Done | Actual P&ID is not the same with the submitted P&ID as of now follow actual P&ID in the site On-going finalization of program Initial Creation of program as per sir elle. Conducted functionlity test for rotary filter #4 done last year | 1 | 1 | 100% | April 17: 4
| Rotary Filter # 1 | [7 empty] | 0 | 0 | 0%
| Rotary Filter # 2 | [7 empty] | 0 | 0 | 0%
| Rotary Filter # 3 | [7 empty] | 0 | 0 | 0%
| Rotary Filter # 4 | [7 empty] | 0 | 0 | 0%
3 | Offline Simulation | [5 empty] | Done |  | 1 | 1 | 100% | April 17: 4
4 | Risk assesment | [5 empty] | Done |  | 1 | 1 | 100% | April 17: 4
5 | Functionality Test and actual simulation based from new SOO | [5 empty] | Done |  | 2 | 2 | 100% | May 18: 4; May 19: 4
| Testing and Commissioning | [7 empty] | 1 | 0 | 0%
6 | Commissioning | [6 empty] | Production will do the schedule as per OSL | 1 | 0 | 0% | July 30: 3
| OSL/Vertical Start-up Assessment (Use official template) | [7 empty] | 5 | 1 | 20%
0 | Submission of OSL Assesment | to be done 1 month after credit approval |  |  |  |  | Done | not later than 1 month after approval | 1 | 1 | 100% | April 16: 4
1 | Perform Current Operations Assessment ( COA ) | Complete requirements | [5 empty] | June 2024 - January 2025 | 1 | 0 | 0% | December 4: 3
2 | Initiate Management of Change ( MOC )/ HACCP | [5 empty] | n/a |  | 0 | 0 | 0%
3 | Training for Operators, Mechanics, EIs & FLMs ( AWGs & MWGs ) | [5 empty] | n/a |  | 0 | 0 | 0%
4 | Update QMS and Standard Operational Procedure (SOP) | [5 empty] | n/a |  | 0 | 0 | 0%
5 | Product Commissioning | [6 empty] | 2024-06-01 | 2 | 0 | 0% | June 26: 2; October 44: 3
6 | Hand-over of OSL related documents | [6 empty] | 2025-01-01 | 1 | 0 | 0% | December 4: 3
[6 empty] | SELECTION: | STATUS:
[6 empty] | Title | On-Track
[6 empty] | CP | Delayed
[6 empty] | Ord | Cancelled
n/a
Done
on hold
Note on P9: PHMichelIb: CIP

## ASI
ACTION STATUS INDICATOR - | [9 empty] | 2024-06-29 14:53
Last Updated:
Note:
Important : Must enter MEETING DATE for the template to keep track the status of action plan
No. | Project | Date | Engineering Driver | Action Plan | Who | Support | Planned | Actual | remark | Status
|  | 2023-12-28 |  | Allignment meeting with NPI and Michrom | FCT | WGE | 2023-12-29 | 2023-12-29 |  | Done
|  | 2023-12-30 |  | Justification for cancellation of activity (GCU+) | KJT | Rhajtek | 2023-12-29 | 2023-12-29 |  | Done
|  | 2023-12-30 | To send follow up for methodology | Follow up REC for SCRF manpower |  |  | 2023-12-30 | 2023-12-30 |  | Done
|  | 2024-01-24 |  | Follow up KJT on SIR installation of sealing tank | KJT | REC | 2024-01-24 | 2024-01-24 | To be installed during production run after January CIP due to Mechanical Cost-plus not available. Priority Auto-Compactor | Done
|  | 2024-01-24 |  | Replicate edited timeline of REC to Main file. | REC | KRSC | 2024-01-27 | 2024-01-24 |  | Done
|  | 2024-01-24 |  | PEC2020 tracking to Racel. | KRSC | RPD | 2024-01-24 | 2024-01-24 |  | Done
|  | 2024-01-24 |  | Follow-up Material List on DCP on EA c\o ABP | ABP | ADC | 2024-01-27 | 2024-01-29 |  | Done
|  | 2024-01-24 |  | Send weekly report on HL OVERALL TIMELINE | [5 empty] | Done
|  | 2024-01-24 |  | Follow up ABP/SMG for the status on aircon installation (MCC ROOM) | [5 empty] | Done
|  | 2024-01-24 |  | To set GEMBA with SE for alignment on declared activities on site | RP | SE | 2024-02-19 | 2024-02-19 | March CIP on Coffee Projects | Done
|  | 2024-02-13 |  | Set meeting With PE, SE and PM for SCRF | KRSC |  | 2024-02-17 | 2024-02-17 |  | Done
|  | 2024-02-13 |  | Set meeting With PE and PM for Project handling | KRSC |  | 2024-02-13 | 2024-02-13 |  | Done
|  | 2024-02-13 |  | Set meeting for ICIP with SE and PE | KRSC |  | 2024-02-13 | 2024-02-13 |  | Done
|  | 2024-02-13 |  | Set meeting for GC Transport phase 2 with PE and SE | KRSC |  |  |  |  | Done
|  | 2024-02-13 |  | Ask SMG for the location of the delivered ducting | KRSC | SMG | 2024-02-13 | 2024-02-13 | Delivered at lay down area | Done
|  | 2024-02-21 |  | Reconfirm with MAPP if need catch-up plan on conceptual stage and for the SE plotting on 1 week time | KRSC |  | 2024-03-01 | 2024-03-01 | Yes to catch-up plan to any activities | Done
|  | 2024-02-21 |  | Ask REC for plotting on PR for FFE RARE | KRSC |  | 2024-02-24 | 2024-02-24 |  | Done
|  | 2024-02-21 |  | Ask REC what is RBC on SCRF | KRSC |  | 2024-02-24 | 2024-02-23 |  | Done
|  | 2024-02-21 |  | Ask REC for 3D Drawing approval based from TCU Standard on SCRF | KRSC |  | 2024-02-24 | 2024-02-23 | On-going Drawing. For routing next week | Done
|  | 2024-02-22 |  | Ask Timeline of Zurich Structural Integrity from AVI | KRSC |  | 2024-02-22 | 2024-02-22 |  | Done
|  | 2024-02-22 |  | Ask RADY for new timeline for Smokestack | KRSC |  | 2024-02-22 | 2024-02-22 | Received detailed timeline from RADY. To reflect on Q1 Tracking | Done
|  | 2024-02-22 |  | Ask SE and PE for allignment meeting with MAPP and PT Cerna | KRSC |  | 2024-02-22 | 2024-02-22 | PT Cerna commited to give updated timeline on Feb 23, 2024. JRUS and BDY to set allignment meeting with MAPP with PT cerna | Done
|  | 2024-02-22 |  | Ask SE and PE for action plan for the delays on Marley activities | KRSC |  | Wk 9 | 2024-02-23 | Informed SE and PE. | Done
|  | 2024-02-22 |  | Challenge schedule of Autocompactor Civil to compress to avoid the contractor for causing delay in execution | KRSC |  | 2024-02-22 | 2024-02-22 | As per RADY, cannot compress schedule. Pre-bidding may be scheduled on week. | Done
|  | 2024-02-22 |  | Kick off meeting for Van tilting should be done 2-3 weeks after approval of project. Inform SE and PE | KRSC |  | 2024-02-22 | 2024-02-22 | Informed SE and PE. To be scheduled with stakeholders as per REC | Done
|  | 2024-02-22 |  | Review timeline of Van tilting with REC to finalize | KRSC |  | 2024-02-22 | 2024-02-22 | On-going revision with REC | Done
|  | 2024-04-06 |  | Clarification sa pagbuhat og presentation for simple activities and for the previous year/finished projects bisan human |  |  | 2024-04-06 | 2024-04-06 |  | Done
|  | 2024-04-22 |  | Replotting for PE Panel timeline | KRSC | ABP | Week 17 | 2024-04-22 | ABP set new timeline for advance works on Sep 2024 SD as a separate item. | Done
|  | 2024-04-22 |  | Advance work for PEC2020 E&A works | KRSC | ABP | Week 17 | Week 17 | ABP will consult ADC for possible advance works to be declared in the activity tracker | Done
|  | 2024-04-22 |  | Advance works on EA Adaptation that are related to P&ID | KRSC | ABP | Week 17 | Week 17 | ABP will consult ADC for possible advance works to be declared in the activity tracker. Waiting for Mechanical to finalized P&ID | Done
|  | 2024-04-22 |  | Remind DTL for updated timeline for PE Panel | KRSC | DTL | Week 17 |  | As per DTL, he will start making the updated timeline Waiting for submission of final timeline | Done
|  | 2024-04-22 |  | OSL Assessment for FFE RARE | CMD | REC | Week 18 |  | Timeline to be finalized with REC and WGE due to delay in PO. Still on quotation as per REC. Need final commissioning to plot activities on OSL | Done
|  | 2024-04-22 |  | OSL Assessment GC Transport and GC Van tilting | CMD | REC | Week 18 | Week 17 | Ask CMD to make Assessment for the project | Done
|  | 2024-04-22 |  | OSL Assessment for ICIP and SCRF, to follow-up JCBaltazar | KRSC |  | Week 17 | Week 17 | JCB currently occupied by meetings No need for JCB signeture as per MAPP | Done
|  | 2024-04-22 |  | Edit OSL works to minor projects | KRSC |  | Week 17 | 2024-04-22 | As per MAPP as for now, do not include SP. For minor projects only. MAPP to assess on SP | Done
|  | 2024-04-22 |  | Update HL timeline for all projects | KRSC |  | Week 17 | 2024-04-22 | Sent to RD the projects that are due on the past months. Waiting for updated CRF. | Done
|  | 2024-04-22 |  | Ask BDY for the catch-up plan on softwater | BDY | KRSC | Week 17 | Week 17 | As per MAPP, CRF on route is not a catch-up plan. Catch-up plan is on route currently on MAPP | Done
ESCALATIONS
legend
Done
Pending
Delayed
Note on D6: Note : Input as mm/dd/yyyy
Note on I6: Note : Input as mm/dd/yyyy
Note on J6: Note : Input as mm/dd/yyyy

## Links
Timeline
DTL | KJGT | FCT | SMG | BDY | MGS
Enclosure | GCU+ | SCRF | SMG CP | BDY Over-all | MGS Over-all
Transport ph2 | Process Adaptation | ICIP | SMG MAOA
Van Tilting | Hydraulic | FFE RARE
PE Panel | SIR
Other Tracker for updating
OSL Assesment | Catch-up Plan Reports | Project Assessment | PEC2020 Over-all | DPC Tracker | OSL Tracker
CRF
Over-all High level Timeline |  | CIP Tracker | SD Tracker | Weekly Governance (Thrusday)
CP HL Over-all | HL Timeline MAOA | January | 2024-09-01 | MAOA | CP
|  | February | 2024-12-01
March
Over-all High level Scope |  | April
HL Scope Coffee | HL Scope MAOA | May |  | Coffee Projects | Milk Project
|  | June |  | PEC2020 | DHNS COMPLIANCE TO FB PREVENTION STANDARD PHASE 2
|  | July |  | Project GCU+ | SECONDARY PACKING AREA VENTILATION
Quality Files |  | August |  | SIR System Upgrade | HOMOGENIZERS&HPP COOLING WATER RECOVERY SYSTEM
JJA QO Summary Report | Quality Forms | September |  | Van Tilting | UPGRADATION OF MARLEY COOLING TOWERS
|  | October |  | Self Cleaning Filter ( E45 & E54 ) | PROJECT POPEYE(FERRIC SULPHATE DOSING EQUIPMENT)
|  | November |  | FFE RARE Filter System
My Old Files |  | December |  | iCIP( FFE & RF )
My Old Quality Files | KRSC PDAR |  |  | Green Coffee Transport System Upgrade
E54 High Pressure Water Heater
AutoCompactor
Master Schedule |  |  |  | Hydraulic
PEC2020 | CP Projects |  |  | Upgradation of E45 & E54 Final Cooler
Procurement
PO Copy CP | PO Copy MAOA

## Blank (2)
PROJECT TITLE:
AREA:
2024-06-29 14:53
| LEGEND |  | WEEK | [5 empty] | Year |  |  | 2024 | [51 empty] | 2025
|  |  | DAY | [5 empty] | Month |  |  | January |  |  |  | February |  |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December
[9 empty] | Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 = No Activity
|  |  | a. | Total Planned Activity ( Project Overall ) |  |  |  |  | Total Planned Activity ( Project Overall ) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 = Missed Activity |  | b. | Completed (for the Day) |  |  |  |  | Completed (for the Day) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 = Planned Activity |  | c. | Total Planned Activity (for the DAY) |  |  |  |  | Total Planned Activity (for the DAY) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 = Completed Activity |  | d. | Adherence ( DAILY ) --> Bar ( Target: 100% ) |  |  |  |  | Adherence ( DAILY ) --> Bar ( Target: 100% )
|  |  | e. | Completed (YTD) |  |  |  |  | Completed (YTD) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | f. | Total Planned Activity (YTD) |  |  |  |  | Total Planned Activity (YTD) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | g. | Adherence ( YTD ) |  |  |  |  | Adherence ( YTD )
|  |  | h. | Daily Target Cummulative ( Project Overall ) |  |  |  |  | Daily Target Cummulative ( Project Overall ) |  |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | i. | Daily Actuals Cummulative ( Project Overall ) |  |  |  |  | Daily Actuals Cummulative ( Project Overall )
Item | ACTIVITIES | Requirement to consider done | PIC | Contractor | AREA | Type | COMPLETION STATUS | Remarks | P | A | %
Title
A. | Preparation Stage |  |  |  |  | Title
| I. Governance | [6 empty] | At the start of that project based on HL timeline | 0 | 0 | 0%
0 | Establish complete PLAN for Activity Tracker | PLAN of all Activities in I.Governance are already completed and reflected in the Activity Tracker | Controller | [5 empty] | 0 | 0 | 0%
| Submit Project Compliance Schedule Assessment | Conduct assessment based on approved NIMT. For any changes on timeline, conduct another assessment. (See separate form) | Controller | [5 empty] | 0 | 0 | 0%
| Submit OSL Assessment | Based on approved NIMT (See separate form) | Controller | [5 empty] | 0 | 0 | 0%
| Submit OSL Tracker and Master schedule | Based on Submitted OSL Assessment (See separate form) | Controller | [5 empty] | 0 | 0 | 0%
1 | Establish Governance Meeting | Agenda and conduct weekly meeting | SE | [5 empty] | 0 | 0 | 0%
2 | Establish Activity Tracker | With activity tracker with approval of PM | SE | [5 empty] | 0 | 0 | 0%
3 | Establish Project Timeline | Timeline is already approved by PM and PE | SE | [5 empty] | 0 | 0 | 0%
4 | Establish ASI | ASI must be standard formst and link to link table | SE | [5 empty] | 0 | 0 | 0%
5 | Establish PM Routines | Conduct weekly ASI closure governance | Controller | [5 empty] | 0 | 0 | 0%
6 | Establish Project Management Dashboard Tracking | Completely inputed in the system | Controller | [5 empty] | 0 | 0 | 0%
7 | Project Kick-off ( Start of the project ) | Submission of kick off material based on template and presented to the team | NPI/SE | [5 empty] | 0 | 0 | 0%
8 | Scope Detailing | Submission o f scope detailing material with approved and sign | NPI/SE | [5 empty] | 0 | 0 | 0%
9 | Design Freeze | Sign design documents ( P& ID etc.) | NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
10 | URS | Submit signed URS documents | NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
11 | Initiate PR |  | NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
11 | PO ( Critical Matls ) | Official hard copy of PO from procurement | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
12 | Delivery ( Critical Matls ) | Physical arrival of materials in the factory | Procurement NPI/SE | [5 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
| II. Shutdown Preparation Works: | [7 empty] | 0 | 0 | 0%
1 | Ask Project Engineers for the SD Activities confirmed with the Contractor |  | NPI/SE |  |  |  |  | 1 month before Sd | 0 | 0 | 0%
2 | Submit shifting plan of project team |  | NPI/SE | [5 empty] | 0 | 0 | 0%
3 | Conduct & submit Vertical Start Up ( VSU ) Risk analysis |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
4 | Review and submit justification of manpower loading and required additional support |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submission of detailed Activity Tracker for 2024 Activities |  | NPI/SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
5 | Submit blank form startup Checklists to Controller |  | SE |  |  |  |  | 3 wks before SD | 0 | 0 | 0%
6 | PEP Compliance |  | SO/QO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
7 | Risk Assessment of Methodology |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
8 | Project Kick - off w/ Stakeholders & Area Owners |  | NPI/SE |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
9 | Conduct Alignment Meeting w/ Production |  | NPI/SE | [5 empty] | 0 | 0 | 0%
10 | Discuss / Align SD Activities with project Team |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
11 | Alignment meeting with Key personnel (Contractor, PE, SO, QO, Supervisor, & Foreman) |  | NPI/SE/SO | [5 empty] | 0 | 0 | 0%
12 | Review of completenes of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
13 | Send mobilization plan and final scoping |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
14 | Project Management Plan for SD |  | NPI/SE |  |  |  |  | N/A | 0 | 0 | 0%
15 | Plot the schedule for the execution of start up checklist |  | Controller |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
16 | Complete mobilization on site by Contractor: |  | NPI/SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
17 | Balikatan with all contractors |  | SO |  |  |  |  | N/A | 0 | 0 | 0%
18 | Line tracing of LOTO points and submit report |  | SO |  |  |  |  | 1wk before SD | 0 | 0 | 0%
19 | Validation of LOTO Points |  | SO |  |  |  |  | 1st day of SD | 0 | 0 | 0%
20 | Submission of Quality Master Plan with Inspection Date |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
21 | Quality Management Plan - Submission of Blank Checklist |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
22 | Welding Inspection |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
23 | Submission of Start up Execution checklist |  | SE |  |  |  |  | after SD | 0 | 0 | 0%
24 | Safety Mapping |  | SO |  |  |  |  | 4 wks before SD | 0 | 0 | 0%
25 | Discuss Risk Assessment of Methodolgy (per project) |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
26 | Hazard familiarization with contractor |  | SO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
27 | Installation of Tempacil |  | SE |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
28 | Activity tracker for Quality |  | QO |  |  |  |  | 2 wk before SD | 0 | 0 | 0%
29 | Submit Man Power Loading Plan (per contractor) |  | SE |  |  |  |  | N/A | 0 | 0 | 0%
B. | Mechanical Works |  |  |  |  | Title |  |  | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
| Civil Works |  |  |  |  | Title |  |  | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
| Electrical Works |  |  |  |  | Title |  |  | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
| Automation Works (Testing and Commissioning) |  |  |  |  | Title |  |  | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
| OSL Works | to be done 1 month after credit approval |  |  |  | Title |  |  | 0 | 0 | 0%
1 | Perform Current Operations Assessment ( COA ) | Complete requirements | [6 empty] | 0 | 0 | 0%
2 | Initiate Management of Change ( MOC )/ HACCP | [7 empty] | 0 | 0 | 0%
3 | Training for Operators, Mechanics, EIs & FLMs ( AWGs & MWGs ) | [7 empty] | 0 | 0 | 0%
4 | Update QMS and Standard Operational Procedure (SOP) | [7 empty] | 0 | 0 | 0%
5 | Product Commissioning | [7 empty] | 0 | 0 | 0%
6 | Hand-over of OSL related documents | [7 empty] | 0 | 0 | 0%
| Punchlist |  |  |  |  | Title |  |  | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
| Documantation |  |  |  |  | Title |  |  | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
[9 empty] | 0 | 0 | 0%
| VSU risk assessment |  |  |  |  | Title |  |  | 0 | 0 | 0%
| I. Pre-shutdown stage | [7 empty] | 0 | 0 | 0%
| VSU Assessment | [7 empty] | 0 | 0 | 0%
| Checklist | [7 empty] | 0 | 0 | 0%
| II. Execution stage | [7 empty] | 0 | 0 | 0%
| VSU Assessment | [7 empty] | 0 | 0 | 0%
| Checklist | [7 empty] | 0 | 0 | 0%
| Shutdown Preparation Works |  |  |  |  | Title |  |  | 0 | 0 | 0%
| Conduct & submit Vertical Start Up ( VSU ) Risk analysis | [7 empty] | 0 | 0 | 0%
| Submit blank form startup Checklists to Controller | [7 empty] | 0 | 0 | 0%
| PEP Compliance | [7 empty] | 0 | 0 | 0%
| Quality Management Plan - Submission of Blank Checklist | [7 empty] | 0 | 0 | 0%
| Quality Management Plan -Fully Signed | [7 empty] | 0 | 0 | 0%
| Welding Inspection | [7 empty] | 0 | 0 | 0%
| Submit Fully signed startup Checklists to Controller | [7 empty] | 0 | 0 | 0%
Title
[6 empty] | SELECTION: | STATUS:
[6 empty] | Title | On-Track
[6 empty] | CP | Delayed
[6 empty] | Ord | Cancelled
n/a
Done
on hold
Note on P9: PHMichelIb: CIP