## Summary
PROJECT NAME | STATUS | Week
|  | YTD | 31 | 32 | 33 | 34 | 35 | 36
XXXXXX | Plan |  | 31: 3
| Actual |  | 31: 2
| % Perf | #DIV/0! | 31: 66.67%

## ASI_KRSC
ACTION STATUS INDICATOR - OVERALL PEC 2020 | [12 empty] | Week 31
Last Updated: |  | 2024-07-22
Note:
Important : Must enter MEETING DATE for the template to keep track the status of action plan
No. | Date | Project Name | Action Plan / PRIORITIES FOR THE WEEK | PIC | Support | Planned Week | Actual Week | No. of Wks Delayed | Status | Target Week ( Catch-up ) | Catchup Owner | Catchup Activities | Remarks | remark
1 | 2024-01-08 | SCRF | Proposed modification drawing for E54 SCRF | FCT | FCT | 22 | 23 | 1 | Closed |  |  | On-going approval, require time to discuss with Sir JC. To confirm Sir Mark if Sir JC has alloted 1 hour per week to discuss document for docusign. |  | KVC sent new timeline from sharedpoint
2 | 2024-01-08 | SCRF | Transfer of valve from v8 to NAZ line E54 (SCRF E54 - Relocate supply valve @ E54) | FCT | REC | 22 | 23 | 1 | Closed |  |  | On-going routing, 89%
3 | 2024-01-08 | SCRF | Relocation of bursting disk E54 | FCT | REC | 22 | 23 | 1 | Closed |  |  | On-going routing, 89%
4 | 2024-01-08 | Hydraulic Upgrade | Hydraulic Project: Maintenance Plan | FCT |  | 22 |  | -22 | Overdue | 35 | FCT | Same on WK31: On-going, move to WK35, waiting for signature of Sir Echem
5 | 2024-01-08 | Hydraulic Upgrade | Hydraulic Project: Spare Parts | FCT |  | 22 |  | -22 | Overdue | 35 | FCT | Same on WK31: On-going, Move to WK35, docusign
6 | 2024-04-12 | Improvement of FFE RARE Filtering System | PO for FFE RARE Mechanical Works | FCT | REC | 23 | 25 | 2 | Closed |  |  | Ongoing approval from sir Aaron, To follow up again this week
7 | 2024-05-15 | Improvement of FFE RARE Filtering System | Approved Drawing (Mechanical) | FCT | FCT | 22 | 23 | 1 | Closed |  |  | Done routing, forwarded to Sir Ryan by Roro, forwarded to Maam Dairo from Sir Ryan.
8 | 2024-05-20 | Improvement of FFE RARE Filtering System | Pump readiness test (Electrical) | FCT | ABP | 22 | 23 | 1 | Closed
9 | 2023-12-01 | Green Coffee Van Unloading Facility | Enrollment of Dust collector MPLAN (Routing) | FCT | DTL | 22 | 25 | 3 | Closed |  |  | On-going. Sir Pingoy kuwang perma
10 | 2024-04-12 | Improvement of FFE RARE Filtering System | SOO for FFE-RARE | FCT | FCT | 23 | 24 | 1 | Closed
11 | 2024-06-13 | Spare Parts & MPLAN | Set meeting with M&I & technical store to agree spare parts to be enroll | FCT | WGE | 24 | 25 | 1 | Closed |  |  | print excel file for discussion with M&I and stores.
12 | 2024-06-19 |  | Gasket material subtitute to Peckos | FCT | WGE | 25 | 28 | 3 | Closed |  |  | Email Peckos
13 | 2024-06-19 | SCRF | Identify filter spare parts on biomass and turnover to store | FCT | WGE | 26 |  | -26 | Overdue | 32 | FCT | Waiting for po creation, Moved to WK32
14 | 2024-06-26 | SCRF | Trolley modification on all SCRF (Gathering of feedback) | FCT | WGE | 28 | 29 | 1 | Closed
15 | 2024-06-26 | ICIP | Condenstate valves commisionoing | FCT | CMD | 28 | 29 | 1 | Closed
16 | 2024-06-26 | GCCD Transport | Forward Draft MPLAN to DTL | FCT |  | 27 | 28 | 1 | Closed
17 | 2024-06-26 | SCRF | Pneumatic actuator recon & installation | FCT |  | 27 |  | -27 | Overdue | 33 | FCT | Same on WK31: Still On-going recondition by M&I.
18 | 2024-08-06 | AUTOCOMPACTOR | Pre-wetting pipe modification action plan | FCT | JRUS | 33 |  | -33 | Overdue
19 | 2024-08-06 | AUTOCOMPACTOR | Splash water from compactor to cell issue action plan | FCT | JRUS | 33 |  | -33 | Overdue
20 | [7 empty] | 0 | by when?
21 | [7 empty] | 0 | by when?
22 | [7 empty] | 0 | by when?
23 | [7 empty] | 0 | by when?
24 | [7 empty] | 0 | by when?
25 | [7 empty] | 0 | by when?
26 | [7 empty] | 0 | by when?
27 | [7 empty] | 0 | by when?
ESCALATIONS
Legend:
Done
Ongoing
Delayed
Note on C6: Note : Input as mm/dd/yyyy