## Adjusted bid based on in-house
DESCRIPTION | MAN'R | UNIT | QTY | U/RATE | AMOUNT | PROJECT | TYPE | DATE | SOURCE
mobilization |  | lot | 1 | 554600 | 554600 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Mobilization/Demobilization | 2021-08-17 | Rhajtek
demobilization/housekeeping |  | lot | 1 | 413000 | 413000 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Mobilization/Demobilization | 2021-08-17 | Rhajtek
cotton gloves |  | pair | 480 | 29.5 | 14160 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Safety Provisions | 2021-08-17 | Rhajtek
dust mask |  | bxs | 5 | 295 | 1475 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Safety Provisions | 2021-08-17 | Rhajtek
caution tape |  | roll | 1 | 1416 | 1416 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Safety Provisions | 2021-08-17 | Rhajtek
safety signages |  | lot | 1 | 14160 | 14160 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Safety Provisions | 2021-08-17 | Rhajtek
fire blanket |  | pcs | 8 | 1180 | 9440 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Safety Provisions | 2021-08-17 | Rhajtek
cip suit(28 person) |  | set | 28 | 1770 | 49560 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Safety Provisions | 2021-08-17 | Rhajtek
smaw welding machines |  | unit | 1 | 5310 | 5310 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Tools & Equipment Rentals | 2021-08-17 | Rhajtek
gtaw or tig welding machine |  | unit | 4 | 6490 | 25960 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Tools & Equipment Rentals | 2021-08-17 | Rhajtek
portable grinders 7" diaø with double insulation standard |  | unit | 4 | 4130 | 16520 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Tools & Equipment Rentals | 2021-08-17 | Rhajtek
portable grinders 4" diaø with double insulation standard |  | unit | 4 | 2950 | 11800 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Tools & Equipment Rentals | 2021-08-17 | Rhajtek
scaffolding - rental |  | lot | 1 | 224200 | 224200 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Tools & Equipment Rentals | 2021-08-17 | Rhajtek
extension ladders with certificate |  | unit | 3 | 2950 | 8850 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Tools & Equipment Rentals | 2021-08-17 | Rhajtek
hand tools (complete set of combination wrenches) metric and english standard |  | lot | 3 | 1416 | 4248 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Tools & Equipment Rentals | 2021-08-17 | Rhajtek
construction panel (both for 440 and 220 volts supply ) |  | unit | 2 | 5900 | 11800 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Tools & Equipment Rentals | 2021-08-17 | Rhajtek
endoscope |  | lot | 1 | 9440 | 9440 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Tools & Equipment Rentals | 2021-08-17 | Rhajtek
2" dia ss 304 pipe,sch 40,seamless |  | length | 2 | 10620 | 21240 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304 elbow 90 deg, sch 40,seamless |  | pcs | 6 | 495.6 | 2973.6 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304 elbow 45 deg, sch 40,seamless |  | pcs | 4 | 472 | 1888 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304 tee, sch 40,seamless |  | pcs | 1 | 1038.4 | 1038.4 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" 1/2 dia ss 304 tee, sch 40,seamless |  | pcs | 1 | 1121 | 1121 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2"x1 1/2"eccentric reducer , sch 40,seamless |  | pcs | 1 | 1416 | 1416 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2"x2 1/2"eccentric reducer , sch 40,seamless |  | pcs | 1 | 1416 | 1416 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,pn16, manual ball valve,valtaco,ss |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50, ss check valve,flap type |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn25,pn16, ss manual ball valve, 3 piece assembly,weld end |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn15,pn16, ss manual ball valve, 3 piece assembly,threaded |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1 /2" dia npt pressure gauge with fittings (0 to 25 bar) |  | set | 1 | 5310 | 5310 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss flexible connector,weld end connection |  | pcs | 2 | 5664 | 11328 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets |  | lot | 1 | 9440 | 9440 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 pipe,sch 40,iso tube |  | length | 2 | 10620 | 21240 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 elbow 90 deg, sch 40,iso |  | pcs | 6 | 495.6 | 2973.6 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 elbow 45 deg, sch 40,iso |  | pcs | 4 | 472 | 1888 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 tee, sch 40,iso |  | pcs | 1 | 1038.4 | 1038.4 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" 1/2 dia ss 304 tee, sch 40,seamless |  | pcs | 1 | 1121 | 1121 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2"x1 1/2"eccentric reducer , sch 40,seamless |  | pcs | 1 | 1416 | 1416 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2"x2 1/2"eccentric reducer , sch 40,seamless |  | pcs | 1 | 1416 | 1416 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
transfer pump,50m3/hr |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn100,pn16, manual ball valve,valtaco,ss |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn100, ss check valve,flap type |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn25,pn16, ss manual ball valve, 3 piece assembly,weld end |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn15,pn16, ss manual ball valve, 3 piece assembly,threaded |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1 /2" dia npt pressure gauge with fittings (0 to 25 bar) |  | set | 1 | 5310 | 5310 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn100 ss ss flexible connector |  | pcs | 2 | 9440 | 18880 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn100,ss 304 flange,weld neck type,with ss bolt,nut,washer and gasket |  | pair | 2 | 5133 | 10266 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 pipe,sch 40, seamless |  | length | 16 | 35400 | 566400 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia sms union,ss 304 |  | pcs | 2 | 3540 | 7080 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1" dia ss 304 pipe,sch 40 seamless, |  | length | 1 | 5900 | 5900 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 elbow 90 deg, sch 40,seamless |  | pcs | 22 | 2242 | 49324 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 elbow 45 deg, sch 40,seamless |  | pcs | 6 | 1770 | 10620 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 tee 45 deg, sch 40,seamless |  | pcs | 1 | 2714 | 2714 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1" dia ss 304 elbow 90 deg, sch 40,seamless |  | pcs | 4 | 177 | 708 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets |  | lot | 1 | 37760 | 37760 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn100, ss mixed proof valve |  | pcs | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn80, ss mixed proof valve |  | pcs | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 sms union |  | pcs | 3 | 3540 | 10620 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 sms union |  | pcs | 3 | 1888 | 5664 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1 1/2" dia ss 304 sms union |  | pcs | 1 | 535.72 | 535.72 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 pipe,sch 40, seamless |  | length | 7 | 35400 | 247800 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 pipe,sch 40 seamless |  | length | 1 | 23600 | 23600 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia x 3" dia ss 304 concentric reducer,sch 40,seamless |  | pcs | 4 | 2773 | 11092 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1 1/2" dia ss 304 pipe,sch 40 seamless |  | length | 1 | 8260 | 8260 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 elbow 90 deg, sch 40,seamless, |  | pcs | 14 | 2242 | 31388 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 elbow 45 deg, sch 40,seamless |  | pcs | 4 | 1770 | 7080 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 tee, sch 40,seamless |  | pcs | 1 | 2714 | 2714 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 tee, sch 40,seamless |  | pcs | 4 | 2159.4 | 8637.6 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
support and brackets |  | lot | 0 | 24780 | 0 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn100,pn16, pneumatic ball valve,ss |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn100, temperature indicator |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 sms union |  | pcs | 1 | 3540 | 3540 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304 sms union |  | pcs | 1 | 826 | 826 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia x 2" dia ss 304 concentric reducer,sch 40,iso,seamless |  | pcs | 2 | 2478 | 4956 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia ss 304 elbow 90 deg, sch 40,iso,seamless |  | pcs | 2 | 4484 | 8968 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn80,pn16, pneumatic butterflyvalve,ss |  | set | 5 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn25,pn16, pneumatic butterflyvalve,ss |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn80,flow indicator transmitter |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn80,pn16 flow control valve |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn80,temperature indicator transmitter |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia,iso tubes, 304 pipe,sch 40, ,seamless |  | length | 4 | 21240 | 84960 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1" dia iso tubes, 304 pipe,sch 40, ,seamless |  | length | 2 | 6490 | 12980 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia,elbow 90 deg,ss304,sch 40, iso, seamless |  | pcs | 10 | 1888 | 18880 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 elbow 45 deg, sch 40,iso, seamless |  | pcs | 2 | 2360 | 4720 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 tee, sch 40,iso ,seamless |  | pcs | 3 | 2596 | 7788 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia x 1" dia ss 304 concentric reducer,sch 40,iso,seamless |  | pcs | 2 | 2124 | 4248 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia x 1/2" dia ss 304 tee reducer,sch 40,iso,seamless |  | pcs | 1 | 2696.3 | 2696.3 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1" dia ss 304 elbow 90 deg, sch 40,iso,seamless |  | pcs | 8 | 649 | 5192 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1" dia ss 304 elbow 45 deg, sch 40,iso,seamless |  | pcs | 4 | 708 | 2832 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets |  | lot | 1 | 17700 | 17700 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn80,pn16, pneumatic butterflyvalve,ss |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,pn16, pneumatic butterflyvalve,ss |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn80,ss check valve,flap type |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1 /2" dia npt pressure gauge with fittings (0 to 25 bar) |  | set | 1 | 5310 | 5310 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia iso tube,sch 40,seamless |  | length | 8 | 28320 | 226560 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia iso elbow,90 deg,sch 40,seamles |  | length | 3 | 4484 | 13452 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia iso elbow,45 deg,sch 40,seamless |  | length | 3 | 2822.56 | 8467.68 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia sms union,ss 304 |  | length | 3 | 3540 | 10620 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia iso tube,sch 40, seamless |  | length | 3 | 21240 | 63720 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304 pipe,sch 40 seamless |  | length | 1 | 10620 | 10620 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 elbow 90 deg, sch 40,seamless, iso |  | pcs | 6 | 1888 | 11328 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 elbow 45 deg, sch 40,seamless,iso |  | pcs | 2 | 2360 | 4720 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 tee, sch 40,seamless,iso |  | pcs | 3 | 2596 | 7788 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia x 2 1/2" dia ss 304 concentric reducer,sch 40,seamless,iso |  | pcs | 4 | 2655 | 10620 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia x 1 1/2" dia ss 304 concentric reducer,sch 40,seamless,iso |  | pcs | 1 | 2537 | 2537 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304 elbow 90 deg, sch 40,seamless,iso |  | pcs | 8 | 495.6 | 3964.8 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304 elbow 45 deg, sch 40,seamless,iso |  | pcs | 4 | 472 | 1888 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets |  | lot | 1 | 42480 | 42480 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn80, ss mixed proof valve |  | pcs | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia iso tube pipe,sch 40,seamless,ss 304 |  | length | 11 | 28320 | 311520 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia elbow,ss 304,90 deg,sch 40,seamless, iso |  | pcs | 20 | 4484 | 89680 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
4" dia elbow,ss 304,45 deg,sch 40,seamless,iso |  | pcs | 6 | 2822.56 | 16935.36 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia sms union,ss 304 |  | pcs | 3 | 1888 | 5664 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 pipe,sch 40, iso tube,seamless |  | length | 1 | 21240 | 21240 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
3" dia ss 304 elbow 90 deg, sch 40,iso |  | pcs | 6 | 1888 | 11328 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets |  | lot | 0 | 38940 | 0 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn40,conductivity meter |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn40,pn16, pneumatic butterflyvalves |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn40,ss mixed proof valve |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn 40,sight glass |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1 1/2" dia ss 304 pipe, sch 40,seamless |  | length | 2 | 8260 | 16520 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1 1/2" dia ss 304, elbow 90 deg,sch 40,seamless |  | pcs | 8 | 413 | 3304 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1 1/2" dia ss 304, elbow 45 deg,sch 40,seamless |  | pcs | 4 | 389.4 | 1557.6 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1 1/2" dia ss 304 tee, sch 40,seamless |  | pcs | 1 | 767 | 767 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets |  | lot | 1 | 9440 | 9440 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,pn16, pneumatic ball valve,valtaco,ss |  | set | 5 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,pn16, manual ball valve,valtaco,ss |  | set | 5 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn25,pn16, manual ball valve,valtaco,ss |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,sight glass |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,conductivity meter |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,ss mixed proof valve |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304 pipe, sch 40,seamless |  | length | 15 | 10620 | 159300 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1" dia ss 304 pipe, sch 40,seamless |  | length | 1 | 6490 | 6490 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304, elbow 90 deg,sch 40,seamless |  | pcs | 28 | 495.6 | 13876.8 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304, elbow 45 deg,sch 40,seamless |  | pcs | 6 | 472 | 2832 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia ss 304 tee, sch 40,welded |  | pcs | 7 | 1038.4 | 7268.8 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
2" dia sms union,ss 304 |  | pcs | 10 | 826 | 8260 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets |  | lot | 1 | 44840 | 44840 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,ss mixed proof valve |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,conductivity meter |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets |  | lot | 1 | 5310 | 5310 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,pn16, pneumatic butterflyvalve,valtaco,ss |  | set | 3 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets & fittings |  | lot | 1 | 8850 | 8850 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,pn16, pneumatic butterflyvalve,valtaco,ss |  | set | 2 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets & fittings |  | lot | 1 | 5900 | 5900 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,pn16, pneumatic butterflyvalve,valtaco,ss |  | set | 3 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,conductivity meter |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets & fittings |  | lot | 1 | 10030 | 10030 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,pn16, pneumatic butterflyvalve,valtaco,ss |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets & fittings |  | lot | 1 | 4130 | 4130 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
dn50,pn16, pneumatic butterflyvalve,valtaco,ss |  | set | 1 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
supports and brackets & fittings |  | lot | 1 | 4130 | 4130 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
air filter |  | pcs | 3 |  |  | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1/2" dia ball valve,3 piece assembly,ss 304,threaded or welded type |  | pcs | 3 | 1062 | 3186 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
pressure gauge - 20 bars |  | pcs | 3 | 4130 | 12390 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
pressure gauge assembly fittings (pigtail,nipple,etc.) |  | Set | 3 | 708 | 2124 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
1/2" dia b.i. pipe,sch 40 |  | length | 10 | 767 | 7670 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
fittings for compressed air line |  | lot | 1 | 7670 | 7670 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
painting works |  | lot | 1 | 7080 | 7080 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Materials | 2021-08-17 | Rhajtek
cutting discs, 7" diaø, " diatyrolit" dia brand, 8,600 rated rpm |  | pcs | 50 | 135.7 | 6785 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
cutting discs, 4" diaø, " diatyrolit" dia brand, 15,300 rated rpm |  | pcs | 300 | 34.22 | 10266 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
grinding discs, 4" diaø, " diatyrolit" dia brand, 15,300 rated rpm |  | pcs | 300 | 34.22 | 10266 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
grinding discs, 7" diaø, " diatyrolit" dia brand, 8,600 rated rpm |  | pcs | 50 | 135.7 | 6785 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
tungsten |  | pcs | 30 | 118 | 3540 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
ss filler rod, 304 |  | kgs | 40 | 519.2 | 20768 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
ss welding rods, 1/8" diaø |  | kgs | 15 | 590 | 8850 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
teflon tape |  | roll | 10 | 17.7 | 177 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
argon gas |  | cyl | 100 | 4366 | 436600 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
tig cleene |  | kgs | 4 | 767 | 3068 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
buffing soap |  | pcs | 4 | 389.4 | 1557.6 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
sand paper, # 120 |  | pcs | 80 | 17.7 | 1416 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
sans paper, # 400 |  | pcs | 80 | 17.7 | 1416 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
flap wheel, 4" diaø |  | pcs | 50 | 54.28 | 2714 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
oxygen |  | cyl | 4 | 531 | 2124 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
acetylene |  | cyl | 2 | 1593 | 3186 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
miscelleneous |  | lot | 1 | 154621.3 | 154621.3 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Consumables | 2021-08-17 | Rhajtek
project manager | 1 | days | 15 | 2950 | 44250 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Labor | 2021-08-17 | Rhajtek
project engineer/project supervisor | 1 | days | 45 | 1770 | 79650 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Labor | 2021-08-17 | Rhajtek
quality officer - certified | 1 | days | 45 | 1180 | 53100 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Labor | 2021-08-17 | Rhajtek
safety officer-s03 | 1 | days | 45 | 1416 | 63720 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Labor | 2021-08-17 | Rhajtek
foreman | 1 | days | 45 | 1180 | 53100 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Labor | 2021-08-17 | Rhajtek
fabricators/fitter | 4 | days | 45 | 1121 | 201780 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Labor | 2021-08-17 | Rhajtek
welders | 4 | days | 45 | 1062 | 191160 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Labor | 2021-08-17 | Rhajtek
skilled helpers/scaffolders | 12 | days | 45 | 944 | 509760 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Labor | 2021-08-17 | Rhajtek
electrician | 1 | days | 45 | 1062 | 47790 | INDEPENDENT CIP EVAPORATOR - PHASE 2 | Labor | 2021-08-17 | Rhajtek