## cleaned
Project Name | Description of Issue | Date initiated | Activity Category | Incident name | Original Schedule | Detailed Cause/Reason | Category | Reason Code | Catch up plan activity | Who | When | Overall completion | Prepared By
AFBB Smokestack | Delayed | 2024-03-04 | Civil | Risk Assessment of Methodology | 2024-02-24 | Ravago did not submit load chart for 500T | Procurement | R02 | Follow-up Ravago | SMG |  |  | SMG | Ravago did not submit load chart for 500T | Procurement
AFBB Smokestack | Delayed | 2024-03-04 | Civil | Lifting Methodology | 2024-02-24 | Ravago did not submit load chart for 500T | Procurement | R02 | Follow-up Ravago | SMG |  |  | SMG | Ravago did not submit load chart for 500T | Procurement
GC Transport Upgrade Ph 1 | Delayed | 2024-03-04 | Mechanical | Approval of structural analysis for scaffolding | 2024-03-01 | Structural Analysis approval | Design/Engineering | R06 | Close monitor, Follow-up and Render OT | DTL | 2024-03-06 | Delayed |  | Structural Analysis approval | Design/Engineering
GC Transport Upgrade Ph 1 | Delayed | 2024-03-04 | Mechanical | Approval of PEP | 2024-03-01 | Structural Analysis approval | Design/Engineering | R06 | Close monitor, Follow-up and Render OT | DTL | 2024-03-06 |  |  | Structural Analysis approval | Design/Engineering
GC Transport Upgrade Ph 1 | Delayed | 2024-03-04 | Mechanical | Installation of Lifting Provision no. 2 (Mechanical Boom) | 2024-03-02 | Delayed due to structural analysis | Design/Engineering | R06 | Close monitor, Follow-up and Render OT | DTL | 2024-03-07 | Delayed |  | Delayed due to structural analysis | Design/Engineering
Independent CIP for Falling Film Evaporator | Delayed | 2024-03-02 | Mechanical | Create program | 2024-03-01 | Actual P&ID is not the same with the submitted P&ID, as of now follow actual P&ID in the site, On-going finalization of program | Design/Engineering | R06 | Weekly Meeting with production and project team. Use actual P&ID for continuation | FCT | 2024-03-04 | Delayed |  | Actual P&ID is not the same with the submitted P&ID, as of now follow actual P&ID in the site, Ongoing finalization of program | Design/Engineering
Independent CIP for Falling Film Evaporator | Delayed | 2024-03-02 | Mechanical | Offline Simulation | 2024-03-01 | To reschedule meeting with production, mheco and project Team | Communication | R06 | Weekly Meeting with production and project team. Use actual P&ID for continuation | FCT | 2024-03-04 |  |  | To reschedule meeting with production, mheco and project Team | Communication
Independent CIP for Falling Film Evaporator | Delayed | 2024-03-02 | Mechanical | Risk assesment | 2024-03-02 | To reschedule meeting with production, mheco and project Team | Communication | R06 | Weekly Meeting with production and project team. Use actual P&ID for continuation | FCT | 2024-03-04 |  |  | To reschedule meeting with production, mheco and project Team | Communication
GC Transport Upgrade Ph 1 | Delayed | 2024-03-12 | Mechanical | Modification of Cyclonic Hopper no. 3(Outlet) | 2024-03-09 | If will be done after lifting of new cyclonic to silo since it will have 3 days to perform | Change in Plan | R06 | Render OT | DTL | 2024-03-14 | On-track | DTL | If will be done after lifting of new cyclonic to silo since it will have 3 days to perform | Change in Plan
GC Transport Upgrade Ph 1 | Delayed | 2024-03-12 | Mechanical | Installation of cyclonic hopper #3 | 2024-03-09 | Structural Ananlysis approval for silo | Design/Engineering | R06 | Render OT | DTL | 2024-03-16 | On-track | DTL | Structural Analysis approval for silo | Design/Engineering
SCRF (self cleaning rotary filter) | Delayed | 2024-03-12 | Mechanical | Allignment meeting with TCU | 2024-03-08 | TCU not available (on leave) | Resource Availability | R06 | Join Meeting on March 15, 2024 | FCT | 2024-03-15 | On-track | FCT | TCU not available (on leave) | Resource Availability
Independent CIP for Falling Film Evaporator | Delayed | 2024-03-12 | Mechanical | Create program | 2024-03-09 | P&ID alignment | Design/Engineering | R06 | Waiting for production Schedule / Week 12 | FCT | 2024-03-12 | On-track | FCT | P&ID alignment | Design/Engineering
Independent CIP for Falling Film Evaporator | Delayed | 2024-03-12 | Mechanical | Offline Simulation | 2024-03-08 | P&ID alignment | Design/Engineering | R06 | Waiting for production Schedule / Week 12 | FCT | 2024-03-12 |  | FCT | P&ID alignment | Design/Engineering
Independent CIP for Falling Film Evaporator | Delayed | 2024-03-12 | Mechanical | Actual simulation (Water run) | 2024-03-09 | P&ID alignment | Design/Engineering | R06 | Waiting for production Schedule / Week 12 | FCT | 2024-03-12 |  | FCT | P&ID alignment | Design/Engineering
AFBB Smokestack | Delayed | 2024-03-11 | Electrical | Installation of Lightning Arrester | 2024-03-11 | Civil works was delayed | Construction | R06 | Week 14 | MGS | 2024-04-05 | Delayed | MGS | Civil works was delayed | Construction
GC Transport Upgrade Ph 1 | Delayed | 2024-03-19 | Mechanical | Modification of Cyclonic Hopper no. 3(Outlet) | 2024-03-13 | Prioritized site activities | Project Prioritization | R03 | After site activities, render OT | DTL | 2024-04-06 | Delayed | DTL | Prioritized site activities | Project Prioritization
Green Coffee Van Unloading | Delayed | 2024-03-19 | Mechanical | Project Kick-off ( Start ): Dust Collector | 2024-03-15 | Production will use the GC Tilting | Other | R03 | After site activities, render OT | DTL | 2024-04-06 | Delayed | DTL | Production will use the GC Tilting | Other
Green Coffee Van Unloading | Delayed | 2024-03-18 | Civil | Enclosure inside | 2024-02-26 | Production will use the GC Tilting | Other | R07 | Waiting for Production Schedule | SMG |  | Delayed | SMG | Production will use the GC Tilting | Other
Green Coffee Van Unloading | Delayed | 2024-03-18 | Mechanical | PO release: Dust Collector | 2024-03-15 | Delay on approval of the PR to PO (PR submitted: Feb 01, 2024 | Approval Process | R14 | Follow-up and escalate on the PR to PO meeting with ESD | WGE | 2024-04-06 | Delayed |  | Delay on approval of the PR to PO (PR submitted: Feb 01, 2024) | Approval Process
Improvement of FFE RARE Filtering System | Delayed | 2024-03-18 | Mechanical | Fully signed URS | 2024-03-16 | No signature yet from JCBaltazar | Approval Process | R15 | Send follow-up email | FCT | 2024-03-29 | On-track | FCT | No signature yet from JCBaltazar | Approval Process
AFBB Smokestack | Delayed | 2024-03-18 | Civil | Lifting and installation of Smokestack and Platform | 2024-03-11 | Priority Installation of Stack | Project Prioritization | R03 | Overtime | SMG | 2024-03-29 | On-track | SMG | Priority Installation of Stack | Project Prioritization
SCRF (self cleaning rotary filter) | Delayed | 2024-03-18 | Mechanical | Allignment meeting with TCU/ Coordination meeting w/ TCU for discussion of existing set up | 2024-03-15 | TCU not available | Resource Availability | R02 | Reschedule meeting with TCU on Week 12 | REC | 2024-03-22 | On-track |  | TCU not available | Resource Availability
Auto-compactor | Delayed | 2024-03-18 | Civil | Project Kick-off ( Start ): Maintenance Platform | 2024-03-15 | Priority other projects: AFBB Smokestack Upgrade | Project Prioritization | R03 | Overtime | SMG | 2024-03-29 | On-track | SMG | Priority other projects: AFBB Smokestack Upgrade | Project Prioritization
Auto-compactor | Delayed | 2024-03-18 | Civil | Scope detailing | 2024-03-15 | Priority other projects: AFBB Smokestack Upgrade | Project Prioritization | R03 | Overtime | SMG | 2024-03-29 | On-track | SMG | Priority other projects: AFBB Smokestack Upgrade | Project Prioritization
Auto-compactor | Delayed | 2024-03-18 | Civil | Design Freeze | 2024-03-16 | Priority other projects: AFBB Smokestack Upgrade | Project Prioritization | R03 | Overtime | SMG | 2024-03-29 | On-track | SMG | Priority other projects: AFBB Smokestack Upgrade | Project Prioritization
Auto-compactor | Delayed | 2024-03-18 | Civil | Routing and approval of drawing | 2024-03-11 | Priority other projects: AFBB Smokestack Upgrade | Project Prioritization | R03 | Overtime | SMG | 2024-03-29 | On-track | SMG | Priority other projects: AFBB Smokestack Upgrade | Project Prioritization
Upgradation of Marley Cooling Tower | Delayed | 2024-03-18 | Mechanical | Demolition of Cooling tower #6 | 2024-03-16 | Included in danger zone area during Smokestack lifting civil activity | Safety | R16 | Overtime | ALC | 2024-03-22 | On-track | FCT | Included in danger zone area during Smokestack lifting civil activity | Safety
PEC2020 - E54 Spot Cooling | Delayed | 2024-03-18 | Mechanical | Installation of E54 Spot Cooling duct | 2024-03-16 | High Profile Visitor | Other | R03 | Render OT | DTL | 2024-03-22 | Delayed | DTL | High Profile Visitor | Other
PEC2020 - E54 Spot Cooling | Delayed | 2024-03-18 | Mechanical | PO release | 2024-03-16 | Delay on approval of the PR to PO (PR submitted: Feb 12, 2024 | Approval Process | R14 | Follow-up and escalate on the PR to PO meeting with ESD | WGE | 2024-04-06 | Delayed |  | Delay on approval of the PR to PO (PR submitted: Feb 12, 2024) | Approval Process
PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-20 | Mechanical | Installation of screen window - entire assembly in E54 | 2024-03-16 | Too tight timeline due to delay release of PO | Other | R14 | Prioritized PEP approval, fabrication and installation of E54 screen window | KJT | 2024-03-22 | Delayed | KJT | Too tight timeline due to delay release of PO | Other
PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-20 | Mechanical | Installation of scaffolding, main frame and screen frame, PEP approval in E45 | 2024-03-16 | Too tight timeline due to delay release of PO and additional scope (extension of E54 scaffolding) | Other | R14 | Daily overtime and alignment meeting with contractor | KJT | 2024-03-29 | Delayed | KJT | Too tight timeline due to delay release of PO and additional scope (extension of E54 scaffolding) | Other
PEC2020-EA Process Adaptation | Delayed | 2024-03-20 | Electrical | URS and Critical Material | 2024-02-23 | Process adaptation P&ID on-going | Design/Engineering | R10 | Close coordination with team, set meeting with mechanical team | ABP | 2024-03-22 | Delayed | ABP | Process adaptation P&ID on-going | Design/Engineering
PEC2020-Installation of New PE PANELS | Delayed | 2024-03-20 | Electrical | Installation of cable trays | 2024-03-22 | Need to revise timeline because of possibility production will not allow us | Other | R10 | Need to revise timeline | ABP | 2024-03-29 | Delayed | ABP | Need to revise timeline because of possibility production will not allow us | Other
PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade | Delayed | 2024-03-20 | Electrical | Installation of cable tray raceway | 2024-03-22 | Need to revise timeline because of possibility production will not allow us | Other | R10 | Need to revise timeline | ABP | 2024-03-29 | Delayed | ABP | Need to revise timeline because of possibility production will not allow us | Other
PEC2020-Extraction 54 PEC2020 PLC Upgrade | Delayed | 2024-03-20 | Electrical | PO for critical instrument | 2024-03-16 | PO for CLC CPU - done, waiting for delivery | Procurement | R09 | Ask ADC for PO Copy | ABP | 2024-03-29 | Delayed | ABP | PO for CLC CPU - done, waiting for delivery | Procurement
PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-25 | Mechanical | Cleaning/Polishing of screen window in E54 | 2024-03-22 | Cannot install movable scaffolding due to lifting hoist cannot remove the cell filters beside the window | Construction | R06 | Proceed the cleaning in low level portion of the window | KJT | 2024-03-29 | Delayed | KJT | Cannot install movable scaffolding due to lifting hoist cannot remove the cell filters beside the window | Construction
PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-04-01 | Mechanical | Installation of Screen window in E45 | 2024-03-29 | Prioritized E54 scaffolding and polishing of screen window frame | Project Prioritization | R12 | Overtime of manpower | KJT | 2024-04-05 | Delayed | KJT | Prioritized E54 scaffolding and polishing of screen window frame | Project Prioritization
PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-25 | Mechanical | Cleaning/Polishing of screen window in E54 | 2024-03-22 | Cannot install movable scaffolding due to lifting hoist cannot remove the cell filters beside the window | Construction | R06 | Proceed the cleaning in low level portion of the window | KJT | 2024-03-29 | Delayed | KJT | Cannot install movable scaffolding due to lifting hoist cannot remove the cell filters beside the window | Construction
PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-04-01 | Mechanical | Installation of screen window in E45 | 2024-03-29 | Prioritized E54 scaffolding and polishing of screen window frace | Project Prioritization | R12 | Overtime manpower | KJT | 2024-04-05 | Delayed | KJT | Prioritized E54 scaffolding and polishing of screen window frame | Project Prioritization
Upgradation of Marley Cooling Tower | Delayed | 2024-04-10 | Mechanical | Installation of mechanical components, upper and lower cylinder, and testing of marley #6 | 2024-04-05 | JAV contractor not onsite due to manpower availability | Resource Availability | R01 | Priority Delayed activity and pause the advance works (all contractor focus on delayd activities) | ALC | 2024-04-19 | On-track | ALC | JAV contractor not onsite due to manpower availability | Resource Availability
PEC2020-Installation of New PE PANELS | Cancellation | 2024-04-11 | Electrical | Timeline adjustment | 2024-04-05 | Unable to perorm the activities due to continuous production run | Other | R09 | Revised timeline to 2025 Annual SD | ABP | 2024-07-26 | On-track | ABP | Unable to perform the activities due to continuous production run | Other
PEC2020-EA Process Adaptation | Cancellation | 2024-04-11 | Electrical | Timeline adjustment | 2024-04-05 | Unable to perorm the activities due to continuous production run | Other | R09 | Revised timeline to 2025 Annual SD | ABP | 2024-07-26 |  | ABP | Unable to perform the activities due to continuous production run | Other
PEC2020-Extraction 54 PEC2020 PLC Upgrade | Cancellation | 2024-04-11 | Electrical | Timeline adjustment | 2024-04-05 | Unable to perorm the activities due to continuous production run | Other | R09 | Revised timeline to 2025 Annual SD | ABP | 2024-07-26 |  | ABP | Unable to perform the activities due to continuous production run | Other
PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade | Cancellation | 2024-04-11 | Electrical | Timeline adjustment | 2024-04-05 | Unable to perorm the activities due to continuous production run | Other | R09 | Revised timeline to 2025 Annual SD | ABP | 2024-07-26 |  | ABP | Unable to perform the activities due to continuous production run | Other
PEC2020-Replacement of Ventillation duct at loading area(ph1A) | Cancellation | 2024-04-11 | Mechanical | Lifting and installation of ducts Rmoval of obstacles (angle bar, etc) | 2024-04-05 | Area is congested Give way to floor painting activities | Construction | R16 | Render OT | DTL | 2024-04-12 | Delayed | DTL | Area is congested Give way to floor painting activities | Construction
Green Coffee Van Unloading | Delayed | 2024-04-11 | Mechanical | Kick-off Scope detailing Design Freeze | 2024-04-05 | Scope detailing is on-going route Kick-off cration is on-going Design Freeze approved for construction is on-going routing | Design/Engineering | R06 | Render OT and time management | DTL | 2024-04-19 | Delayed | DTL | Scope detailing is on-going route Kick-off creation is on-going Design Freeze approved for construction is on-going routing | Design/Engineering
Safety Upgrade of E54 Cell cover | Delayed | 2024-04-11 | Mechanical | Tagging of lines and equipment | 2024-04-05 | Delay preparation of tags | Documentation | R06 | Set new timeline, print all tags for preparation | FCT | 2024-05-31 | Delayed | FCT | Delay preparation of tags | Documentation
Independent CIP for Falling Film Evaporator | Delayed | 2024-04-11 | Mechanical | Finalized SOO, Create program, offline simulation, risk assessment, actual simuation. | 2024-04-05 | Delayed programm creation | Other | R01 | Set new timeline agreed by all stakeholders | FCT | 2024-04-26 | On-track | FCT | Delayed program creation | Other
Green Coffee Van Unloading | Cancellation | 2024-04-11 | Electrical | Tapping of temporary LDP power supply, Installation of cable tray droppings, and installation of wirings of GC van tilting for motor controls | 2024-04-05 | Prioritized removal of cable tray ladder and installation of new cable tray and harnessing of wires since it involves working on heights | Construction | R12 | Next CIP schedule Provide scaffolding | ABP | 2024-05-03 | On-track | ABP | Prioritized removal of cable tray ladder and installation of new cable tray and harnessing of wires since it involves working on heights | Construction
AFBB Smokestack | Delayed | 2024-04-11 | Electrical | Installation of lightning arrester rod | 2024-04-05 | Contractors PEP was declined by SHE due to lacking safety documents | Safety | R11 | Cost-plus to back up | MGS | 2024-04-19 | Delayed | MGS | Contractors PEP was declined by SHE due to lacking safety documents | Safety
PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-04-12 | Mechanical | Scope detailing Kick-off | 2024-02-10 | Need alignment meeting with supplier for technical clarification | Communication | R06 | Need alignment meeting with supplier | DTL | 2024-05-03 | Delayed | DTL | Need alignment meeting with supplier for technical clarification | Communication
GC Transport Upgrade Ph 2 | Delayed | 2024-04-12 | Mechanical | Kick-off Scope detailing Design Freeze | 2024-02-23 | Cannot proceed this activity, we need to finish first technical clarification (Dust collector) | Design/Engineering | R06 | Allignment meeting with supplier | DTL | 2024-05-03 | Delayed | DTL | Cannot proceed this activity, we need to finish first technical clarification (Dust collector) | Design/Engineering
PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-04-12 | Mechanical | Installation of flatbar, fullwelding of hinges | 2024-04-05 | Additional scope, installation of flatbar above window | Construction | R06 | Manpower overtime | KJT | 2024-04-12 | Delayed | KJT | Additional scope, installation of flatbar above window | Construction
SIR E45 | Cancellation | 2024-04-12 | Mechanical | Installation of E45 Pneumatic cylinder | 2024-04-05 | prioritized self-cleaning (Contractor), No EI to calibrate the load cell and lacking of pin | Construction | R13 | Machining of pin and Coordinate with EI | KJT | 2024-05-03 | On-track | KJT | Prioritized self-cleaning (Contractor), No EI to calibrate the load cell and lacking of pin | Construction
GCU+ | Cancellation | 2024-04-12 | Mechanical | Installaition of V5.1 flashing plate in E54 | 2024-04-05 | Plan is to install flashing plate when production costplus will replace V6.1 pipes for cleaning, they cancell the plan cleaning. | Change in Plan | R12 | To install next replacement of V6.1 | KJT | 2024-05-03 | On-track | KJT | Plan is to install flashing plate when production costplus will replace V6.1 pipes for cleaning, they cancel the plan cleaning. | Change in Plan
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-13 | Mechanical | Delivery of PM, Tuflin and Mixed proof valves | 2024-09-07 | Finalization of P&ID and material list with Paolo and encountered problem in Procurement Processing. | Procurement | R08 | To follow-up procurement | KJT | 2024-11-16 | On-track | KJT | Finalization of P&ID and material list with Paolo and encountered problem in Procurement Processing. | Procurement
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-13 | Mechanical | PO of PM, Tuflin and mixed proof valves | 2024-01-06 | Finalization of P&ID and material list with Paolo and encountered problem in Procurement Processing. | Procurement | R08 | To follow-up procurement | KJT | 2024-05-31 | On-track | KJT | Finalization of P&ID and material list with Paolo and encountered problem in Procurement Processing. | Procurement
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-15 | Mechanical | Design Freeze, Kick-off and Scope detailing | 2024-02-02 | Cancelled Meeting with TCU | Communication | R08 | Manpower overtime so that we can present to TCU the pending drawings | KJT | 2024-06-21 | On-track | KJT | Cancelled Meeting with TCU | Communication
GC Transport Upgrade Ph 1 | Delayed | 2024-04-20 | Mechanical | Submission of Welding Inspection and 5S | 2024-04-05 | Focus on clearing areas | Other | R12 | Submit on Week 17 | JJA | 2024-04-26 | Delayed | JJA | Focus on clearing areas | Other
AFBB Smokestack | Delayed | 2024-04-20 | Civil | Submission of Welding Inspection and 5S | 2024-04-05 | Focus on clearing areas | Other | R12 | Submit on Week 17 | JJA | 2024-04-26 | Delayed | JJA | Focus on clearing areas | Other
Auto-compactor | Delayed | 2024-04-20 | Civil | Design Freeze on Civil drawing | 2024-04-19 | JCB is un available due to currenty occupied with urgent matters | Resource Availability | R06 | Approach him and follow-up | RES | 2024-04-26 | Delayed | RES | JCB is unavailable due to currently occupied with urgent matters | Resource Availability
AFBB Smokestack | Delayed | 2024-04-20 | Civil | Cladding works and Demobilization | 2024-04-13 | Prioritized cleaning of the area for visitor | Other | R12 | OT | SMG | 2024-05-03 | Delayed | SMG | Prioritized cleaning of the area for visitor | Other
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-20 | Mechanical | Delayed PO for Valves and sight glass | 2024-04-13 | Delayed P&ID and material list approval. Some details were revised | Approval Process | R12 | Focus on the valves and sight glass PR to PO conversion | WGE | 2024-05-01 | Delayed |  | Delayed P&ID and material list approval. Some details were revised | Approval Process
PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-04-20 | Mechanical | Delayed PO for PE Panel AHU | 2024-04-13 | Prio other projects and urgent support | Project Prioritization | R12 | Focus on the technical Recon and PR to PO process | WGE | 2024-07-01 | Delayed |  | Prio other projects and urgent support | Project Prioritization
GC Transport Upgrade Ph 2 | Delayed | 2024-04-20 | Mechanical | PO for dust collector | 2024-04-19 | Under technical clarification with WGE and TCU | Communication | R10 | Set allignment meeting with TCU | DTL | 2024-05-31 | Delayed | DTL | Under technical clarification with WGE and TCU | Communication
Green Coffee Van Unloading | Delayed | 2024-04-20 | Mechanical | Design Freeze | 2024-04-19 | JCB is unavailable for the past week to sign the documents | Approval Process | R05 | Approach him and follow-up | ZAF | 2024-05-03 | Delayed | ZAF | JCB is unavailable for the past week to sign the documents | Approval Process
Green Coffee Van Unloading | Delayed | 2024-04-20 | Mechanical | Scope detailing | 2024-04-19 | MAPP declined to sign due to lacking of documents. Add electrical and civil works | Approval Process | R06 | Add electrical and civil works then load to docusign | ZAF | 2024-05-24 | Delayed | ZAF | MAPP declined to sign due to lacking of documents. Add electrical and civil works | Approval Process
Green Coffee Van Unloading | Delayed | 2024-04-20 | Mechanical | Kick-off fully signed | 2024-04-19 | Short on time | Other | R06 | Time management of SE | ZAF | 2024-05-24 | Delayed | ZAF | Short on time | Other
SCRF (self cleaning rotary filter) | Delayed | 2024-04-20 | Mechanical | Missed alignment meeting with TCU | 2024-04-05 | TCU availability | Resource Availability | R05 | Ask for another date | FCT | 2024-04-26 | Delayed | FCT | TCU availability | Resource Availability
Improvement of FFE RARE Filtering System | Delayed | 2024-04-20 | Mechanical | Delay delivery of rotary filter | 2024-04-19 | Supplier have issues with materials and logistics | Procurement | R01 | Follow-up for new timeline | FCT | 2024-04-26 | Delayed | FCT | Supplier has issues with materials and logistics | Procurement
Auto-compactor | Delayed | 2024-04-20 | Mechanical | Delayed material purchasing | 2024-04-19 | Difficulty finding exact specs for screeb | Design/Engineering | R09 | Ask Joors for new timeline | FCT | 2024-04-26 | Delayed | FCT | Difficulty finding exact specs for screen | Design/Engineering
Upgradation of Soft water plans | Delayed | 2024-04-22 | Mechanical | PEP Approval | 2024-03-29 | Lack of SHE requirements: Hot work and Work on heights | Safety | R11 | Coordinate and conduct alignment meeting with contractors | BDY | 2024-04-26 | Delayed | BDY | Lack of SHE requirements: Hot work and Work on heights | Safety
Upgradation of Soft water plans | Delayed | 2024-04-22 | Mechanical | Mechanical Works | 2024-03-01 | On-going routing of CRF | Design/Engineering | R11 | Follow-up PIC for the signatories | BDY | 2024-05-17 | Delayed | BDY | On-going routing of CRF | Design/Engineering
Upgradation of Soft water plans | Delayed | 2024-04-27 | Mechanical | PEP Approval | 2024-04-27 | PEP not yet approved by SHE and lacking of requirements in PEP | Safety | R01 | Issue site instruction and coordinate with contractor PIC | BDY | 2024-05-03 | Delayed | BDY | PEP not yet approved by SHE and lacking of requirements in PEP | Safety
Upgradation of Marley Cooling Tower | Delayed | 2024-04-27 | Mechanical | Testing of Marley cooling tower #6 and #9 | 2024-04-27 | Additional fabrication and installation of torque tube assymbly in cooling tower #6 and #9 | Construction | R06 | On-going extention of test run until Monday | ALC | 2024-05-03 | Delayed | ALC | Additional fabrication and installation of torque tube assembly in cooling tower #6 and #9 | Construction
PEC2020-Replacement of Ventillation duct at loading area(ph1A) | Delayed | 2024-05-01 | Mechanical | Delivery of fabricated ducting | 2024-05-01 | Fabricated ducts failed in line release (1/4) | Construction | R06 | Re-check quality standard | FEDCON | 2024-05-02 | Delayed | DTL | Fabricated ducts failed in line release (1/4) | Construction
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-27 | Mechanical | Aproval of P&ID | 2024-04-27 | Cancelled Meeting with TCU due to TCU is not available | Communication | R06 | Moved meeting with TCU | KJT | 2024-05-03 | Delayed | KJT | Cancelled Meeting with TCU due to TCU is not available | Communication
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-27 | Mechanical | Design modification and URS Finalization (approved) | 2024-04-27 | Factory engineer busy | Other | R05 | set follow-up schedule for signatory | KJT | 2024-05-03 | Delayed | KJT | Factory engineer busy | Other
Green Coffee Van Unloading | Cancellation | 2024-04-30 | Electrical | Tapping of temporary LDP power supply (380VAC) | 2024-05-01 | Area is not available due to inventory of stocks and early start-up of production | Other | R10 | Next CIP schedule | ABP | 2024-06-07 | On-track | ABP | Area is not available due to inventory of stocks and early start-up of production | Other
Green Coffee Van Unloading | Delayed | 2024-05-03 | Mechanical | Mechanical Works | 2024-04-27 | Delayed PO release | Procurement | R14 | To meke new timeline and close monitoring on the delivery of dust colector | SMG | 2024-07-05 | Delayed | SMG | Delayed PO release | Procurement
GCU+ | Cancellation | 2024-05-04 | Mechanical | Fit-up of V6 and V6.1 spare pipe of cell 5 and 6 Fit-up V4 spare splt flange of cell 3 and 4 | 2024-05-04 | not enough time to finish the job. Schedule was change from 2 days to 7 hours. Moved to next CIP | Other | R06 | Moved to next CIP | KJT | 2024-06-07 | Delayed | KJT | Not enough time to finish the job. Schedule was changed from 2 days to 7 hours. Moved to next CIP | Other
AFBB Smokestack | Delayed | 2024-05-06 | Civil | Installation of cladding | 2024-05-04 | Personnel still comply the requirement | Human Resources | R04 | Follow-up contractor and advise to OT | SMG | 2024-05-17 | Delayed | SMG | Personnel still comply with the requirement | Human Resources
Auto-compactor | Delayed | 2024-05-06 | Civil | Design Freeze | 2024-05-01 | Revise drawing from area owner | Design/Engineering | R06 | Fast track the revised drawing and approval |  |  |  | SMG | Revise drawing from area owner | Design/Engineering
Improvement of FFE RARE Filtering System | Delayed | 2024-05-09 | Mechanical | PO of valves and mechanical works | 2024-05-04 | Qoutation from supplier not yet submitted & Technical Evaluation for Mechanical works was delayed | Procurement | R14 | 1. Follow-up Procurement for the qoutation of the supplier 2. Check the availability of pump and valves at technical stores 3. Ask procurement to priority the release of PO for mechanical works | FCT | 2024-05-17 | Delayed | FCT | Quotation from supplier not yet submitted & Technical Evaluation for Mechanical works was delayed | Procurement
Improvement of FFE RARE Filtering System | Delayed | 2024-05-09 | Mechanical | Delivery of Rotary Filter | 2024-04-27 | Manufacturing of equipment was delayed | Construction | R01 | Monitor and send email for the supplier regarding the delivery of equipment | FCT | 2024-06-28 | Delayed | FCT | Manufacturing of equipment was delayed | Construction
Independent CIP for Falling Film Evaporator | Delayed | 2024-05-09 | Mechanical | The functionality Test was completed 50% only because the program licensed from mheco was expired | 2024-05-04 | Licensed Program from mheco was expired | Other | R06 | Update licensed program and make a back up planned | REC | 2024-05-11 | Delayed | FCT | Licensed Program from mheco was expired | Other
GC Transport Upgrade Ph 2 | Delayed | 2024-05-09 | Mechanical | 1. Scope Detailing 2. Design Freeze 3. URS | 2024-05-11 | The project concept was delayed because as per TCU, the dust collector should be separate (Green coffee and Roasted Coffee) | Design/Engineering | R08 | Schedule alignment meeting with production the concept of dust collection | WGE | 2024-05-17 | Delayed | WGE | The project concept was delayed because as per TCU, the dust collector should be separate (Green coffee and Roasted Coffee) | Design/Engineering
Auto-compactor | Delayed | 2024-05-09 | Mechanical | Delivery of mechanical (Fabrication Works) | 2024-05-11 | The PO releasing of mechanical works was delayed | Procurement | R01 | Monitor the fabrication work, as per update. Fabrication works will be completed on week 22 | REC | 2024-05-31 | Delayed | FCT | The PO releasing of mechanical works was delayed | Procurement
Upgradation of Soft water plans | Delayed | 2024-05-08 | Mechanical | PEP Approval | 2024-05-11 | Manpower clinic appointment/revision of Methodology | Human Resources | R11 | Discussion of Methodology step by step with the project in-charge | BDY | 2024-05-11 | Delayed | BDY | Manpower clinic appointment/revision of Methodology | Human Resources
Upgradation of Soft water plans | Delayed | 2024-05-11 | Mechanical | Delivery of Pump | 2024-04-13 | to CRF not fully signed | Documentation | R06 |  |  | 2024-06-21 | Delayed |  | To CRF not fully signed | Documentation
PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-05-11 | Mechanical | All Activities | 2024-05-24 | PO release, Installation, Delayed due to alignment meeting with TCU | Communication | R08 | Change timeline (create new timeline) | DTL | 2024-07-26 | Delayed | DTL | PO release, Installation, Delayed due to alignment meeting with TCU | Communication
PEC2020-Replacement of Ventillation duct at loading area(ph1A) | Delayed | 2024-05-11 | Mechanical | Removal of affected area, existing duct and commissioning | 2024-05-11 | Removal of scaffolding @ph1 - Done, Alignment meting with Production | Construction | R10 | Render OT and additional manpower | DTL | 2024-05-15 | Delayed | DTL | Removal of scaffolding @ph1 - Done, Alignment meeting with Production | Construction
Zurich Gap Closure | Delayed | 2024-05-30 | Electrical | Delivery and Installation Works | 2024-05-24 | On-going PEP and Lacking manpower | Human Resources | R11 | Conduct meeting with supplier/contractor and set revise new timeline | MGS | 2024-08-23 | Delayed | MGS | On-going PEP and Lacking manpower | Human Resources
GCU+ | Cancellation | 2024-05-30 | Mechanical | Cancellation of fit-up of v4 split flange of cell 5 and 6 | 2024-05-31 | Due to the request of production which is to chech ASAP the v4 spare pipe of cell 8 E54 suspected to be misallign. Need to address on week 22 CIP | Construction | R12 | To priority next CIP | KJT | 2024-06-28 | Delayed | KJT | Due to the request of production which is to check ASAP the v4 spare pipe of cell 8 E54 suspected to be misaligned. Need to address on week 22 CIP | Construction
SCRF (self cleaning rotary filter) | Delayed | 2024-05-27 | Mechanical | Removal of bursting disk & orientation of valves & pipes | 2024-04-27 | Approval of drawing according to TCU standard | Approval Process | R06 | Advance fabrication of pipes & tie in works @May CIP | FCT | 2024-05-31 | Delayed | DTL | Approval of drawing according to TCU standard | Approval Process
Safety Upgrade of E54 Cell cover | Delayed | 2024-05-27 | Mechanical | Tagging of lines and equipment | 2024-05-31 | Change design of tagging | Design/Engineering | R10 | Expedite tagging design approval | FCT | 2024-05-31 | Delayed | FCT | Change design of tagging | Design/Engineering
Improvement of FFE RARE Filtering System | Delayed | 2024-05-27 | Mechanical | PO releasing of valves and pumps was delayed | 2024-04-01 | There is no quotation from supplier with the control for this activity is the makati procurement | Procurement | R14 | Get pumps at Technical stores - done check the availability of valves at technical stores and at biomass | FCT | 2024-06-07 | Delayed | FCT | There is no quotation from supplier with the control for this activity is the Makati procurement | Procurement
Improvement of FFE RARE Filtering System | Delayed | 2024-06-10 | Mechanical | To follow-up PO for Mechanical Works | 2024-06-07 | PIC on meeting for project discussion | Communication | R12 | To follow-up WGE for updates | KRC | 2024-06-21 | On-track | KRC | PIC on meeting for project discussion | Communication
Green Coffee Van Unloading | Delayed | 2024-06-10 | Civil | Installation of sandwich panel, ceiling installation and painting works | 2024-06-07 | Priority installation of ceiling | Construction | R12 | Follow-up contractor | SMG | 2024-06-28 | On-track | SMG | Priority installation of ceiling | Construction
Auto-compactor | Delayed | 2024-06-10 | Civil | Design freeze and PR to PO | 2024-06-07 | Revised drawing and approval | Design/Engineering | R06 | Fast track drawing and routing | RES | 2024-06-14 | On-track | SMG | Revised drawing and approval | Design/Engineering
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-07 | Mechanical | Design Freeze - construction drawing on group 1, 2 and 3 | 2024-05-01 | TCU is not available on scheduled meeting, MM0 is the topic during with TCU. Prioritize other urgent project: MM0 P&ID, Vacuum pump P&ID, as0built and modification of design | Communication | R12 | Overtime and discuss on how to improve the process like using the hygienic engineering standard drawing | KJT | 2024-06-14 | On-track | KJT | TCU is not available on scheduled meeting, MM0 is the topic during with TCU. Prioritize other urgent project: MM0 P&ID, Vacuum pump P&ID, as-built and modification of design | Communication
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-07 | Mechanical | PO approval - Group 1 (ph 2 ) Piping - works | 2024-05-31 | Procurement is not available in the requested schedule of pre-bidding | Procurement | R14 | Follow-up procurement; Procurement confirm the schedule on week 24 | KJT | 2024-07-12 | On-track | KJT | Procurement is not available in the requested schedule of pre-bidding | Procurement
Green Coffee Van Unloading | Delayed | 2024-05-31 | Mechanical | Delivery of dust collector and Mechanical works | 2024-05-31 | Delivery is 10 weeks from PO (Wk26) Mechanical works is wk 24 as per new timeline | Procurement | R14 | Change timeline as new reference (Close Monitoring) | DTL | 2024-06-28 | On-track | DTL | Delivery is 10 weeks from PO (Wk26) Mechanical works is wk 24 as per new timeline | Procurement
GC Transport Upgrade Ph 2 | Delayed | 2024-05-25 | Mechanical | Design Freeze and URS of Dust collector | 2024-05-18 | Allignment meeting with TCU - Week 24 | Communication | R08 | Conduct and finalized P&ID (week 25) | DTL | 2024-07-12 | Delayed | DTL | Alignment meeting with TCU - Week 24 | Communication
Green Coffee Van Unloading | Delayed | 2024-06-03 | Civil | Installaition of sandwich panel | 2024-05-31 | Other priority | Other | R01 | Follow-up contractor to fast track the activities | SMG | 2024-06-07 | On-track | SMG | Other priority | Other
PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-06-03 | Mechanical | Design freeze, URS and PR of ACU | 2024-05-31 | Other priority - GCCD transport commissioning. RFQ for supplier - on going | Other | R12 | Render OT once | DTL | 2024-06-28 | Delayed | DTL | Other priority - GCCD transport commissioning. RFQ for supplier - ongoing | Other
E54 High Pressure water heater | Delayed | 2024-06-03 | Mechanical | Project Kick-off, scope detailing and design freeze | 2024-05-18 | No water heater drawing received from supplier as of now. We will use the latest WH Drawing from supplier and follow-up PE | Procurement | R06 | To finish once the drawing is received. Render OT, it would take 1-2 weeks | DTL | 2024-06-28 | Delayed | DTL | No water heater drawing received from supplier as of now. We will use the latest WH Drawing from supplier and follow-up PE | Procurement
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-07 | Mechanical | PO approval of Tufflin, Peter Meyer, Mixed proof, Valtaco valve and sight glasss | 2024-05-17 | Delayed submission of quotation from supplier, delayed approval of PO from procurement | Procurement | R14 | To follow-up procurement and supplier | KJT | 2024-06-14 | On-track | KJT | Delayed submission of quotation from supplier, delayed approval of PO from procurement | Procurement
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-14 | Mechanical | URS creation - Group 4 (DPC/Additional) | 2024-06-15 | Prioritized other activities since no credit yet | Project Prioritization | R12 | Overtime | KJT | 2024-07-05 | On-track | KJT | Prioritized other activities since no credit yet | Project Prioritization
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-14 | Mechanical | Approved PO - Tuflin valves and peter meyer | 2024-06-15 | On-going approval of procurement, requires additional approval on OLYMPE | Procurement | R14 | To follow-up procurement | KJT | 2024-06-28 | On-track | KJT | On-going approval of procurement, requires additional approval on OLYMPE | Procurement
SIR E45 | Delayed | 2024-06-18 | Mechanical | Creation of CILT, Gasket and Tools list | 2024-07-26 | Prioritized PEC2020 activities scope detailing of group 3 | Project Prioritization | R12 | Prioritized SIR activities since done on PEC2020 | KJT | 2024-06-21 | Delayed | KJT | Prioritized PEC2020 activities scope detailing of group 3 | Project Prioritization
PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-14 | Mechanical | Approved scope - group 1 - doc 12 (1 of 3) VEC valves | 2024-06-15 | Delayed completion of the creation of scope detailing | Other | R12 | Overtime | KJT | 2024-06-21 | On-track | KJT | Delayed completion of the creation of scope detailing | Other

## Summary
| Project Titles | Description of Issue | Category | SE | Overall completion |  | Reason code | [5 empty] | Project Timeline based on NIMT | SE | PE | PM
1 | GC Transport Upgrade Ph 1 | Delayed | Mechanical | SMG | On-track | R01 | Time commited by contractor is not followed |  |  |  |  | 3 | Step 3 Design | SMG | WGE | MAPP | Ok
2 | GC Transport Upgrade Ph 2 | Cancellation | Electrical | MGS | Delayed | R02 | 3RD party logistic issue (Delivery of Materials) |  |  |  |  | 4 | Step 4 Construction | MGS | REC |  | Not ok
3 | Green Coffee Van Unloading |  | Civil | BDY |  | R03 | No available SO from contractor |  |  |  |  | 5 | Step 5 Installation | BDY | JRUS
4 | Improvement of FFE RARE Filtering System |  | Automation | ALC |  | R04 | Key personnel not available | 96 |  |  |  | 6 | Step 6 Commissioning | ALC | ADC
5 | AFBB Smokestack |  |  | ABP |  | R05 | PIC/stakeholders availability |  |  |  |  | 7 | Step 7 Qualification | ABP | RADY
6 | SCRF (self cleaning rotary filter) |  |  | DTL |  | R06 | Others |  |  |  |  | 8 | Step 8 Verification | DTL
7 | Auto-compactor |  |  | KJT |  | R07 | SHE Violation/Issue |  |  |  |  | 9 | Step 9 Hand-over | KJT
8 | Independent CIP for Falling Film Evaporator |  |  | FCT |  | R08 | Alignment to TCU Standard | [6 empty] | FCT
9 | Upgradation of Soft water plans |  |  |  |  | R09 | Materials did not arrive
10 | Upgradation of Marley Cooling Tower |  |  |  |  | R10 | For Alignment meeting
11 | Project Horizon 1 |  |  |  |  | R11 | PEP not yet approved
12 | Project Horizon 2 |  |  |  |  | R12 | Other priority
13 | Zurich Gap Closure |  |  |  |  | R13 | Lack of man power
14 | PEC2020-Improvement of Natural Ventilation (window) |  |  |  |  | R14 | PO release
15 | PEC2020-Installation of New PE PANELS |  |  |  |  | R15 | Approval of URS
16 | PEC2020-EA Process Adaptation |  |  |  |  | R16 | On-hold
17 | PEC2020-Program Development for PEC2020
18 | PEC2020-Extraction 54 PEC2020 PLC Upgrade
19 | PEC2020-DMO GCU+
20 | PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade
21 | PEC2020-Upgrade of cooper tubes to steel braided hose etc.
22 | PEC2020-Installation of new PE Panel cooling system(PH1b)
23 | PEC2020-Replacement of Ventillation duct at loading area(ph1A)
24 | PEC2020-Process Adaptation ( Mechl )
25 | Safety Upgrade of E54 Cell cover
| Project Name | Description of Issue | Date initiated | Activity Category | Incident name | Original Schedule | Detailed Cause/Reason | Reason Code | Catch up plan activity | Who | When | Overall completion | Project Timeline based on NIMT | Prepared By | Approved by | Noted By | Submitted
| AFBB Smokestack | Delayed |  | Civil | Risk Assessment of Methodology | 2024-02-24 | Ravago did not submit load chart for 500T |  | Follow-up Ravago | SMG |  |  |  | SMG | RADY | MAPP | Ok
| AFBB Smokestack | Delayed |  | Civil | Lifting Methodology | 2024-02-24 | Ravago did not submit load chart for 500T |  | Follow-up Ravago | SMG |  |  |  | SMG | RADY | MAPP | Ok
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-04 | Mechanical | Approval of structural analysis for scaffolding | 2024-03-01 | Structural Analysis approval |  | Close monitor, Follow-up and Render OT | DTL | 2024-03-06 | Delayed |  |  |  |  | Ok
| GC Transport Upgrade Ph 1 | Delayed |  | Mechanical | Approval of PEP | 2024-03-01 |  |  |  | DTL
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-04 | Mechanical | Installation of Lifting Provision no. 2 (Mechanical Boom) | 2024-03-02 | Delayed due to structural analysis |  | Close monitor, Follow-up and Render OT | DTL | 2024-03-07 | Delayed |  |  |  |  | Ok
| Independent CIP for Falling Film Evaporator | Delayed | 2024-03-02 | Mechanical | Create program | 2024-03-01 | Actual P&ID is not the same with the submitted P&ID as of now follow actual P&ID in the site On-going finalization of program |  | Weekly Meeting with production and project team. Use actual P&ID for continuation | FCT | 2024-03-04 | Delayed |  |  |  |  | Ok
| Independent CIP for Falling Film Evaporator | Delayed |  | Mechanical | Offline Simulation | 2024-03-01 | To reschedule meeting with production, mheco and project Team |  |  | FCT
| Independent CIP for Falling Film Evaporator | Delayed |  | Mechanical | Risk assesment | 2024-03-02 | To reschedule meeting with production, mheco and project Team |  |  | FCT
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-12 | Mechanical | Modification of Cyclonic Hopper no. 3(Outlet) | 2024-03-09 | If will be done after lifting of new cyclonic to silo since it will have 3 days to perform |  | Render OT | DTL | 2024-03-14 | On-track |  | DTL | REC | MAPP | Ok
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-12 | Mechanical | Installation of cyclonic hopper #3 | 2024-03-09 | Structural Ananlysis approval for silo |  | Render OT | DTL | 2024-03-16 | On-track |  | DTL | REC | MAPP | Ok
| SCRF (self cleaning rotary filter) | Delayed |  | Mechanical | Allignment meeting with TCU | 2024-03-08 | TCU not available (on leave) |  | Join Meeting on March 15, 2024 | FCT | 2024-03-15 | On-track |  | FCT | REC | MAPP | Ok
| Independent CIP for Falling Film Evaporator | Delayed | 2024-03-12 | Mechanical | Create program | 2024-03-09 | P&ID alignment |  | Waiting for production Schedule / Week 12 | FCT | 2024-03-12 | On-track |  | FCT | REC | MAPP | Ok
| Independent CIP for Falling Film Evaporator | Delayed |  | Mechanical | Offline Simulation | 2024-03-08 |  |  |  | FCT
| Independent CIP for Falling Film Evaporator | Delayed |  | Mechanical | Actual simulation (Water run) | 2024-03-09 |  |  |  | FCT
| AFBB Smokestack | Delayed | 2024-03-11 | Electrical | Installation of Lightning Arrester | 2024-03-11 | Civil works was delayed |  | Week 14 | MGS | Week 14 | Delayed |  | MGS | ADC | MAPP | Ok
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-19 | Mechanical | Modification of Cyclonic Hopper no. 3(Outlet) | March 13-16, 2024 | Prioritized site activities | R03 | After site activities, render OT | DTL | Wk 14 | Delayed |  | DTL | REC | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-03-19 | Mechanical | Project Kick-off ( Start ): Dust Collector | 2024-03-15 |  | R03 | After site activities, render OT | DTL | Wk 14 | Delayed |  | DTL | REC | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-03-18 | Civil | Enclosure inside | Wk 9 | Production will use the GC Tilting | R07 | Waiting for Production Schedule | SMG | TBD | Delayed |  | SMG | RADY | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-03-18 | Mechanical | PO release: Dust Collector | 2024-03-15 | Delay on approval of the PR to PO (PR submitted: Feb 01, 2024 | R14 | Follow-up and escalate on the PR to PO meeting with ESD | WGE | Wk 14 | Delayed |  |  | WGE | MAPP | Ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-03-18 | Mechanical | Fully signed URS | 2024-03-16 | No signature yet from JCBaltazar | R15 | Send follow-up email | FCT | Wk 13 | On-track |  | FCT | REC | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-03-18 | Civil | Lifting and installation of Smokestack and Platform | March 11-17, 2024 | Priority Installation of Stack | R03 | Overtime | SMG | Wk 13 | On-track |  | SMG | RADY | MAPP | Ok
| SCRF (self cleaning rotary filter) | Delayed | 2024-03-18 | Mechanical | Allignment meeting with TCU/ Coordination meeting w/ TCU for discussion of existing set up | 2024-03-15 | TCU not available | R02 | Reschedule meeting with TCU on Week 12 | REC | 2024-03-22 | On-track |  |  | REC | MAPP | Ok
| Auto-compactor | Delayed | 2024-03-18 | Civil | Project Kick-off ( Start ): Maintenance Platform | 2024-03-15 | Priority other project AFBB Smokestack Upgrade | R03 | Overtime | SMG | Wk13 | On-track |  | SMG | RADY | MAPP | Ok
| Auto-compactor |  |  | Civil | Scope detailing | 2024-03-15 |  |  |  | SMG
| Auto-compactor |  |  | Civil | Design Freeze | 2024-03-16 |  |  |  | SMG
| Auto-compactor |  |  | Civil | Routing and approval of drawing | March 11-16, 2024 |  |  |  | SMG
| Upgradation of Marley Cooling Tower | Delayed | 2024-03-18 | Mechanical | Demolition of Cooling tower #6 | Wk11 | Included in danger zone area during Smokestack lifting civil activity | R16 | Overtime | ALC | Wk 12 | On-track |  | ALC | JRUS | MAPP | Ok
| PEC2020 - E54 Spot Cooling | Delayed | 2024-03-18 | Mechanical | Installation of E54 Spot Cooling duct | Week 11 | High Profile Visitor | R03 | Render OT | DTL | Wk 12 | Delayed |  | DTL | REC | MAPP | Ok
| PEC2020 - E54 Spot Cooling | Delayed | 2024-03-18 | Mechanical | PO release | Wk 11 | Delay on approval of the PR to PO (PR submitted: Feb 12, 2024 | R14 | Follow-up and escalate on the PR to PO meeting with ESD | WGE | Wk 14 | Delayed |  |  | WGE | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-20 | Mechanical | Installation of screen window - entire assembly in E54 | Wk 11 | Too tight timeline due to delay release of PO | R14 | Prioritized PEP approval, fabrication and installation of E54 screen window | KJT | Week 12 | Delayed |  | KJT | WGE | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-20 | Mechanical | Installation of scaffolding, main frame and screen frame, PEP approval in E45 | Wk 11 | Too tight timeline due to delay release of PO and additional scope (extension of E54 scaffolding) | R14 | Daily overtime and alignment meeting with contractor | KJT | Week 13 | Delayed |  | KJT | WGE | MAPP | Ok
| PEC2020-EA Process Adaptation | Delayed | 2024-03-20 | Electrical | URS and Critical Material | Week 8 and 11 | Process adaptation P&ID on-going | R10 | Close coordination with team, set meeting with mechanical team | ABP | Week 12 | Delayed |  | ABP | ADC | MAPP | Ok
| PEC2020-Installation of New PE PANELS | Delayed | 2024-03-20 | Electrical | Installation of cable trays | wk 12 | Need to revise timeline because of possibility production will not allow us | R10 | Need to revise timeline | ABP | Week 13 | Delayed |  | ABP | ADC | MAPP | Ok
| PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade | Delayed | 2024-03-20 | Electrical | Installation of cable tray raceway | wk 12 | Need to revise timeline because of possibility production will not allow us | R10 | Need to revise timeline | ABP | Week 13 | Delayed |  | ABP | ADC | MAPP | Ok
| PEC2020-Extraction 54 PEC2020 PLC Upgrade | Delayed | 2024-03-20 | Electrical | PO for critical instrument | Wk 11 | PO for CLC CPU - done, waiting for delivery | R09 | Ask ADC for PO Copy | ABP | Week 13 | Delayed |  | ABP | ADC | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-25 | Mechanical | Cleaning/Polishing of screen window in E54 | Week 12 | Cannot install movable scaffolding due to lifting hoist cannot remove the cell filters beside the window | R06 | Proceed the cleaning in low level portion of the window | KJT | Week 13 | Delayed |  | KJT | WGE | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-04-01 | Mechanical | Installation of Screen window in E45 | Week 13 | Prioritized E54 scaffolding and polishing of screen window frame | R12 | Overtime of manpower | KJT | Week 14 | Delayed |  | KJT | WGE | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-25 | Mechanical | Cleaning/Polishing of screen window in E54 | Week 12 | Cannot install movable scaffolding due to lifting hoist cannot remove the cell filters beside the window | R06 | Proceed the cleaning in low level portion of the window | KJT | Week 13 | Delayed |  | KJT | WGE | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-04-01 | Mechanical | Installation of screen window in E45 | Week 13 | Prioritized E54 scaffolding and polishing of screen window frace | R12 | Overtime manpower | KJT | Week 14 | Delayed |  | KJT | WGE | MAPP | Ok
| Upgradation of Marley Cooling Tower | Delayed | 2024-04-10 | Mechanical | Installation of mechanical components, upper and lower cylinder, and testing of marley #6 | Week 14 | JAV contractor not onsite due to manpower availability | R01 | Priority Delayed activity and pause the advance works (all contractor focus on delayd activities) | ALC | Week 16 | On-track |  | ALC | JRUS | MAPP | Ok
| PEC2020-Installation of New PE PANELS | Cancellation | 2024-04-11 | Electrical | Timeline adjustment | Week 14 | Unable to perorm the activities due to continuous production run | R09 | Revised timeline to 2025 Annual SD | ABP | Week 30, 2025 | On-track |  | ABP | ADC | MAPP | Ok
PEC2020-EA Process Adaptation
PEC2020-Extraction 54 PEC2020 PLC Upgrade
PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade
| PEC2020-Replacement of Ventillation duct at loading area(ph1A) | Cancellation | 2024-04-11 | Mechanical | Lifting and installation of ducts Rmoval of obstacles (angle bar, etc) | Week 14 | Area is congested Give way to floor painting activities | R16 | Render OT | DTL | Week 15 | Delayed |  | DTL | REC | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-04-11 | Mechanical | Kick-off Scope detailing Design Freeze | Week 14 | Scope detailing is on-going route Kick-off cration is on-going Design Freeze approved for construction is on-going routing | R06 | Render OT and time management | DTL | Week 16 | Delayed |  | DTL | REC | MAPP | Ok
| Safety Upgrade of E54 Cell cover | Delayed | 2024-04-11 | Mechanical | Tagging of lines and equipment | Week 14 | Delay preparation of tags | R06 | Set new timeline, print all tags for preparation | FCT | Week 22 | Delayed |  | FCT | REC | MAPP | Ok
| Independent CIP for Falling Film Evaporator | Delayed | 2024-04-11 | Mechanical | Finalized SOO, Create program, offline simulation, risk assessment, actual simuation. | Week 14 | Delayed programm creation | R01 | Set new timeline agreed by all stakeholders | FCT | Week 17 | On-track |  | FCT | REC | MAPP | Ok
| Green Coffee Van Unloading | Cancellation | 2024-04-11 | Electrical | Tapping of temporary LDP power supply, Installation of cable tray droppings, and installation of wirings of GC van tilting for motor controls | Week 14 | Prioritized removal of cable tray ladder and installation of new cable tray and harnessing of wires since it involves working on heights | R12 | Next CIP schedule Provide scaffolding | ABP | Week 18 | On-track |  | ABP | ADC | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-04-11 | Electrical | Installation of lightning arrester rod | Week 14 | Contractors PEP was declined by SHE due to lacking safety documents | R11 | Cost-plus to back up | MGS | Week 15 | Delayed |  | MGS | ADC | MAPP | Ok
| PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-04-12 | Mechanical | Scope detailing Kick-off | Week 6 | Need alignment meeting with supplier for technical clarification | R06 | Need alignment meeting with supplier | DTL | TBD, Week 18 | Delayed |  | DTL | REC | MAPP | Ok
| GC Transport Upgrade Ph 2 | Delayed | 2024-04-12 | Mechanical | Kick-off Scope detailing Design Freeze | Week 8 | Cannot proceed this activity, we need to finish first technical clarification (Dust collector) | R06 | Allignment meeting with supplier | DTL | TBD, Week 18 | Delayed |  | DTL | REC | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-04-12 | Mechanical | Installation of flatbar, fullwelding of hinges | Week 14 | Additional scope, installation of flatbar above window | R06 | Manpower overtime | KJT | Week 15 | Delayed |  | KJT | WGE | MAPP | Ok
| SIR E45 | Cancellation | 2024-04-12 | Mechanical | Installation of E45 Pneumatic cylinder | Week 14 | prioritized self-cleaning (Contractor), No EI to calibrate the load cell and lacking of pin | R13 | Machining of pin and Coordinate with EI | KJT | Week 18 | On-track |  | KJT | WGE | MAPP | Ok
| GCU+ | Cancellation | 2024-04-12 | Mechanical | Installaition of V5.1 flashing plate in E54 | Week 14 | Plan is to install flashing plate when production costplus will replace V6.1 pipes for cleaning, they cancell the plan cleaning. | R12 | To install next replacement of V6.1 | KJT | Week 18 | On-track |  | KJT | WGE | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-13 | Mechanical | Delivery of PM, Tuflin and Mixed proof valves | Week 36 | Finalization of P&ID and material list with Paolo and encountered problem in Procurement Processing. | R08 | To follow-up procurement | KJT | Week 46 | On-track |  | KJT | WGE | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-13 | Mechanical | PO of PM, Tuflin and mixed proof valves | Week 1 | Finalization of P&ID and material list with Paolo and encountered problem in Procurement Processing. | R08 | To follow-up procurement | KJT | Week 22 | On-track |  | KJT | WGE | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-15 | Mechanical | Design Freeze, Kick-off and Scope detailing | Week 5 | Cancelled Meeting with TCU | R08 | Manpower overtime so that we can present to TCU the pending drawings | KJT | Week 25 | On-track |  | KJT | WGE | MAPP | Ok
| GC Transport Upgrade Ph 1 | Delayed | 2024-04-20 | Mechanical | Submission of Welding Inspection and 5S | Week 14 | Focus on clearing areas | R12 | Submit on Week 17 | JJA | Week 17 | Delayed |  | JJA | WGE | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-04-20 | Civil | [11 empty] | MAPP | Ok
| Auto-compactor | Delayed | 2024-04-20 | Civil | Design Freeze on Civil drawing | Week 16 | JCB is un available due to currenty occupied with urgent matters | R06 | Approach him and follow-up | RES | Week 17 | Delayed |  | RES | WGE | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-04-20 | Civil | Cladding works and Demobilization | Week 15 | Prioritized cleaning of the area for visitor | R12 | OT | SMG | Week 18 | Delayed |  | SMG | RADY | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-20 | Mechanical | Delayed PO for Valves and sight glass |  | Delayed P&ID and material list approval. Some details were revised | R12 | Focus on the valves and sight glass PR to PO conversion | WGE | 2024-05-01 | Delayed |  |  | WGE | MAPP | Ok
| PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-04-20 | Mechanical | Delayed PO for PE Panel AHU |  | Prio other projects and urgent support | R12 | Focus on the technical Recon and PR to PO process | WGE | 2024-07-01 | Delayed |  |  | WGE | MAPP | Ok
| GC Transport Upgrade Ph 2 | Delayed | 2024-04-20 | Mechanical | PO for dust collector | Week 16 | Under technical clarification with WGE and TCU | R10 | Set allignment meeting with TCU | DTL | Week 22 | Delayed |  | DTL | WGE | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-04-20 | Mechanical | Design Freeze | Week 16 | JCB is unavailable for the past week to sign the documents | R05 | Approach him and follow-up | ZAF | Week 18 | Delayed |  | ZAF | WGE | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-04-20 | Mechanical | Scope detailing | Week 16 | MAPP declined to sign due to lacking of documents. Add electrical and civil works | R06 | Add electrical and civil works then load to docusign | ZAF | Week 21 | Delayed |  | ZAF | WGE | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-04-20 | Mechanical | Kick-off fully signed | Week 16 | Short on time | R06 | Time management of SE | ZAF | Week 21 | Delayed |  | ZAF | WGE | MAPP | Ok
| SCRF (self cleaning rotary filter) | Delayed | 2024-04-20 | Mechanical | Missed alignment meeting with TCU | Week 14 | TCU availability | R05 | Ask for another date | FCT | Week 17 | Delayed |  | FCT | WGE | MAPP | Ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-04-20 | Mechanical | Delay delivery of rotary filter | Week 16 | Supplier have issues with materials and logistics | R01 | Follow-up for new timeline | FCT | Week 17 | Delayed |  | FCT | WGE | MAPP | Ok
| Auto-compactor | Delayed | 2024-04-20 | Mechanical | Delayed material purchasing | Week 16 | Difficulty finding exact specs for screeb | R09 | Ask Joors for new timeline | FCT | Week 17 | Delayed |  | FCT | WGE | MAPP | Ok
| Upgradation of Soft water plans | Delayed | 2024-04-22 | Mechanical | PEP Approval | Week 13 | Lack of SHE requirements: Hot work and Work on heights | R11 | Coordinate and conduct alignment meeting with contractors | BDY | Week 17 | Delayed |  | BDY | JRUS | MAPP | Ok
| Upgradation of Soft water plans | Delayed | 2024-04-22 | Mechanical | Mechanical Works | Week 9 | On-going routing of CRF | R11 | Follow-up PIC for the signatories | BDY | Week 20 | Delayed |  | BDY | JRUS | MAPP | Ok
| Upgradation of Soft water plans | Delayed | 2024-04-27 | Mechanical | PEP Approval | Week 17 | PEP not yet approved by SHE and lacking of requirements in PEP | R01 | Issue site instruction and coordinate with contractor PIC | BDY | Week 18 | Delayed |  | BDY | JRUS | MAPP | Ok
| Upgradation of Marley Cooling Tower | Delayed | 2024-04-27 | Mechanical | Testing of Marley cooling tower #6 and #9 | Week 17 | Additional fabrication and installation of torque tube assymbly in cooling tower #6 and #9 | R06 | On-going extention of test run until Monday | ALC | Week 18 | Delayed |  | ALC | JRUS | MAPP | Ok
| PEC2020-Replacement of Ventillation duct at loading area(ph1A) | Delayed | 2024-05-01 | Mechanical | Delivery of fabricated ducting | 2024-05-01 | Fabricated ducts failed in line release (1/4) | R06 | Re-check quality standard | Fedcon | 2024-05-02 | Delayed |  | DTL | REC | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-27 | Mechanical | Aproval of P&ID | Week 17 | Cancelled Meeting with TCU due to TCU is not available | R06 | Moved meeting with TCU | KJT | Week 18 | Delayed |  | KJT | WGE | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-27 | Mechanical | Design modification and URS Finalization (approved) | Week 17 | Factory engineer busy | R05 | set follow-up schedule for signatory | KJT | Week 18 | Delayed |  | KJT | WGE | MAPP | Ok
| Green Coffee Van Unloading | Cancellation | 2024-04-30 | Electrical | Tapping of temporary LDP power supply (380VAC) | Week 18 | Area is not available due to inventory of stocks and early start-up of production | R10 | Next CIP schedule | ABP | Week 23 | On-track |  | ABP | ADC | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-05-03 | Mechanical | Mechanical Works | Week 17 | Delayed PO release | R14 | To meke new timeline and close monitoring on the delivery of dust colector | SMG | Week 27 | Delayed |  | SMG | RADY | MAPP | Ok
| GCU+ | Cancellation | 2024-05-04 | Mechanical | Fit-up of V6 and V6.1 spare pipe of cell 5 and 6 Fit-up V4 spare splt flange of cell 3 and 4 | Week 18 | not enough time to finish the job. Schedule was change from 2 days to 7 hours. Moved to next CIP | R06 | Moved to next CIP | KJT | Week 23 | Delayed |  | KJT | WGE | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-05-06 | Civil | Installation of cladding | Week 18 | Personnel still comply the requirement | R04 | Follow-up contractor and advise to OT | SMG | Week 20 | Delayed |  | SMG | RADY | MAPP | Ok
| Auto-compactor | Delayed | 2024-05-06 | Civil | Design Freeze | Week 18 | Revise drawing from area owner | R06 | Fast track the revised drawing and approval |  |  |  |  | SMG | RADY | MAPP | Ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-05-09 | Mechanical | PO of valves and mechanical works | Week 18 and 19 | 1. Qoutation from supplier not yet submitted 2. Technical Evaluation for Mechanical works was delayed | R14 | 1. Follow-up Procurement for the qoutation of the supplier 2. Check the availability of pump and valves at technical stores 3. Ask procurement to priority the release of PO for mechanical works | FCT | Week 20 (Qoutation from supplier) | Delayed |  | FCT | REC | MAPP | ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-05-09 | Mechanical | Delivery of Rotary Filter | Week 17 | Manufacturing of equipment was delayed | R01 | Monitor and send email for the supplier regarding the delivery of equipment | FCT | Week 26 (As per supplier) | Delayed |  | FCT | REC | MAPP | ok
| Independent CIP for Falling Film Evaporator | Delayed | 2024-05-09 | Mechanical | The functionality Test was completed 50% only because the program licensed from mheco was expired | Week 18 | Licensed Program from mheco was expired | R06 | Update licensed program and make a back up planned | Chis/REC | Week 19 | Delayed |  | FCT | REC | MAPP | ok
| GC Transport Upgrade Ph 2 | Delayed | 2024-05-09 | Mechanical | 1. Scope Detailing 2. Design Freeze 3. URS | Week 18 and 19 | The project concept was delayed because as per TCU, the dust collector should be separate (Green coffee and Roasted Coffee) | R08 | Schedule alignment meeting with production the concept of dust collection | WGE | Week 20 | Delayed |  | WGE | REC | MAPP | ok
| Auto-compactor | Delayed | 2024-05-09 | Mechanical | Delivery of mechanical (Fabrication Works) | Week 19 | The PO releasing of mechanical works was delayed | R01 | Monitor the fabrication work, as per update. Fabrication works will be completed on week 22 | REC | Week 22 | Delayed |  | FCT | REC | MAPP | ok
| Upgradation of Soft water plans | Delayed | 2024-05-08 | Mechanical | PEP Approval | Week 19 | Manpower clinic appointment/revision of Methodology | R11 | Discussion of Methodology step by step with the project in-charge | BDY | Week 19 | Delayed |  | BDY | JRUS | MAPP | ok
| Upgradation of Soft water plans | Delayed | 2024-05-11 | Mechanical | Delivery of Pump | Week 15 | to CRF not fully signed |  |  |  | Week 25 | Delayed
| PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-05-11 | Mechanical | All Activities | May 2024 July 2024 | PO release Installation Delayed due to alignment meeting with TCU | R08 | Change timeline (create new timeline) | DTL | July 2024 Dec 2024 | Delayed |  | DTL | WGE | MAPP | ok
| PEC2020-Replacement of Ventillation duct at loading area(ph1A) | Delayed | 2024-05-11 | Mechanical | Removal of affected area, existing duct and commissioning | Week 19 | Removal of scaffolding @ph1 - Done Alignment meting with Production | R10 | Render OT and additional manpower | DTL | 2024-05-15 | Delayed |  | DTL | WGE | MAPP | ok
| Zurich Gap Closure | Delayed | 2024-05-30 | Electrical | Delivery and Installation Works | Week 21 | On-going PEP and Lacking manpower | R11 | Conduct meeting with supplier/contractor and set revise new timeline | MGS | Week 34 | Delayed |  | MGS | ADC | MAPP | ok
| GCU+ | Cancellation | 2024-05-30 | Mechanical | Cancellation of fit-up of v4 split flange of cell 5 and 6 | Week 22 | Due to the request of production which is to chech ASAP the v4 spare pipe of cell 8 E54 suspected to be misallign. Need to address on week 22 CIP | R12 | To priority next CIP | KJT | Week 26 | Delayed |  | KJT | WGE | MAPP | ok
| SCRF (self cleaning rotary filter) | Delayed | 2024-05-27 | Mechanical | Removal of bursting disk & orientation of valves & pipes | April CIP | Approval of drawing according to TCU standard | R06 | Advance fabrication of pipes & tie in works @May CIP | FCT | Week 22 | Delayed |  | DTL | REC | MAPP | ok
| Safety Upgrade of E54 Cell cover | Delayed | 2024-05-27 | Mechanical | Tagging of lines and equipment | Week 22 | Change design of tagging | R10 | Expedite tagging design approval | FCT | Week 22 | Delayed |  | FCT | REC | MAPP | ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-05-27 | Mechanical | PO releasing of valves and pumps was delayed | 2024-04-01 | There is no quotation from supplier with the control for this activity is the makati procurement | R14 | Get pumps at Technical stores - done check the availability of valves at technical stores and at biomass | FCT | Week 23 | Delayed |  | FCT | REC | MAPP | ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-06-10 | Mechanical | To follow-up PO for Mechanical Works | Week 23 | PIC on meeting for project discussion | R12 | To follow-up WGE for updates | KRC | Week 25 | On-track |  | KRC | WGE | MAPP | ok
| Green Coffee Van Unloading | Delayed | 2024-06-10 | Civil | Installation of sandwich panel, ceiling installation and painting works | Week 23 | Priority installation of ceiling | R12 | Follow-up contractor | SMG | Week 26 | On-track |  | SMG | RADY | MAPP | ok
| Auto-compactor | Delayed | 2024-06-10 | Civil | Design freeze and PR to PO | Week 23 | Revised drawing and approval | R06 | Fast track drawing and routing | RN&RES | Week 24 | On-track |  | SMG | RADY | MAPP | ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-07 | Mechanical | Design Freeze - construction drawing on group 1, 2 and 3 | G1 - Week 18 G2 - Week 19 | TCU is not available on scheduled meeting, MM0 is the topic during with TCU. Prioritize other urgent project: MM0 P&ID, Vacuum pump P&ID, as0built and modification of design | R12 | Overtime and discuss on how to improve the process like using the hygienic engineering standard drawing | KJT | G1 - Week 24 G2 - Week 25 | On-track |  | KJT | WGE | MAPP | ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-07 | Mechanical | PO approval - Group 1 (ph 2 ) Piping - works | Week 22 | Procurement is not available in the requested schedule of pre-bidding | R14 | Follow-up procurement; Procurement confirm the schedule on week 24 | KJT | Week 28 | On-track |  | KJT | WGE | MAPP | ok
| Green Coffee Van Unloading | Delayed | 2024-05-31 | Mechanical | Delivery of dust collector and Mechanical works | Delivery - Week 22 Mech works - Week 24 | Delivery is 10 weeks from PO (Wk26) Mechanical works is wk 24 as per new timeline | R14 | Change timeline as new reference (Close Monitoring) | DTL | Delivery - wk 26 Mech works - wk 24 | On-track |  | DTL | REC | MAPP | ok
| GC Transport Upgrade Ph 2 | Delayed | 2024-05-25 | Mechanical | Design Freeze and URS of Dust collector | Week 20 | Allignment meeting with TCU - Week 24 | R08 | Conduct and finalized P&ID (week 25) | DTL | Week 28 | Delayed |  | DTL | REC | MAPP | ok
| Green Coffee Van Unloading | Delayed | 2024-06-03 | Civil | Installaition of sandwich panel | Week 22 | Other priority | R01 | Follow-up contractor to fast track the activities | SMG | Week 23 | On-track |  | SMG | RADY | MAPP | ok
| PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-06-03 | Mechanical | Design freeze, URS and PR of ACU | Week 22 | Other priority - GCCD transport commissioning. RFQ for supplier - on going | R12 | Render OT once | DTL | Week 26 | Delayed |  | DTL | REC | MAPP | ok
| E54 High Pressure water heater | Delayed | 2024-06-03 | Mechanical | Project Kick-off, scope detailing and design freeze | Week 20 | No water heater drawing received from supplier as of now. We will use the latest WH Drawing from supplier and follow-up PE | R06 | To finish once the drawing is received. Render OT, it would take 1-2 weeks | DTL | Week 26 | Delayed |  | DTL | REC | MAPP | ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-07 | Mechanical | PO approval of Tufflin, Peter Meyer, Mixed proof, Valtaco valve and sight glasss | Week 20 Week 22 | Delayed submission of quotation from supplier, delayed approval of PO from procurement | R14 | To follow-up procurement and supplier | KJT | Week 24 Week 26 | On-track |  | KJT | WGE | MAPP | ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-14 | Mechanical | URS creation - Group 4 (DPC/Additional) | Week 24 | Prioritized other activities since no credit yet | R12 | Overtime | KJT | Week 27 | On-track |  | KJT | WGE | MAPP | ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-14 | Mechanical | Approved PO - Tuflin valves and peter meyer | Week 24 | On-going approval of procurement, requires additional approval on OLYMPE | R14 | To follow-up procurement | KJT | Week 26 | On-track |  | KJT | WGE | MAPP | ok
| SIR E45 | Delayed | 2024-06-18 | Mechanical | Creation of CILT, Gasket and Tools list | from week 30 moved to week 24 | Prioritized PEC2020 activities scope detailing of group 3 | R12 | Prioritized SIR activities since done on PEC2020 | KJT | Week 25 | Delayed |  | KJT | WGE | MAPP | ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-06-14 | Mechanical | Approved scope - group 1 - doc 12 (1 of 3) VEC valves | Week 24 | Delayed completion of the creation of scope detailing | R12 | Overtime | KJT | Week 25 | On-track |  | KJT | WGE | MAPP | ok

## Sheet2
Procurement
Design/Engineering
Communication
Change in Plan
Resource Availability
Construction
Project Prioritization
Other
Documentation
Safety
Approval Process
Human Resources

## Count_Final
0
Reason Code Legend |  |  | Project Title | # of Catch - up reports | Reason Code | [15 empty] | Total Code | Project Timeline based on NIMT | [6 empty] | Total Steps | Step 3 Design | Step 4 Construction | Step 5 Installation | Step 6 Commissioning | Step 7 Qualification | Step 8 Verification | Step 9 Hand-over
| 7 |  |  |  | R01 | R02 | R03 | R04 | R05 | R06 | R07 | R08 | R09 | R10 | R11 | R12 | R13 | R14 | R15 | R16 |  | Step 3 Design | Step 4 Construction | Step 5 Installation | Step 6 Commissioning | Step 7 Qualification | Step 8 Verification | Step 9 Hand-over
R01 | Time commited by contractor is not followed
R02 | 3RD party logistic issue (Delivery of Materials) |  | GC Transport Upgrade Ph 1 | 7 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R03 | No available SO from contractor |  | GC Transport Upgrade Ph 2 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R04 | Key personnel not available |  | Green Coffee Van Unloading | 13 | 1 | 0 | 1 | 0 | 1 | 3 | 1 | 0 | 0 | 1 | 0 | 2 | 0 | 3 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R05 | PIC/stakeholders availability |  | Improvement of FFE RARE Filtering System | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R06 | Others |  | AFBB Smokestack | 8 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R07 | SHE Violation/Issue |  | SCRF (self cleaning rotary filter) | 4 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R08 | Alignment to TCU Standard |  | Auto-compactor | 9 | 1 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R09 | Materials did not arrive |  | Independent CIP for Falling Film Evaporator | 8 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R10 | For Alignment meeting |  | Upgradation of Soft water plans | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R11 | PEP not yet approved |  | Upgradation of Marley Cooling Tower | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R12 | Other priority |  | Project Horizon 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R13 | Lack of man power |  | Project Horizon 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R14 | PO release |  | Zurich Gap Closure | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R15 | Approval of URS |  | PEC2020-Improvement of Natural Ventilation (window) | 7 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R16 | On-hold |  | PEC2020-Installation of New PE PANELS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PEC2020-EA Process Adaptation | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 |  | PEC2020-Program Development for PEC2020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | PEC2020-Extraction 54 PEC2020 PLC Upgrade | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PEC2020-DMO GCU+ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PEC2020-Upgrade of cooper tubes to steel braided hose etc. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PEC2020-Installation of new PE Panel cooling system(PH1b) | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PEC2020-Replacement of Ventillation duct at loading area(ph1A) | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | PEC2020-Process Adaptation ( Mechl ) | 12 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Safety Upgrade of E54 Cell cover | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 104 | 7 | 1 | 4 | 1 | 3 | 17 | 1 | 6 | 3 | 7 | 5 | 13 | 0 | 10 | 1 | 2 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Catch-up Plan Rev1
PROJECT DELAY, CANCELATION, & CATCH-UP REPORT
Rev. 2024.Mar.12
Project Name: _______________________________________________ | [5 empty] | Date initiated: _____________________________
I. Incident Name ( Description of Issue: Delayed Cancellation of Activities)
II. Original Planned Schedule of Activity:
III. Why ( Detailed cause/reason of Delay or Cancellation):
IV. What (What are the Catch-up Activities; Corrective Actions to be done):
V. Who (Action Owner, Person-Incharge):
VI. When (Date of Catch-up):
VII. Over-all Completion Outlook (vs Original Schedule): On-Track or Delayed?
Prepared by: |  |  | Approved by: |  |  |  | Noted by
___________________________________ |  |  | ___________________________________ |  |  |  | ___________________________________
Site Engineer |  |  | Project Engineer/Lead |  |  |  | Project Head
| R01 | Time commited by contractor is not followed |  | R07 | SHE Violation/Issue |  |  | R12 | Other priority
| R02 | 3RD party logistic issue (Delivery of Materials) |  | R08 | Alignment to TCU Standard |  |  | R13 | Lack of man power
| R03 | No available SO from contractor |  | R09 | Materials did not arrive |  |  | R14 | PO release
| R04 | Key personnel not around |  | R10 | For Alignment meeting |  |  | R15 | Approval of URS
| R05 | PIC/stakeholders availability |  | R11 | PEP not yet approved |  |  | R16 | On-hold
| R06 | Others (Please indicate):
PROJECT DELAY, CANCELATION, & CATCH-UP REPORT
Rev. 2024.Mar.12
Project Name: _______________________________________________ | [5 empty] | Date initiated: _____________________________
I. Incident Name ( Description of Issue: Delayed Cancellation of Activities)
II. Original Planned Schedule of Activity:
III. Why ( Detailed cause/reason of Delay or Cancellation):
IV. What (What are the Catch-up Activities; Corrective Actions to be done):
V. Who (Action Owner, Person-Incharge):
VI. When (Date of Catch-up):
VII. Over-all Completion Outlook (vs Original Schedule): On-Track or Delayed?
Prepared by: |  |  | Approved by: |  |  |  | Noted by
___________________________________ |  |  | ___________________________________ |  |  |  | ___________________________________
Site Engineer |  |  | Project Engineer/Lead |  |  |  | Project Head
| R01 | Time commited by contractor is not followed |  | R07 | SHE Violation/Issue |  |  | R12 | Other priority
| R02 | 3RD party logistic issue (Delivery of Materials) |  | R08 | Alignment to TCU Standard |  |  | R13 | Lack of man power
| R03 | No available SO from contractor |  | R09 | Materials did not arrive |  |  | R14 | PO release
| R04 | Key personnel not around |  | R10 | For Alignment meeting |  |  | R15 | Approval of URS
| R05 | PIC/stakeholders availability |  | R11 | PEP not yet approved |  |  | R16 | On-hold
| R06 | Others (Please indicate):

## ASI
ACTION STATUS INDICATOR - | [9 empty] | 2024-06-24 13:55
Last Updated:
Note:
Important : Must enter MEETING DATE for the template to keep track the status of action plan
No. | Project | Date | Engineering Driver | Action Plan | Who | Support | Planned | Actual | remark | Status
|  | 2024-03-12 |  | Revisit catch-up plan construction (boundaries for creation) | KRSC | MAPP | 2024-03-19 | 2024-03-17 |  | Done
|  | 2024-03-12 |  | Computer upgrade for draftsman may cause delay on 3D modelling | KRSC | MAPP | 2024-03-19 | 2024-03-17 |  | Done
To send follow up for methodology
ESCALATIONS
legend
Done
Pending
Delayed
Note on D6: Note : Input as mm/dd/yyyy
Note on I6: Note : Input as mm/dd/yyyy
Note on J6: Note : Input as mm/dd/yyyy

## Sheet1
Catch up plan: Should be submitted before Saturday
Problem | Why we have to do follow ups from time to time for catch plan? |  |  | Action
Why?? | ky wala naghatag on time | busy sa uban nga task | naay nakaplan nga task for that day | Overtime on that day
Ediscuss nila sa PE
Make it a priority on the next day
plan to create catch up plan every Friday
Create simplified form

## Summary - Original
| Project Titles | Description of Issue | Category | SE | Overall completion |  | Reason code | [5 empty] | SE | PE | PM
1 | GC Transport Upgrade Ph 1 | Delayed | Mechanical | SMG | On-track | R01 | Time commited by contractor is not followed | [5 empty] | SMG | WGE | MAPP | Ok
2 | GC Transport Upgrade Ph 2 | Cancellation | Electrical | MGS | Delayed | R02 | 3RD party logistic issue (Delivery of Materials) | [5 empty] | MGS | REC |  | Not ok
3 | Green Coffee Van Unloading |  | Civil | BDY |  | R03 | No available SO from contractor | [5 empty] | BDY | JRUS
4 | Improvement of FFE RARE Filtering System |  | Automation | ALC |  | R04 | Key personnel not available | [5 empty] | ALC | ADC
5 | AFBB Smokestack |  |  | ABP |  | R05 | PIC/stakeholders availability | [5 empty] | ABP | RADY
6 | SCRF (self cleaning rotary filter) |  |  | DTL |  | R06 | Others | [5 empty] | DTL
7 | Auto-compactor |  |  | KJT |  | R07 | SHE Violation/Issue | [5 empty] | KJT
8 | Independent CIP for Falling Film Evaporator |  |  | FCT |  | R08 | Alignment to TCU Standard | [5 empty] | FCT
9 | Upgradation of Soft water plans |  |  |  |  | R09 | Materials did not arrive
10 | Upgradation of Marley Cooling Tower |  |  |  |  | R10 | For Alignment meeting
11 | Project Horizon 1 |  |  |  |  | R11 | PEP not yet approved
12 | Project Horizon 2 |  |  |  |  | R12 | Other priority
13 | Zurich Gap Closure |  |  |  |  | R13 | Lack of man power
14 | PEC2020-Improvement of Natural Ventilation (window) |  |  |  |  | R14 | PO release
15 | PEC2020-Installation of New PE PANELS |  |  |  |  | R15 | Approval of URS
16 | PEC2020-EA Process Adaptation |  |  |  |  | R16 | On-hold
17 | PEC2020-Program Development for PEC2020
18 | PEC2020-Extraction 54 PEC2020 PLC Upgrade
19 | PEC2020-DMO GCU+
20 | PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade
21 | PEC2020-Upgrade of cooper tubes to steel braided hose etc.
22 | PEC2020-Installation of new PE Panel cooling system(PH1b)
23 | PEC2020-Replacement of Ventillation duct at loading area(ph1A)
24 | PEC2020-Process Adaptation ( Mechl )
25 | Safety Upgrade of E54 Cell cover
| Project Name | Description of Issue | Date initiated | Activity Category | Incident name | Original Schedule | Detailed Cause/Reason | Reason Code | Catch up plan activity | Who | When | Overall completion | Prepared By | Approved by | Noted By | Submitted
| GC Transport Upgrade Ph 2 | Delayed |  | Mechanical | Project Kick-off meeting with stakeholder | 2023-02-24 |  |  |  | DTL
| GC Transport Upgrade Ph 2 | Delayed |  | Mechanical | Scope detailing | 2023-02-24 |  |  |  | DTL
| GC Transport Upgrade Ph 1 | Delayed |  | Mechanical | Approval of Structural Analysis | 2023-02-22 |  |  |  | DTL
| Green Coffee Van Unloading | Delayed |  | Mechanical | Scope detailing | 2023-02-23 |  |  |  | DTL
| Green Coffee Van Unloading | Delayed |  | Civil | Fabrication and Installation of Column & Beams | 2024-02-17 | on-hold due to testing of container tilting van till further notice |  |  | SMG
| Green Coffee Van Unloading | Delayed |  | Civil | Installation of Sandwich Panel | 2024-02-17 | on-hold due to testing of container tilting van till further notice |  |  | SMG
| Green Coffee Van Unloading | Delayed |  | Civil | Construction of Concrete Studs | 2024-02-17 | on-hold due to testing of container tilting van till further notice |  |  | SMG
| Green Coffee Van Unloading | Delayed |  | Civil | Fabrication and Installation of Ceiling | 2024-02-17 | on-hold due to testing of container tilting van till further notice |  |  | SMG
| Green Coffee Van Unloading | Delayed |  | Civil | Installation of Roofing Support | 2024-02-19 |  |  |  | SMG
| AFBB Smokestack | Delayed |  | Civil | Risk Assessment of Methodology | 2024-02-24 | Ravago did not submit load chart for 500T |  | Follow-up Ravago | SMG |  |  | SMG | RADY | MAPP | Ok
| AFBB Smokestack | Delayed |  | Civil | Lifting Methodology | 2024-02-24 | Ravago did not submit load chart for 500T |  | Follow-up Ravago | SMG |  |  | SMG | RADY | MAPP | Ok
| Improvement of FFE RARE Filtering System | Delayed |  | Mechanical | Design Freeze | 2024-02-24 | Waiting for signatures for JCB and MAPP. (latest drawing on docusign) |  |  | FCT
| Improvement of FFE RARE Filtering System | Delayed |  | Mechanical | URS | 2023-02-23 | Waiting for signed P&ID |  |  | FCT
| SCRF (self cleaning rotary filter) | Delayed |  | Mechanical | 3D Drawing approval based from TCU Standard (E54) | 2024-02-24 | Waiting for allignment with TCU before proceding For further discussion See item 16 |  |  | FCT
| Independent CIP for Falling Film Evaporator | Delayed |  | Mechanical | Offline Simulation | 2024-02-24 | To reschedule meeting with production, mheco and project Team |  |  | FCT
| GC Transport Upgrade Ph 2 | Delayed |  | Mechanical | Design freeze | 2024-03-02 |  |  |  | DTL
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-04 | Mechanical | Approval of structural analysis for scaffolding | 2024-03-01 | Structural Analysis approval |  | Close monitor, Follow-up and Render OT | DTL | 2024-03-06 | Delayed |  |  |  | Ok
| GC Transport Upgrade Ph 1 | Delayed |  | Mechanical | Approval of PEP | 2024-03-01 |  |  |  | DTL
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-04 | Mechanical | Installation of Lifting Provision no. 2 (Mechanical Boom) | 2024-03-02 | Delayed due to structural analysis |  | Close monitor, Follow-up and Render OT | DTL | 2024-03-07 | Delayed |  |  |  | Ok
| Green Coffee Van Unloading | Delayed |  | Mechanical | Design freeze for Mechanical Works (Dust Collector)-Fabrication Drawing | 2024-03-01 | on-routing March 2, 2024 |  |  | DTL
| Green Coffee Van Unloading | Delayed |  | Mechanical | URS for Dust Collector | 2024-03-01 | for rerouting Lacking signature og macapil |  |  | DTL
| Green Coffee Van Unloading | Delayed |  | Civil | Painting Works | 2024-02-29 |  |  |  | SMG
| Green Coffee Van Unloading | Delayed |  | Civil | Removal of Scaffolding | 2024-02-29 |  |  |  | SMG
| Green Coffee Van Unloading | Delayed |  | Civil | Removal of Scaffolding & Enclosure | 2024-02-29 |  |  |  | SMG
| Green Coffee Van Unloading | Delayed |  | Civil | Demobilization | 2024-02-29 |  |  |  | SMG
| Improvement of FFE RARE Filtering System | Delayed |  | Mechanical | URS | 2024-03-02 | Waiting for signed P&ID |  |  | FCT
| AFBB Smokestack | Delayed |  | Civil | Risk Assessment of Methodology | 2024-03-02 |  |  |  | SMG
| AFBB Smokestack | Delayed |  | Civil | Lifting Methodology | 2024-03-02 |  |  |  | SMG
| SCRF (self cleaning rotary filter) | Delayed |  | Mechanical | 3D Drawing approval based from TCU Standard | 2024-03-02 | on-hold For Allignment meeting for actual installation with TCU Item 16 |  |  | FCT
| SCRF (self cleaning rotary filter) | Delayed |  | Mechanical | Re-orientation of isolation valves | 2024-03-02 | Waiting for allignment with TCU before proceding For further discussion See item 16 |  |  | FCT
| SCRF (self cleaning rotary filter) | Delayed |  | Mechanical | Removal of vursting dist at SCRF as per TCU Standard | 2024-03-02 | Waiting for allignment with TCU before proceding For further discussion See item 16 |  |  | FCT
| SCRF (self cleaning rotary filter) | Delayed |  | Mechanical | Removal of bursting disk and pressure relief valve at Nas filter as per TCU Standard | 2024-03-02 | Waiting for allignment with TCU before proceding For further discussion See item 16 |  |  | FCT
| SCRF (self cleaning rotary filter) | Delayed |  | Mechanical | Installation of relief valve and piping works at main line of product inlet line | 2024-03-02 | Waiting for allignment with TCU before proceding For further discussion See item 16 |  |  | FCT
| SCRF (self cleaning rotary filter) | Delayed |  | Mechanical | Installation of bursting disk and piping works at main line of product inlet line | 2024-03-02 | Waiting for allignment with TCU before proceding For further discussion See item 16 |  |  | FCT
| Independent CIP for Falling Film Evaporator | Delayed | 2024-03-02 | Mechanical | Create program | 2024-03-01 | Actual P&ID is not the same with the submitted P&ID as of now follow actual P&ID in the site On-going finalization of program |  | Weekly Meeting with production and project team. Use actual P&ID for continuation | FCT | 2024-03-04 | Delayed |  |  |  | Ok
| Independent CIP for Falling Film Evaporator | Delayed |  | Mechanical | Offline Simulation | 2024-03-01 | To reschedule meeting with production, mheco and project Team |  |  | FCT
| Independent CIP for Falling Film Evaporator | Delayed |  | Mechanical | Risk assesment | 2024-03-02 | To reschedule meeting with production, mheco and project Team |  |  | FCT
| GC Transport Upgrade Ph 2 | Delayed |  | Mechanical | Project Kick-off with project team to production ( attendance, ppt presentation ) | 2024-03-09 |  |  |  | DTL
| GC Transport Upgrade Ph 2 | Delayed |  | Mechanical | Scope Detailing | 2024-03-09 |  |  |  | DTL
| GC Transport Upgrade Ph 1 | Delayed |  | Mechanical | Approval of structural analysis for scaffolding | 2024-03-04 |  |  |  | DTL
| GC Transport Upgrade Ph 1 | Delayed |  | Mechanical | Approval of PEP | 2024-03-04 |  |  |  | DTL
| GC Transport Upgrade Ph 1 | Delayed |  | Mechanical | Installation of Lifting Provision no. 2 (Mechanical Boom) | 2024-03-06 |  |  |  | DTL
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-12 | Mechanical | Modification of Cyclonic Hopper no. 3(Outlet) | 2024-03-09 | If will be done after lifting of new cyclonic to silo since it will have 3 days to perform |  | Render OT | DTL | 2024-03-14 | On-track | DTL | REC | MAPP | Ok
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-12 | Mechanical | Installation of cyclonic hopper #3 | 2024-03-09 | Structural Ananlysis approval for silo |  | Render OT | DTL | 2024-03-16 | On-track | DTL | REC | MAPP | Ok
| Green Coffee Van Unloading | Delayed |  | Mechanical | Project Kick-off with project team to production ( attendance, ppt presentation ) | 2024-03-04 |  |  |  | DTL
| Green Coffee Van Unloading | Delayed |  | Mechanical | Scope Detailing | 2024-03-09 |  |  |  | DTL
| Improvement of FFE RARE Filtering System | Delayed |  | Mechanical | Initiate PR | 2024-03-09 |  |  |  | FCT
| SCRF (self cleaning rotary filter) | Delayed |  | Mechanical | Allignment meeting with TCU | 2024-03-08 | TCU not available (on leave) |  | Join Meeting on March 15, 2024 | FCT | 2024-03-15 | On-track | FCT | REC | MAPP | Ok
| Independent CIP for Falling Film Evaporator | Delayed | 2024-03-12 | Mechanical | Create program | 2024-03-09 | P&ID alignment |  | Waiting for production Schedule / Week 12 | FCT | 2024-03-12 | On-track | FCT | REC | MAPP | Ok
| Independent CIP for Falling Film Evaporator | Delayed |  | Mechanical | Offline Simulation | 2024-03-08 |  |  |  | FCT
| Independent CIP for Falling Film Evaporator | Delayed |  | Mechanical | Actual simulation (Water run) | 2024-03-09 |  |  |  | FCT
| AFBB Smokestack | Delayed | 2024-03-11 | Electrical | Installation of Lightning Arrester | 2024-03-11 | Civil works was delayed |  | Week 14 | MGS | Week 14 | Delayed | MGS | ADC | MAPP | Ok
| GC Transport Upgrade Ph 1 | Delayed | 2024-03-19 | Mechanical | Modification of Cyclonic Hopper no. 3(Outlet) | March 13-16, 2024 | Prioritized site activities | R03 | After site activities, render OT | DTL | Wk 14 | Delayed | DTL | REC | MAPP | Ok
| GC Transport Upgrade Ph 1 | Delayed |  | Mechanical | Installation of Cyclonic hopper no. 3 | March 13-16, 2024 |  |  |  | DTL
| GC Transport Upgrade Ph 1 | Delayed |  | Mechanical | Punchlist closure: Painting works and torque tightening | March 11-16, 2024 |  |  |  | DTL
| Green Coffee Van Unloading | Delayed | 2024-03-19 | Mechanical | Project Kick-off ( Start ): Dust Collector | 2024-03-15 |  | R03 | After site activities, render OT | DTL | Wk 14 | Delayed | DTL | REC | MAPP | Ok
| Green Coffee Van Unloading | Delayed |  | Electrical | Project Kick-off ( Start ): Dust Collector | 2024-03-15 |  |  |  | ABP
| Green Coffee Van Unloading | Delayed |  | Automation | Project Kick-off ( Start ): Dust Collector | 2024-03-15 |  |  |  | ABP
| Green Coffee Van Unloading | Delayed | 2024-03-18 | Civil | Enclosure inside | Wk 9 | Production will use the GC Tilting | R07 | Waiting for Production Schedule | SMG | TBD | Delayed | SMG | RADY | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-03-18 | Mechanical | PO release: Dust Collector | 2024-03-15 | Delay on approval of the PR to PO (PR submitted: Feb 01, 2024 | R14 | Follow-up and escalate on the PR to PO meeting with ESD | WGE | Wk 14 | Delayed |  | WGE | MAPP | Ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-03-18 | Mechanical | Fully signed URS | 2024-03-16 | No signature yet from JCBaltazar | R15 | Send follow-up email | FCT | Wk 13 | On-track | FCT | REC | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-03-18 | Civil | Lifting and installation of Smokestack and Platform | March 11-17, 2024 | Priority Installation of Stack | R03 | Overtime | SMG | Wk 13 | On-track | SMG | RADY | MAPP | Ok
| SCRF (self cleaning rotary filter) | Delayed | 2024-03-18 | Mechanical | Allignment meeting with TCU/ Coordination meeting w/ TCU for discussion of existing set up | 2024-03-15 | TCU not available | R02 | Reschedule meeting with TCU on Week 12 | REC | 2024-03-22 | On-track |  | REC | MAPP | Ok
| Auto-compactor | Delayed | 2024-03-18 | Civil | Project Kick-off ( Start ): Maintenance Platform | 2024-03-15 | Priority other project AFBB Smokestack Upgrade | R03 | Overtime | SMG | Wk13 | On-track | SMG | RADY | MAPP | Ok
| Auto-compactor |  |  | Civil | Scope detailing | 2024-03-15 |  |  |  | SMG
| Auto-compactor |  |  | Civil | Design Freeze | 2024-03-16 |  |  |  | SMG
| Auto-compactor |  |  | Civil | Routing and approval of drawing | March 11-16, 2024 |  |  |  | SMG
| Upgradation of Marley Cooling Tower | Delayed | 2024-03-18 | Mechanical | Demolition of Cooling tower #6 | Wk11 | Included in danger zone area during Smokestack lifting civil activity | R16 | Overtime | ALC | Wk 12 | On-track | ALC | JRUS | MAPP | Ok
| PEC2020 - E54 Spot Cooling | Delayed | 2024-03-18 | Mechanical | Installation of E54 Spot Cooling duct | Week 11 | High Profile Visitor | R03 | Render OT | DTL | Wk 12 | Delayed | DTL | REC | MAPP | Ok
| PEC2020 - E54 Spot Cooling | Delayed | 2024-03-18 | Mechanical | PO release | Wk 11 | Delay on approval of the PR to PO (PR submitted: Feb 12, 2024 | R14 | Follow-up and escalate on the PR to PO meeting with ESD | WGE | Wk 14 | Delayed |  | WGE | MAPP | Ok
| Green Coffee Van Unloading |  |  | Mechanical | Design freeze for Dust collector | wk 12 |  |  |  | DTL
| PEC2020-Replacement of Ventillation duct at loading area(ph1A) |  |  | Mechanical | Structural analysis | wk 12 |  |  |  | DTL
| PEC2020-Replacement of Ventillation duct at loading area(ph1A) |  |  | Mechanical | PEP Approval | wk 12 |  |  |  | DTL
| PEC2020-Replacement of Ventillation duct at loading area(ph1A) |  |  | Mechanical | Structural analysis | wk 12 |  |  |  | DTL
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-20 | Mechanical | Installation of screen window - entire assembly in E54 | Wk 11 | Too tight timeline due to delay release of PO | R14 | Prioritized PEP approval, fabrication and installation of E54 screen window | KJT | Week 12 | Delayed | KJT | WGE | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-20 | Mechanical | Installation of scaffolding, main frame and screen frame, PEP approval in E45 | Wk 11 | Too tight timeline due to delay release of PO and additional scope (extension of E54 scaffolding) | R14 | Daily overtime and alignment meeting with contractor | KJT | Week 13 | Delayed | KJT | WGE | MAPP | Ok
| PEC2020-EA Process Adaptation | Delayed | 2024-03-20 | Electrical | URS and Critical Material | Week 8 and 11 | Process adaptation P&ID on-going | R10 | Close coordination with team, set meeting with mechanical team | ABP | Week 12 | Delayed | ABP | ADC | MAPP | Ok
| PEC2020-Installation of New PE PANELS | Delayed | 2024-03-20 | Electrical | Installation of cable trays | wk 12 | Need to revise timeline because of possibility production will not allow us | R10 | Need to revise timeline | ABP | Week 13 | Delayed | ABP | ADC | MAPP | Ok
| PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade | Delayed | 2024-03-20 | Electrical | Installation of cable tray raceway | wk 12 | Need to revise timeline because of possibility production will not allow us | R10 | Need to revise timeline | ABP | Week 13 | Delayed | ABP | ADC | MAPP | Ok
| PEC2020-Extraction 54 PEC2020 PLC Upgrade | Delayed | 2024-03-20 | Electrical | PO for critical instrument | Wk 11 | PO for CLC CPU - done, waiting for delivery | R09 | Ask ADC for PO Copy | ABP | Week 13 | Delayed | ABP | ADC | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-25 | Mechanical | Cleaning/Polishing of screen window in E54 | Week 12 | Cannot install movable scaffolding due to lifting hoist cannot remove the cell filters beside the window | R06 | Proceed the cleaning in low level portion of the window | KJT | Week 13 | Delayed | KJT | WGE | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-04-01 | Mechanical | Installation of Screen window in E45 | Week 13 | Prioritized E54 scaffolding and polishing of screen window frame | R12 | Overtime of manpower | KJT | Week 14 | Delayed | KJT | WGE | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-03-25 | Mechanical | Cleaning/Polishing of screen window in E54 | Week 12 | Cannot install movable scaffolding due to lifting hoist cannot remove the cell filters beside the window | R06 | Proceed the cleaning in low level portion of the window | KJT | Week 13 | Delayed | KJT | WGE | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-04-01 | Mechanical | Installation of screen window in E45 | Week 13 | Prioritized E54 scaffolding and polishing of screen window frace | R12 | Overtime manpower | KJT | Week 14 | Delayed | KJT | WGE | MAPP | Ok
| Upgradation of Marley Cooling Tower | Delayed | 2024-04-10 | Mechanical | Installation of mechanical components, upper and lower cylinder, and testing of marley #6 | Week 14 | JAV contractor not onsite due to manpower availability | R01 | Priority Delayed activity and pause the advance works (all contractor focus on delayd activities) | ALC | Week 16 | On-track | ALC | JRUS | MAPP | Ok
| PEC2020-Installation of New PE PANELS | Cancellation | 2024-04-11 | Electrical | Timeline adjustment | Week 14 | Unable to perorm the activities due to continuous production run | R09 | Revised timeline to 2025 Annual SD | ABP | Week 30, 2025 | On-track | ABP | ADC | MAPP | Ok
PEC2020-EA Process Adaptation
PEC2020-Extraction 54 PEC2020 PLC Upgrade
PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade
| PEC2020-Replacement of Ventillation duct at loading area(ph1A) | Cancellation | 2024-04-11 | Mechanical | Lifting and installation of ducts Rmoval of obstacles (angle bar, etc) | Week 14 | Area is congested Give way to floor painting activities | R16 | Render OT | DTL | Week 15 | Delayed | DTL | REC | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-04-11 | Mechanical | Kick-off Scope detailing Design Freeze | Week 14 | Scope detailing is on-going route Kick-off cration is on-going Design Freeze approved for construction is on-going routing | R06 | Render OT and time management | DTL | Week 16 | Delayed | DTL | REC | MAPP | Ok
| Safety Upgrade of E54 Cell cover | Delayed | 2024-04-11 | Mechanical | Tagging of lines and equipment | Week 14 | Delay preparation of tags | R06 | Set new timeline, print all tags for preparation | FCT | Week 22 | Delayed | FCT | REC | MAPP | Ok
| Independent CIP for Falling Film Evaporator | Delayed | 2024-04-11 | Mechanical | Finalized SOO, Create program, offline simulation, risk assessment, actual simuation. | Week 14 | Delayed programm creation | R01 | Set new timeline agreed by all stakeholders | FCT | Week 17 | On-track | FCT | REC | MAPP | Ok
| Green Coffee Van Unloading | Cancellation | 2024-04-11 | Electrical | Tapping of temporary LDP power supply, Installation of cable tray droppings, and installation of wirings of GC van tilting for motor controls | Week 14 | Prioritized removal of cable tray ladder and installation of new cable tray and harnessing of wires since it involves working on heights | R12 | Next CIP schedule Provide scaffolding | ABP | Week 18 | On-track | ABP | ADC | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-04-11 | Electrical | Installation of lightning arrester rod | Week 14 | Contractors PEP was declined by SHE due to lacking safety documents | R11 | Cost-plus to back up | MGS | Week 15 | Delayed | MGS | ADC | MAPP | Ok
| PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-04-12 | Mechanical | Scope detailing Kick-off | Week 6 | Need alignment meeting with supplier for technical clarification | R06 | Need alignment meeting with supplier | DTL | TBD, Week 18 | Delayed | DTL | REC | MAPP | Ok
| GC Transport Upgrade Ph 2 | Delayed | 2024-04-12 | Mechanical | Kick-off Scope detailing Design Freeze | Week 8 | Cannot proceed this activity, we need to finish first technical clarification (Dust collector) | R06 | Allignment meeting with supplier | DTL | TBD, Week 18 | Delayed | DTL | REC | MAPP | Ok
| PEC2020-Improvement of Natural Ventilation (window) | Delayed | 2024-04-12 | Mechanical | Installation of flatbar, fullwelding of hinges | Week 14 | Additional scope, installation of flatbar above window | R06 | Manpower overtime | KJT | Week 15 | Delayed | KJT | WGE | MAPP | Ok
| SIR E45 | Cancellation | 2024-04-12 | Mechanical | Installation of E45 Pneumatic cylinder | Week 14 | prioritized self-cleaning (Contractor), No EI to calibrate the load cell and lacking of pin | R13 | Machining of pin and Coordinate with EI | KJT | Week 18 | On-track | KJT | WGE | MAPP | Ok
| GCU+ | Cancellation | 2024-04-12 | Mechanical | Installaition of V5.1 flashing plate in E54 | Week 14 | Plan is to install flashing plate when production costplus will replace V6.1 pipes for cleaning, they cancell the plan cleaning. | R12 | To install next replacement of V6.1 | KJT | Week 18 | On-track | KJT | WGE | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-13 | Mechanical | Delivery of PM, Tuflin and Mixed proof valves | Week 36 | Finalization of P&ID and material list with Paolo and encountered problem in Procurement Processing. | R08 | To follow-up procurement | KJT | Week 46 | On-track | KJT | WGE | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-13 | Mechanical | PO of PM, Tuflin and mixed proof valves | Week 1 | Finalization of P&ID and material list with Paolo and encountered problem in Procurement Processing. | R08 | To follow-up procurement | KJT | Week 22 | On-track | KJT | WGE | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-15 | Mechanical | Design Freeze, Kick-off and Scope detailing | Week 5 | Cancelled Meeting with TCU | R08 | Manpower overtime so that we can present to TCU the pending drawings | KJT | Week 25 | On-track | KJT | WGE | MAPP | Ok
| GC Transport Upgrade Ph 1 | Delayed | 2024-04-20 | Mechanical | Submission of Welding Inspection and 5S | Week 14 | Focus on clearing areas | R12 | Submit on Week 17 | JJA | Week 17 | Delayed | JJA | WGE | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-04-20 | Civil | [10 empty] | MAPP | Ok
| Auto-compactor | Delayed | 2024-04-20 | Civil | Design Freeze on Civil drawing | Week 16 | JCB is un available due to currenty occupied with urgent matters | R06 | Approach him and follow-up | RES | Week 17 | Delayed | RES | WGE | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-04-20 | Civil | Cladding works and Demobilization | Week 15 | Prioritized cleaning of the area for visitor | R12 | OT | SMG | Week 18 | Delayed | SMG | RADY | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-20 | Mechanical | Delayed PO for Valves and sight glass |  | Delayed P&ID and material list approval. Some details were revised | R12 | Focus on the valves and sight glass PR to PO conversion | WGE | 2024-05-01 | Delayed |  | WGE | MAPP | Ok
| PEC2020-Installation of new PE Panel cooling system(PH1b) | Delayed | 2024-04-20 | Mechanical | Delayed PO for PE Panel AHU |  | Prio other projects and urgent support | R12 | Focus on the technical Recon and PR to PO process | WGE | 2024-07-01 | Delayed |  | WGE | MAPP | Ok
| GC Transport Upgrade Ph 2 | Delayed | 2024-04-20 | Mechanical | PO for dust collector | Week 16 | Under technical clarification with WGE and TCU | R10 | Set allignment meeting with TCU | DTL | Week 22 | Delayed | DTL | WGE | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-04-20 | Mechanical | Design Freeze | Week 16 | JCB is unavailable for the past week to sign the documents | R05 | Approach him and follow-up | ZAF | Week 18 | Delayed | ZAF | WGE | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-04-20 | Mechanical | Scope detailing | Week 16 | MAPP declined to sign due to lacking of documents. Add electrical and civil works | R06 | Add electrical and civil works then load to docusign | ZAF | Week 21 | Delayed | ZAF | WGE | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-04-20 | Mechanical | Kick-off fully signed | Week 16 | Short on time | R06 | Time management of SE | ZAF | Week 21 | Delayed | ZAF | WGE | MAPP | Ok
| SCRF (self cleaning rotary filter) | Delayed | 2024-04-20 | Mechanical | Missed alignment meeting with TCU | Week 14 | TCU availability | R05 | Ask for another date | FCT | Week 17 | Delayed | FCT | WGE | MAPP | Ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-04-20 | Mechanical | Delay delivery of rotary filter | Week 16 | Supplier have issues with materials and logistics | R01 | Follow-up for new timeline | FCT | Week 17 | Delayed | FCT | WGE | MAPP | Ok
| Auto-compactor | Delayed | 2024-04-20 | Mechanical | Delayed material purchasing | Week 16 | Difficulty finding exact specs for screeb | R09 | Ask Joors for new timeline | FCT | Week 17 | Delayed | FCT | WGE | MAPP | Ok
| Upgradation of Soft water plans | Delayed | 2024-04-22 | Mechanical | PEP Approval | Week 13 | Lack of SHE requirements: Hot work and Work on heights | R11 | Coordinate and conduct alignment meeting with contractors | BDY | Week 17 | Delayed | BDY | JRUS | MAPP | Ok
| Upgradation of Soft water plans | Delayed | 2024-04-22 | Mechanical | Mechanical Works | Week 9 | On-going routing of CRF | R11 | Follow-up PIC for the signatories | BDY | Week 20 | Delayed | BDY | JRUS | MAPP | Ok
| Upgradation of Soft water plans | Delayed | 2024-04-27 | Mechanical | PEP Approval | Week 17 | PEP not yet approved by SHE and lacking of requirements in PEP | R01 | Issue site instruction and coordinate with contractor PIC | BDY | Week 18 | Delayed | BDY | JRUS | MAPP | Ok
| Upgradation of Marley Cooling Tower | Delayed | 2024-04-27 | Mechanical | Testing of Marley cooling tower #6 and #9 | Week 17 | Additional fabrication and installation of torque tube assymbly in cooling tower #6 and #9 | R06 | On-going extention of test run until Monday | ALC | Week 18 | Delayed | ALC | JRUS | MAPP | Ok
| PEC2020-Replacement of Ventillation duct at loading area(ph1A) | Delayed | 2024-05-01 | Mechanical | Delivery of fabricated ducting | 2024-05-01 | Fabricated ducts failed in line release (1/4) | R06 | Re-check quality standard | Fedcon | 2024-05-02 | Delayed | DTL | REC | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-27 | Mechanical | Aproval of P&ID | Week 17 | Cancelled Meeting with TCU due to TCU is not available | R06 | Moved meeting with TCU | KJT | Week 18 | Delayed | KJT | WGE | MAPP | Ok
| PEC2020-Process Adaptation ( Mechl ) | Delayed | 2024-04-27 | Mechanical | Design modification and URS Finalization (approved) | Week 17 | Factory engineer busy | R05 | set follow-up schedule for signatory | KJT | Week 18 | Delayed | KJT | WGE | MAPP | Ok
| Green Coffee Van Unloading | Cancellation | 2024-04-30 | Electrical | Tapping of temporary LDP power supply (380VAC) | Week 18 | Area is not available due to inventory of stocks and early start-up of production | R10 | Next CIP schedule | ABP | Week 23 | On-track | ABP | ADC | MAPP | Ok
| Green Coffee Van Unloading | Delayed | 2024-05-03 | Mechanical | Mechanical Works | Week 17 | Delayed PO release | R14 | To meke new timeline and close monitoring on the delivery of dust colector | SMG | Week 27 | Delayed | SMG | RADY | MAPP | Ok
| GCU+ | Cancellation | 2024-05-04 | Mechanical | Fit-up of V6 and V6.1 spare pipe of cell 5 and 6 Fit-up V4 spare splt flange of cell 3 and 4 | Week 18 | not enough time to finish the job. Schedule was change from 2 days to 7 hours. Moved to next CIP | R06 | Moved to next CIP | KJT | Week 23 | Delayed | KJT | WGE | MAPP | Ok
| AFBB Smokestack | Delayed | 2024-05-06 | Civil | Installation of cladding | Week 18 | Personnel still comply the requirement | R04 | Follow-up contractor and advise to OT | SMG | Week 20 | Delayed | SMG | RADY | MAPP | Ok
| Auto-compactor | Delayed | 2024-05-06 | Civil | Design Freeze | Week 18 | Revise drawing from area owner | R06 | Fast track the revised drawing and approval |  |  |  | SMG | RADY | MAPP | Ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-05-09 | Mechanical | PO of valves and mechanical works | Week 18 and 19 | 1. Qoutation from supplier not yet submitted 2. Technical Evaluation for Mechanical works was delayed | R14 | 1. Follow-up Procurement for the qoutation of the supplier 2. Check the availability of pump and valves at technical stores 3. Ask procurement to priority the release of PO for mechanical works | FCT | Week 20 (Qoutation from supplier) | Delayed | FCT | REC | MAPP | ok
| Improvement of FFE RARE Filtering System | Delayed | 2024-05-09 | Mechanical | Delivery of Rotary Filter | Week 17 | Manufacturing of equipment was delayed | R01 | Monitor and send email for the supplier regarding the delivery of equipment | FCT | Week 26 (As per supplier) | Delayed | FCT | REC | MAPP | ok
| Independent CIP for Falling Film Evaporator | Delayed | 2024-05-09 | Mechanical | The functionality Test was completed 50% only because the program licensed from mheco was expired | Week 18 | Licensed Program from mheco was expired | R06 | Update licensed program and make a back up planned | Chis/REC | Week 19 | Delayed | FCT | REC | MAPP | ok
| GC Transport Upgrade Ph 2 | Delayed | 2024-05-09 | Mechanical | 1. Scope Detailing 2. Design Freeze 3. URS | Week 18 and 19 | The project concept was delayed because as per TCU, the dust collector should be separate (Green coffee and Roasted Coffee) | R08 | Schedule alignment meeting with production the concept of dust collection | WGE | Week 20 | Delayed | WGE | REC | MAPP | ok
| Auto-compactor | Delayed | 2024-05-09 | Mechanical | Delivery of mechanical (Fabrication Works) | Week 19 | The PO releasing of mechanical works was delayed | R01 | Monitor the fabrication work, as per update. Fabrication works will be completed on week 22 | REC | Week 22 | Delayed | FCT | REC | MAPP | ok

## Count
Reason Code Legend |  | Project Title | # of Catch - up reportd | Reason Code
| 7 |  |  | R01 | R02 | R03 | R04 | R05 | R06 | R07 | R08 | R09 | R10 | R11 | R12 | R13 | R14 | R15 | R16
R01 | Time commited by contractor is not followed
R02 | 3RD party logistic issue (Delivery of Materials) | GC Transport Upgrade Ph 1 | 7 | Reason Code R01: 0; Reason Code R03: 1; Reason Code R12: 1
R03 | No available SO from contractor | GC Transport Upgrade Ph 2 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
R04 | Key personnel not available | Green Coffee Van Unloading | 13 | bar: Reason Code R01
R05 | PIC/stakeholders availability | Improvement of FFE RARE Filtering System | 6 | Reason Code R01: 2
R06 | Others | AFBB Smokestack | 8 | Reason Code R01: 0
R07 | SHE Violation/Issue | SCRF (self cleaning rotary filter) | 4 | Reason Code R01: 0
R08 | Alignment to TCU Standard | Auto-compactor | 9 | bar: Reason Code R01
R09 | Materials did not arrive | Independent CIP for Falling Film Evaporator | 8 | bar: Reason Code R01
R10 | For Alignment meeting | Upgradation of Soft water plans | 5 | bar: Reason Code R01
R11 | PEP not yet approved | Upgradation of Marley Cooling Tower | 3 | bar: Reason Code R01
R12 | Other priority | Project Horizon 1 | 0 | Reason Code R01: 0
R13 | Lack of man power | Project Horizon 2 | 0 | Reason Code R01: 0
R14 | PO release | Zurich Gap Closure | 1 | Reason Code R01: 0
R15 | Approval of URS | PEC2020-Improvement of Natural Ventilation (window) | 7 | Reason Code R01: 0
R16 | On-hold | PEC2020-Installation of New PE PANELS | 2 | Reason Code R01: 0
|  | PEC2020-EA Process Adaptation | 2 | Reason Code R01: 0
| 7 | PEC2020-Program Development for PEC2020 | 0 | Reason Code R01: 0
| 0 | PEC2020-Extraction 54 PEC2020 PLC Upgrade | 2 | Reason Code R01: 0
|  | PEC2020-DMO GCU+ | 0 | Reason Code R01: 0
|  | PEC2020-E54 MCC PANEL Upgrade and Motor Control Upgrade | 2 | Reason Code R01: 0
|  | PEC2020-Upgrade of cooper tubes to steel braided hose etc. | 0 | Reason Code R01: 0
|  | PEC2020-Installation of new PE Panel cooling system(PH1b) | 4 | Reason Code R01: 0
|  | PEC2020-Replacement of Ventillation duct at loading area(ph1A) | 3 | Reason Code R01: 0
|  | PEC2020-Process Adaptation ( Mechl ) | 12 | Reason Code R01: 0
|  | Safety Upgrade of E54 Cell cover | 2 | Reason Code R01: 0