## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
S8APNAURRkSjyCQvPPYzZJYAF0E2 | Fully signed URS of Relief Valve and CIP pump for new scope | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
uL0kePJnRkSQRQOhlh2lW5YAHH2W | URS of Relief Valve and CIP pump for new scope | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
hXT-cXwd7UW2qtrnkCXM05YAGSQ6 | Pre-bidding of Group 4 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 02/14/2025 | false | false
ftatfYwW7U2-sGlBPakr-5YANNT7 | Pre-bidding of Group 3 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/30/2024 | false | false
UwM4R4m6EUywuHZupaUUTpYACvjC | Pre-bidding of Group 2 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 | 07/05/2024 | 07/26/2024 | false | false |  |  |  |  | CATCH-UP PLAN
lrp6a0nAm0WfHDusaoWUsJYAKHLU | Pre-bidding of Peter Meyer | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 10/11/2024 | false | false
8EWXTMGXeEOedhszRKFWi5YADuok | Pre-bidding of Tuflin Valve | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 10/04/2024 | false | false
vIQlWyyrY0SEaZVwUw8RypYAMYLh | Fully signed Construction drawing for Group 3: Doc 22 and 26 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/09/2024 | false | false
ok-roSEL5UaoRMhHd012fpYAKDsX | Construction drawing for Group 3: Doc 22 and 26 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Mangayan,Billy Joe,PH-Cagayan de Oro,Engineering,External;Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Vecina,Jimmer,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/02/2024 | false | false
11lWqsfKO0G6_dFiicgqrJYAFyE7 | Fully signed Construction drawing for Group 3: Doc 2, 8, 14, 15 and 24 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/02/2024 | false | false
CsxkEmG4YkW9B8tprtuKSpYAK0W2 | Construction drawing for Group 3: Doc 2, 8, 14, 15 and 24 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Mangayan,Billy Joe,PH-Cagayan de Oro,Engineering,External;Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Vecina,Jimmer,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/26/2024 | false | false
aKCeCFOeyUK9qqcf0Af8dJYAKBbt | Fully signed Construction drawing for Group 3: Doc 1, 3, 10, and 11 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/26/2024 | false | false
Q_mRP5lfpUW6NH97Akmt2ZYAAx2i | Construction drawing for Group 3: Doc 1, 3, 10, and 11 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Mangayan,Billy Joe,PH-Cagayan de Oro,Engineering,External;Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Vecina,Jimmer,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
K0OqsCBCPkKsoekv05CfC5YAGgta | Fully signed Construction drawing for Group 2: Doc 21 (1 and 2 of 4) | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
uuGRdeBlt0eZ0H2WiReXdpYAOdTB | Construction drawing for Group 2: Doc 21 (1 and 2 of 4) | PEC2020 - (EA) Process Adaptation | Not started | Medium | Mangayan,Billy Joe,PH-Cagayan de Oro,Engineering,External;Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Vecina,Jimmer,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 | 07/05/2024 | 07/19/2024 | false | false |  |  |  |  | CATCH-UP PLAN
BsLAGQ1hmUOBpbgWSboqjJYAKZj- | Fully signed Construction drawing for Group 1: Doc 4, 5, 7, 9, and 12 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
kb8WHM3mxkCMu4dIzYgvVZYAGHAd | Construction drawing for Group 1: Doc 4, 5, 7, 9, and 12 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Mangayan,Billy Joe,PH-Cagayan de Oro,Engineering,External;Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Vecina,Jimmer,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
m6pS75fJaEyzAaYrJu_3sJYANSBp | Design Freeze P&ID (from TCU) | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 | 07/05/2024 | 07/26/2024 | false | false |  |  |  |  | CATCH-UP PLAN
qFqlwqBIYUmPcift9FQJFZYACPwR | Fully signed Scope detailing of Group 4: Doc 28 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 11/15/2024 | false | false
PRuwjl4Gc0OT0SqzNAqMvZYAIpQp | Scope detailing of Group 4: Doc 28 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 11/08/2024 | false | false
1wdxjp3M9EGcXpBnTjL7kZYAI7pK | Fully signed Scope detailing of Group 3: Doc 14, 22 and 26 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/26/2024 | false | false
BHuu_OTbt0Cqk5G7JNR_aZYAMQIY | Scope detailing of Group 3: Doc 14, 22 and 26 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
QNbEiI64GESU4F_BBmnDH5YACv0l | Fully signed Scope detailing of Group 3: Doc 1,2,3,8,10,11,15 and 24 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
UbBISz40IECrl2OaZvmFTJYAI7i7 | Fully signed mechanical Project Kick-off | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 12/20/2024 | false | false
08GNnXHklE-m8SIknMJOx5YAKlaN | Project Kick-off (Mechanical) | PEC2020 - (EA) Process Adaptation | Not started | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 12/13/2024 | false | false
JDxPTpxeHkyCJqcbKhypGZYACRs- | Delivery of Cooling duct | PEC2020 - PE Panel cooling system | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 10/04/2024 | false | false
Jr7nOUoq9kKD0372dNJtUJYAK1aX | Delivery of ACU | PEC2020 - PE Panel cooling system | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 10/11/2024 | false | false
h1Oq-WZVQkamORfBZdIk-ZYAMOhw | PO release of Mechanical Works | PEC2020 - PE Panel cooling system | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/30/2024 | false | false
EMs3oLbsBUifYMr6SLkn55YAKXPE | PO conversion of ACU | PEC2020 - PE Panel cooling system | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
H9WavTRw_kOmROG05k2sNZYAOgmZ | PR conversion of Mechanical Works | PEC2020 - PE Panel cooling system | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
MIyGQVhoJEG7XVhk3knJMpYAMVjK | Fully signed URS of ACU | PEC2020 - PE Panel cooling system | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
aCGNGxoKSES4mgs_eslgBpYACODT | URS of ACU | PEC2020 - PE Panel cooling system | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
sd2pGqn1QUiDO208itnhm5YACd2l | Fully signed Detailed drawing for Freon or Chilled water | PEC2020 - PE Panel cooling system | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
6PIu7yO76U6Yz5yY9I_WQZYALuCu | Detailed drawing for Freon or Chilled water | PEC2020 - PE Panel cooling system | Not started | Medium | Nagales,Reymart,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
ewXmt_4N8Ee1KuLASVakW5YAFCQ9 | Fully signed Mechanical scope detailing | PEC2020 - PE Panel cooling system | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/26/2024 | false | false
7ztV2VbLeECpjp0vCaAmpZYAI6nz | Scope detailing - Mechanical | PEC2020 - PE Panel cooling system | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
IttKR-YV_UeyBFElyfgrHJYAPlcr | Fully signed Cable Tray Fabrication drawing | PEC2020 - Upgrade of Cooper tubes to Polyflo | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 09/27/2024 | false | false
G3dyLITLaESMCcw2F1YZqZYAJPMz | Fully signed Cable Tray Construction drawing | PEC2020 - Upgrade of Cooper tubes to Polyflo | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 09/27/2024 | false | false
DHAfsmVtQke-BEQjbLg01pYAJu7E | Cable Tray Construction drawing | PEC2020 - Upgrade of Cooper tubes to Polyflo | Not started | Medium | Ballentos,Shanel,PH-Cagayan de Oro,Manufacturing,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 09/20/2024 | false | false
7vDOB1fe4UmyvCVtf_tES5YAFb-q | Cable Tray Fabrication drawing | PEC2020 - Upgrade of Cooper tubes to Polyflo | Not started | Medium | Ballentos,Shanel,PH-Cagayan de Oro,Manufacturing,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 09/20/2024 | false | false
zXofKtGls0qqWrC53qpDf5YAGRSI | Fully Signed Scope detailing | PEC2020 - Upgrade of Cooper tubes to Polyflo | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 03/14/2025 | false | false
O9qcisAYokyWTY7R_4R5y5YAKb8h | Scope detailing | PEC2020 - Upgrade of Cooper tubes to Polyflo | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 03/07/2025 | false | false
SAM5dnNRfkGPf0qmoIzSppYAFZHi | Fully signed Project Kick-off | PEC2020 - Upgrade of Cooper tubes to Polyflo | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 04/11/2025 | false | false
zpT_ZCP4eE2F4iAbFyvFN5YAB5wd | Project Kick-off | PEC2020 - Upgrade of Cooper tubes to Polyflo | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 04/04/2025 | false | false
lsUoeFYwbUOiFYb1q4eBapYABLvM | Establish Governance meeting, ASI, and governance meeting | PEC2020 - Upgrade of Cooper tubes to Polyflo | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 02/07/2025 | false | false
RVqfNWLqeUKsMg0GzkmepJYANVFx | Delivery of Additional material | PEC2020 - MCC Panel Upgrade and Motor Contor Update | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/29/2025 | false | false
RV6V6tRSJkqmndIkphGLvJYAA55l | PO of additional materials | PEC2020 - MCC Panel Upgrade and Motor Contor Update | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  |  | false | false
8cT-ZcMoZEGoFHCv6u-X5ZYAHaT2 | PR of additional materials | PEC2020 - MCC Panel Upgrade and Motor Contor Update | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  |  | false | false
fQhBbdlTbUqfjfCbSA9peZYAKN4X | Fully Signed Project Kick-off | PEC2020 - PE Panel cooling system | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/31/2025 | false | false
8m4CTM_y2UOGM3Jx9qJzLJYAGuAJ | Fully Signed Project Kick-off | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 05/30/2025 | false | false
RVea-mBeF02qWgGEahdZdZYAHNjN | Fully signed Project Kick-off | PEC2020 - PLC Upgrade | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 05/30/2025 | false | false
bmULzdBlZEml4XLbEdiI0ZYAG2Fp | Fully Signed Project Kick-off | PEC2020 - MCC Panel Upgrade and Motor Contor Update | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 03/14/2025 | false | false
XaoBPIFS3EGzceUaRaB0gpYAJcl9 | Project Kick-off | PEC2020 - MCC Panel Upgrade and Motor Contor Update | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 03/07/2025 | false | false
KjU6J_Q56UiCjxF0MsmCl5YAHj3w | Fully signed PLC Panel Construction drawing | PEC2020 - PLC Upgrade | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/30/2024 | false | false
bxQ-iHI2f0uks6cB7YMOiZYAEy7j | Fully signed PLC Panel Fabrication drawing | PEC2020 - PLC Upgrade | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/30/2024 | false | false
R_jIivFraUKHrZR03YFNXJYAMc0M | Fully signed Cable Tray Construction drawing | PEC2020 - PLC Upgrade | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/30/2024 | false | false
dB8-Joi2fEWKnfUpeFUBvJYACMPf | Fully signed Cable Tray Fabrication drawing | PEC2020 - PLC Upgrade | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/30/2024 | false | false
JzOAg0RuuEKSslUOKdfbJZYALXbc | PLC Panel Construction drawing | PEC2020 - PLC Upgrade | Not started | Medium | Ballentos,Shanel,PH-Cagayan de Oro,Manufacturing,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/23/2024 | false | false
D3m3l1nlDEWOs_uNkT8CfJYAIvDR | PLC Panel Fabrication drawing | PEC2020 - PLC Upgrade | Not started | Medium | Ballentos,Shanel,PH-Cagayan de Oro,Manufacturing,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/23/2024 | false | false
Zky2ffpU70yC_BWvG1_xpZYAFAke | Cable Tray Construction drawing | PEC2020 - PLC Upgrade | Not started | Medium | Ballentos,Shanel,PH-Cagayan de Oro,Manufacturing,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/23/2024 | false | false
Tit3Jmx_REOBMKYmcDYrwJYANWPR | Cable Tray Fabrication drawing | PEC2020 - PLC Upgrade | Not started | Medium | Ballentos,Shanel,PH-Cagayan de Oro,Manufacturing,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/23/2024 | false | false
qBY6J4OND0-1rIcCFuyc0ZYAJYVd | Project Kick-off | PEC2020 - PLC Upgrade | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 05/23/2025 | false | false
kSBt8ZjH4EG8KSgCMCdS05YAPNUo | Delivery of Valve terminal, sensors, and control cables | PEC2020 - (EA) Process Adaptation | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/25/2025 | false | false
X5o64n_HuUiFMxi6WvYbm5YAAc-Z | PO release of Valve terminal, sensors, and control cables | PEC2020 - (EA) Process Adaptation | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 04/25/2025 | false | false
adH1V_P86kG2LY3mILhiiJYAJpy9 | PO release of Festo Valve Terminal & Instruments for PEC2020 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 04/25/2025 | false | false
YB1GAZ2dEka3nMolmujBN5YAIOjd | PR conversion of Valve terminal, sensors, and control cables | PEC2020 - (EA) Process Adaptation | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 10/18/2024 | false | false
j9HTS4wfcUyGGIJ86fTqa5YAHSuZ | PR conversion of Festo Valve Terminal & Instruments for PEC2020 | PEC2020 - (EA) Process Adaptation | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 10/18/2024 | false | false
egjsiTrUw0GyvNsd2CvprJYAD-7f | Fully signed URS of Festo Valve | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 02/28/2025 | false | false
W2o65gfbn06uaVkYqbv4bZYAMSvA | URS creation of Festo Valve & Instruments | PEC2020 - (EA) Process Adaptation | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 02/21/2025 | false | false
jsgN-zVAzkuYUeEGO71ngZYAKQEd | Fully signed Cable tray Construction drawing | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 10/25/2024 | false | false
_Uu4YpXt4ki2cTwOpy6BtpYAOmeT | Cable tray Construction drawing | PEC2020 - (EA) Process Adaptation | Not started | Medium | Ballentos,Shanel,PH-Cagayan de Oro,Manufacturing,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 10/18/2024 | false | false
oHBR9QQH202WsNfiFU-jf5YAH82d | Fully signed Cable tray Fabrication drawing | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 09/27/2024 | false | false
vGyltFQtUkyIR7s47nzkvZYAJ0V4 | Cable tray Fabrication drawing | PEC2020 - (EA) Process Adaptation | Not started | Medium | Ballentos,Shanel,PH-Cagayan de Oro,Manufacturing,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 09/20/2024 | false | false
PpjlS-Y8qUKgzCUjw7s7a5YAFBVB | Fully signed Scope detailing | PEC2020 - (EA) Process Adaptation | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 05/16/2025 | false | false
j0HcRDH50UqCyEulmMuzfJYAG2p3 | Create Scope Detailing | PEC2020 - (EA) Process Adaptation | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 05/09/2025 | false | false
_29W3P-T1UmDrp2rnz-JEJYAGaZM | Project Kick-off | PEC2020 - (EA) Process Adaptation | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 05/16/2025 | false | false
7IOXhEjl8E6C81QTCyGP4JYANBIB | Project Kick-off | PEC2020 - PE Panel cooling system | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/25/2025 | false | false
IehKXb2I60u1q3cudI3wjZYAIz6u | Delivery of additional control cables | PEC2020 - PE Panel cooling system | Not started | Medium | Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 05/30/2025 | false | false
w0v3Q4wTb0mm6oA4q8rsPZYACcY1 | PO release of Additional Control Cables and Cable trays | PEC2020 - PE Panel cooling system | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/30/2024 | false | false
akc8BhvG60KBG6RoKFGfsZYAC3Mh | Submission of Catch-up plan reports | Reminders | Not started | Medium | Galicia,Shella Mae,PH-Cagayan de Oro,Engineering,External;Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Tadena,Francis Carlo,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External;Salvana,Myka,PH-Cagayan de Oro,Engineering,External;Suello,Rosiell,PH-Cagayan de Oro,Engineering,External;Yap,Brian,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 | 07/05/2024 | 12/31/2024 | true | false
DAMS4sic8ESehdOJW7YfGJYAPVXn | Timeline Update | Reminders | Not started | Medium | Galicia,Shella Mae,PH-Cagayan de Oro,Engineering,External;Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Tadena,Francis Carlo,PH-Cagayan de Oro,Engineering,External;Pacatan,Arnold,PH-Cagayan de Oro,Engineering,External;Salvana,Myka,PH-Cagayan de Oro,Engineering,External;Yap,Brian,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 | 07/04/2024 | 12/31/2024 | true | false
axfJiI1LekCjHrVzChKny5YAMXy4 | Delivery of Pipes | E54 High Pressure Water Heater | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 12/13/2024 | false | false
zd9s51s7HEudN0hNK5YC4JYAMZTA | Delivery of Water Heater Equipment | E54 High Pressure Water Heater | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 11/29/2024 | false | false
QiU7ng6vV0eFK8YPF0zha5YAD6hZ | PO release for Mechanical Works | E54 High Pressure Water Heater | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/23/2024 | false | false
fsfmBYDLAUed41eN3JLry5YALPB6 | Pre-bidding for Mechanical Works | E54 High Pressure Water Heater | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
wh1b4q0XeUKsMsA-gVVezZYACTvJ | PR for Mechanical Works | E54 High Pressure Water Heater | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
x-SORs2P40eY6r5-R_Ljz5YAMtr1 | Fully signed URS | E54 High Pressure Water Heater | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/26/2024 | false | false
ym07GL4nuESTYHeTGwhrT5YACt0t | Fully Signed drawing of High Pressure Water Heater | E54 High Pressure Water Heater | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
l2BFQ5brS0CwpxerlqWEx5YALIjD | Construction drawing of High Pressure Water Heater | E54 High Pressure Water Heater | Not started | Medium | Nagales,Reymart,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
l_S_xTKnqEGMQgtW-vd3apYAA16A | Fully signed Scope detailing | E54 High Pressure Water Heater | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/19/2024 | false | false
_nesj__zdUyJbbOt_byYzJYAA4fP | Creation of Scope Detailing | E54 High Pressure Water Heater | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
Uw4UUs0UK02cNRklTLxczZYAJve6 | Fully signed Project Kick-off | E54 High Pressure Water Heater | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/31/2024 | false | false
KWMQQ7Wr50G2zg2YVjC_P5YADJ4D | Project Kick-off | E54 High Pressure Water Heater | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/26/2024 | false | false
or3JIKm3PUme48dO_lG9mJYAKD7P | Delivery of Pump | Softwater | Not started | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External;Yap,Brian,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/26/2024 | false | false
a9GMn9qnSUqLMnjss1I-jJYACTGq | Delivery of Fabrication Works | FFE RARE | In progress | Medium | Tadena,Francis Carlo,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 09/03/2024 | false | false
izC0CEyr40KoqnyCWlK-t5YAJjaX | Delivery of Rotary Filter and Accessories | FFE RARE | In progress | Medium | Tadena,Francis Carlo,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/26/2024 | false | false
kp1U28JIAU-vk-rO59uziJYADNyw | Delivery of Civil Materials | FFE RARE | Not started | Medium | Galicia,Shella Mae,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
TDyMVFF-WEKepbZt555irZYAJwzb | PO release for Civil Works | FFE RARE | Not started | Medium | Galicia,Shella Mae,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 | 07/05/2024 | 07/12/2024 | false | true
lUE61XBZ1U2FAZGSIDo7-5YAMYda | PR release for Civil Materials | FFE RARE | Not started | Medium | Galicia,Shella Mae,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 | 07/05/2024 | 07/12/2024 | false | true |  |  |  |  | CATCH-UP PLAN
lI8D7H0oqEScMSNkU5n-KJYAD1Xa | Delivery of Dust Collector | Van Tilting | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
Fbrek4Bz2EqOGv5r0oWO0ZYADlfo | Delivery of Dust Collector and Duct | GC Transport PH2 | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 02/07/2025 | false | false
e29vKJ0R1E2_iqmcmsLwB5YAFmWh | PO Release for Mechanical Works | GC Transport PH2 | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 10/31/2024 | false | false
dYvwqOc8H0KaU2SHorMr7pYAHT_H | PO release for Dust Collector | GC Transport PH2 | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 08/16/2024 | false | false
ykeo8d-ovUGsGY4n6XR7vpYAP3do | Pre-bidding for Mechanical Works | GC Transport PH2 | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 09/13/2024 | false | false
HLNS14i-F0qn400PTXiTj5YAOGUI | Pre-bidding for Dust Collector | GC Transport PH2 | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/05/2024 | false | true
qozWM9fwNkW-_FPLUVmD6JYAKWRY | PR for Mechanical Works | GC Transport PH2 | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 09/13/2024 | false | false
ow3mBvFXOEyK5PuQdn3FSJYAEy4Z | PR for Dust Collector | GC Transport PH2 | Not started | Medium | Las Piñas,Dennis,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/05/2024 | false | true
1SpIpIETvkScbFihjXts6pYAI0lT | Fully Signed Design Freeze for P&ID | GC Transport PH2 | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
XlnA1B4qpkatqf-h6TlePJYAEYaD | Fully Signed Design Freeze for Piping Lay-out | GC Transport PH2 | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true
1jClaOwwv0iO-zVaQxW3tZYAKy1z | Creation of Design Freeze for P&ID | GC Transport PH2 | Not started | Medium | Nagales,Reymart,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/10/2024 | false | true
-kazeqqA2EGxiJ14zpFDjpYALoca | Creation of Design Freeze for Piping Lay-out | GC Transport PH2 | Not started | Medium | Nagales,Reymart,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/10/2024 | false | true
GXSOhE-jB0iV_FVwFlMcdJYACJcB | Creation of Design Freeze for Dust Collector | GC Transport PH2 | Not started | Medium | Nagales,Reymart,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/10/2024 | false | true
-HSgex3d-keTvOed7xmNwpYAKIRR | Fully Signed Design Freeze for Dust Collector | GC Transport PH2 | Not started | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | true | [5 empty] | Assign tasks to yourself or team members
F7oanfR0-U2sRhXmu6bF65YADLGy | PO release of Rotary Filter | FFE RARE | Completed | Medium | Tadena,Francis Carlo,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/26/2024 | false | false | 07/11/2024 | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External
oHmPWxV8J0e1WaA9XV1o-pYALP8P | Scope detailing of Group 3: Doc 15 | PEC2020 - (EA) Process Adaptation | Completed | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 | 07/05/2024 | 07/12/2024 | false | false | 07/10/2024 | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External
iYmgHV7qbUeHVFFkdt_Rg5YALggj | Fully signed Scope detailing of Group 2: Doc 21 | PEC2020 - (EA) Process Adaptation | Completed | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 07/12/2024 | false | false | 07/05/2024 | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External
IJgEnDc_yEiP6ukIZKqxKpYAAuio | Scope detailing of Group 2: Doc 21 (1 of 4 and 2 of 4) | PEC2020 - (EA) Process Adaptation | Completed | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 06/28/2024 | false | false | 07/05/2024 | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External
DtU0giyqmkCd9-q_ZbpCjJYAOtrE | Scope detailing of Group 3: Doc Doc 1,2,3,8,10,11, and 24 | PEC2020 - (EA) Process Adaptation | Completed | Medium | Suello,Rosiell,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/05/2024 |  | 07/02/2024 | false | false | 07/05/2024 | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External
fj7t9rzLr0qQi1NeAY76gJYACp6F | Pre-bidding of PE Panel cooling system Mechanical Works | PEC2020 - PE Panel cooling system | Completed | Medium | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | 07/05/2024 |  | 07/05/2024 | false | false | 07/05/2024 | Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External
hoKkgptdFEyiiJocsFe8TZYADN3s | Pre-bidding of Group 1 | PEC2020 - (EA) Process Adaptation | Completed | Medium | Tion,Kurlstein Jmaes,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 |  | 06/21/2024 | false | false | 07/05/2024 | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External
TTfeK-IKnk6g6WHCWTZoqJYAMBbv | PO release of Mechanical Works | FFE RARE | Completed | Medium | Tadena,Francis Carlo,PH-Cagayan de Oro,Engineering,External;Dairo,Ritchel,PH-Cagayan de Oro,Engineering,External | Cabilogan,Khryssmae Rose,PH-Cagayan de Oro,Engineering,External | 07/02/2024 | 05/15/2024 | 07/05/2024 | false | false | 07/04/2024 | Tadena,Francis Carlo,PH-Cagayan de Oro,Engineering,External

## Plan name
Plan name | Project Timeline Update
Plan ID | qtAtdWK_D0OziKYbqokbPpYAFY-S
Date of export | 07/13/2024